## Doc Control
Document Control
Date | Version | Author | Remarks
2015-12-29 | v1.0 | Zaki | Doc Creation
2015-12-29 | v1.1 | Zaki | Renamed: - RPCR 628 -> R4.1.2 - R4.1.2 -> R4.2
2015-12-31 | v1.2 | Zaki | 1. Added PCR581 to scope of R4.1.2 2. Added R4.1.3 to raise Teller SO Limit (R/O:31st Jan)
2016-01-06 | v1.21 | Zaki | - Added PCR 637 to scope of R4.3
2016-01-18 | v2.0 | Zaki | - Added schedule for VISA BIN - Added 4 new defects for R4.2 (4495, 4496, 4497, 4498) - R4.1.3 Release date brought forward to 27th Jan
2016-02-02 | v2.1 | Zaki | - Added 2 new defects for R4.2 (4507, 4508)
2016-02-09 | v2.1.1 | Zaki | - Added 2 defects for R4.2 (4375, 4484) - Removed 2 defects for R4.2 (4414, 4508)
2016-03-10 | v3.0 | Zaki | - Added plans for R4.2.1 & R5.0 - First baseline of scope for R5.0
2016-03-15 | v3.1 | Zaki | - Added plans for R5.1 - First baseline of scope for R5.1
2016-04-04 | v3.2 | Zaki | - Added Defects 4514 & 4545 for R5.0 - Amended plans for R5.1 - Removed PCR 576 from scope of R5.1
2016-05-06 | v3.3 | Zaki | - Amended Plans for R5.1 - Added minor release R5.0.1
2016-06-06 | v3.4 | Zaki | - Added Schedule and Scope for R5.2 - Added Schedule for R5.3
2016-06-07 | v3.4.1 | Zaki | -Amended SIT schedule for R5.3 Regional Link
2016-06-08 | v3.4.2 | Zaki | -Amended SIT schedule for R5.2 -Added 6 new defects for R5.2
2016-07-08 | v3.4.3 | Zaki | -Added 2 new defects for R5.2 originating from SIT
2016-07-26 | v3.5 | Zaki | - Added scope for R5.3 - Amended schedule for R5.3 - Added scope & schedule for Emer release R5.2.1
2016-07-29 | v3.5.1 | Zaki | -Removed #4573 & #4601 from scope of R5.3
2016-08-16 | v3.6 | Yusrin | -Rebaseline scope and timeline for R5.4
2016-08-17 | v3.6.1 | Yusrin | -Drop #3970(PCR468) and #4395 (PCR624) -Add #4536 and #4515 -Amended schedule Regional Link SSW SIT - 22/8 until 23/9 -Amended schedule Regional Link SSW UAT - 29/9 until 7/10
2016-08-24 | v3.6.2 | Yusrin | Add #4563(PCR 649), #4586 (PCR655), #4610 (PCR661) Removed #4373(PCR607) Removed #4536 and #4515
2016-09-07 | v3.6.3 | Yusrin | -Added Schedule and Scope for R5.3.1 -Added Schedule and Scope for R5.3.2
2016-09-19 | v3.6.4 | Yusrin | -Revise scope and timeline for R5.4 -Added Schedule and Scope for R5.5 -Added #4622 to REL5.5
2016-09-24 | v3.6.5 | Yusrin | -Drop #4118 from REL5.5
2016-10-05 | v3.6.6 | Yusrin | -Drop PCR591#4325, PCR460#3954 and PCR470#3923 from REL5.5 -Added Defect #4628, #4629 to REL5.5
2016-10-12 | v3.6.7 | Yusrin | -Added Defect #4508, #4519, #4520, #4524, #4479, #4531 and #4635
2016-10-16 | v3.6.8 | Yusrin | -Drop Defect #4531
2016-10-18 | v3.6.9 | Yusrin | -Drop Defect #4627 and #4542 from REL5.5 -Added Defect #4627 and #4542 to REL5.4
2016-10-22 | v3.6.10 | Yusrin | -Added Defect #4640 and #4641 to REL5.4
2016-11-03 | v3.6.11 | Yusrin | -Added Defect #4644 to REL5.4 -Amended Implementation date for REL5.5
2016-11-24 | v3.6.12 | Yusrin | -Added Defect #4644,#4637,#4645,#4649,#4646,#4647,#4650,#4651 to REL5.5
2016-11-01 | v3.7 | Yusrin | -Added Scope and Schedule for REL5.6
2016-11-14 | v3.7.1 | Naga | -Added additional 15 test lab defects for REL5.6 -Added PCR668#4643
2016-11-25 | v3.7.2 | Yusrin | -Added Defect #4654 and #4655 into REL5.6
2016-12-09 | v3.7.3 | Yusrin | -Added scope and timeline for R5.5.1 -Revise scope and timeline for R5.6 Added 2 Defect -Added scope and timeline for R5.6.1 -Added scope and timeline for R5.6.2
2016-12-14 | v3.7.4 | Yusrin | -Revise scope and timeline for R5.6 Added 2 Defect
2016-12-16 | v3.7.5 | Yusrin | -Added defect #4763
2016-12-21 | v3.7.6 | Yusrin | -Revised timeline for R5.6.1 & R5.6.2
2016-12-29 | v3.7.7 | Yusrin | -Drop Defect #4634 from REL5.6 -Revised Date of SIT Signed Off
2017-01-03 | v3.8.0 | Yusrin | -Added Schedule and Scope for R6.1
2017-01-12 | v3.7.8 | Yusrin | -Added Defect #4680 to REL5.6.1 -Revised SIT/UAT Signed Off and Implementation Date
2017-01-13 | v3.7.9 | Yusrin | -Added Defect #4678, #4681, #4679 to REL5.6.2 -Revised SIT Signed Off date
2017-02-04 | v3.8.1 | Yusrin | -Revised Scope for R6.1 -Added Defect #4664, #4665, #4657, #4653 and #4684
2017-02-13 | v3.8.2 | Yusrin | -Revised Scope for R6.1 -Added PCR #666 and #681
2017-02-13 | v3.9.0 | Yusrin | -Added scope and timeline for R6.2
2017-02-20 | v3.8.3 | Yusrin | -Revised Scope for R6.1 -Drop PCR #681 from R6.1
2017-02-20 | v3.9.1 | Yusrin | -Added Schedule and Scope for R6.1.1 -Added PCR #686 into R6.1.1
2017-04-05 | v3.9.2 | Sim Fui | -Updated R6.1 page - Updated R6.1.1 page - Updated R6.1 new rollout date to 23/4 due to rollback on 26/3
2017-04-06 | v3.9.3 | Sim Fui | -Added R6.2
2017-04-13 | v3.9.4 | Sim Fui | -Added TR Integration timeline
2017-04-20 | v3.9.5 | Sim Fui | -Revised scope for R6.1.1 (added Defect 4711)
2017-04-26 | v3.9.6 | Sim Fui | -Added R6.1.2 for defect 4720 - Updated R6.2 TR Integration timeline - Rename original R6.2 to R6.3
2017-05-12 | v3.9.7 | Sim Fui | - Added R6.1.3 for PCR 694 - Revised R6.1.2 timeline & added defect 4718
2017-05-17 | v3.9.8 | Sim Fui | - Updated R6.1.3
2017-06-02 | v3.9.9 | Sim Fui | - Update R6.2 - UAT date to 12/6 - Updated R6.3 - scope - Added R6.3.1
2017-06-13 | v4.0.0 | Sim Fui | - Update R6.2 rollout date to 25/8
2017-06-14 | v4.0.1 | Sim Fui | - Updated R6.2 tab
2017-06-19 | v4.0.2 | Sim Fui | - Updated R6.2 rollout date to 28/6
2017-06-20 | v4.0.3 | Sim Fui | - Updated scope for R6.3 & R6.3.1
2017-06-22 | v4.0.4 | Sim Fui | - Updated R6.2 rollout date to 2/7
2017-07-06 | v4.0.5 | Sim Fui | - Added 6.2.1
2017-07-12 | v4.0.6 | Sim Fui | -Added 6.4 - Update scope R6.3
2017-07-17 | v4.0.7 | Sim Fui | - Updated timeline for R6.5 - Updated scope for R6.3 - Updated scope for R6.4
2017-07-19 | v4.0.8 | Nina | - Updated scope for R6.4
2017-07-31 | v4.0.9 | Nina | - Updated Timeline for R6.3, R6.4 '- Updated scope for R6.3
2017-08-08 | v4.1.0 | Nina | - Updated scope for R6.4 '- Updated timeline for R6.4
2017-08-08 | v4.1.1 | Nina | - Updated timeline for SIT in R6.3
2017-09-13 | v4.1.2 | Nina | - Updated scope for R6.2.2 -Updated scope for R6.3.1
2017-09-19 | v4.1.3 | Nina | - Updated scope for R6.4
2017-10-03 | v4.1.4 | Nina | - Updated scope and timeline for R6.4
2017-10-05 | v4.1.5 | Nina | - Updated scope for R6.4 '- Updated scope for R6.5
2017-10-16 | v4.1.6 | Nina | - Updated scope for R6.4
2017-10-19 | v4.1.7 | Nina | - Updated timeline for Rel 6.4 & 6.5
2017-10-26 | v4.1.8 | Nina | - Updated scope for 6.5 defect list Drop 1
2017-11-20 | v4.1.9 | Nina | - Updated scope for 6.5 defect list Drop 1
2017-12-07 | v4.1.10 | Nina | - Updated scope for 6.5, 6.5.1, 6.5.2 defect list '- Added new release 6.5.3 and its scope '-Updated timeline for R6.5, 6.5.1, 6.5.2, 6.5.3
2017-12-13 | v4.1.10 | Rakesh | - Updated scope for 6.5.1, 6.5.2, 6.5.3 defect list
2017-12-20 | v4.1.10 | Nina | - Updated scope & timeline for 6.5, 6.5.1, 6.5.2, 6.5.3 release
2018-01-16 | v4.1.11 | Nina | - Rename R6.5.3 to R7.1 '- Updated timeline for R6.5.1 and 7.1 scope '- Defect #4783 in R6.5 moved to R7.1
2018-02-08 | v4.1.12 | Nina | - Added new PCR#727 into R6.5.2
2018-02-21 | v4.1.13 | Nina | - Added new defect #4879 into R7.1 - Removed defect #4842, #4841 from R7.1
2018-02-22 | v4.1.13 | Nina | - Added new tab for Local Incorp schedule
2018-02-26 | v4.1.14 | Nina | - Added new defect item in R7.1
2018-03-05 | v4.1.15 | Nina | - Added new defect item in R7.1
2018-03-09 | v4.1.16 | Nina | - Added new pcr into R7.1 - Removed defect #4759 from R7.1 - Updated R7.1 SIT & UAT signoff date
2018-03-22 | v4.1.17 | Nina | - Added new performance and defect items into R7.1.1 - Added implementation timeline for R7.1.1
2018-03-26 | v4.1.17 | Nina | - Added new pcr into R7.1.1 '- Added remark to R7.1 implementation date
2018-05-15 | v4.1.18 | Sim Fui | - Updated items for R7.1.1. - Added R7.2 - drop 1 (initiate planning)
2018-05-21 | v4.1.19 | Sim Fui | Updated R7.1.0.5
2018-05-23 | v4.1.20 | Sim Fui | Updated R7.1.2
2018-05-31 | v4.1.21 | Sim Fui | Updated R7.1.2 - included defect 4913, 4914, 4916
2018-09-26 | v4.2 | Sim Fui | Updated 16IT/23A (LI Affiliate Creation)
2018-10-10 | v4.2.1 | Sim Fui | Updated R7.1.3 Merge with latest LI implementation plan
2018-10-23 | v4.2.2 | Sim Fui | Updated R7.2
2018-11-14 | v4.2.3 | Sim Fui | Updated R7.1.3 - to include PCR746
2018-11-21 | v4.2.4 | Sim Fui | Updated R7.1.3 - to include PCR773
2018-12-03 | v4.2.5 | Sim Fui | Updated R7.1.3 - included PCR771 dropped PCR773
2018-12-07 | v4.2.6 | Sim Fui | Updated R7.2
2019-01-11 | v4.2.7 | Sim Fui | Updated R7.2 - de-scope PCR 770 TAU Sharing - cutover date revised from 21/1 to 20/1
2019-01-15 | v4.2.8 | Sim Fui | Added R8.0.1
2019-01-24 | v4.3 | Sim Fui | Created R8.0.2
2019-02-20 | v4.3.1 | Sim Fui | Updated R8.0.2 - scope-in PCR 787 + prod backlog + LI deferred defect
2019-02-21 | v4.3.2 | Sim Fui | Created R8.1
2019-03-06 | v4.3.3 | Sim Fui | Update R8.0.2 timeline for PCR 770 & PCR 787. However, no change in overall R8.0.2 timeline
2019-03-15 | v4.3.4 | Sim Fui | Update R8.0.2 Defect Items - descope defect 4884, 4992
2019-04-02 | v4.3.5 | Sim Fui | Created R8.0.3 - for prod issue
2019-04-04 | v4.3.6 | Sim Fui | Added defect 5025 and 5026
2019-04-08 | v4.3.7 | Sim Fui | Added 5008, 5009, 5017 into R8.0.2 Updated R8.1 scope
2019-04-16 | v4.3.8 | Sim Fui | Added 5031, 5033 into R8.1
2019-04-30 | v4.3.9 | Sim Fui | R8-1 - 5033 de-scope R8.1 - PCR 794 revised timeline R8.2 - draft scope
2019-05-17 | v4.4.0 | Sim Fui | R8.1 - updated cutover date R8.1 - updated scope: ilog migration, parameterisation R8.2 - revise scope
2019-05-30 | v4.4.1 | Sim Fui | Created R8.1.1 - emergency release
2019-05-31 | v4.4.2 | Sim Fui | Updated R8.2 scope and time - added new defects, descope ilog & parameterisation
2019-06-07 | v4.4.3 | Sim Fui | Created R8.1.2
2019-06-11 | v4.4.4 | Sim Fui | Created R8.1.3 Update R8.1.2 - cutover date
2019-06-18 | v4.4.5 | Sim Fui | Created R8.1.4 Updated R8.2 timeline
2019-07-09 | v4.4.6 | Sim Fui | Updated R8.2 scope - descope defect 5046 Created R8.3 - timeline and scope
2019-07-12 | v4.4.7 | Sim Fui | R8.2 - extended SIT sign off due to 5062
2019-07-23 | v4.4.8 | Sim Fui | R8.4 - created timeline for PCR785, PCR724 R8.3 - added PCR 810 R8.2 - revised SIT timeline due to down time on 29/7, added 5063 (to add some loggers before calling CIF linkage service(BSD3118))
2019-08-19 | v4.4.9 | Sim Fui | R8.2.1 - schedule for WAS 8.5.5 upgrade R8.3.1 - schedule & scope (PCR 812) R8.3 - revised scope R8.4 - descope PCR 724
2019-09-18 | v4.5.0 | Sim Fui | R8.3 - added 5071, 5073 Incorporated ODM Software upgrade to the plan R8.4 - updated scope
2019-09-19 | v4.5.1 | Sim Fui | R8.3 - added PCR 816 and SIT / UAT sign off update to 23/9
2019-10-15 | v4.5.2 | Sim Fui | R8.4 - revised scope R9.0.1 & R89.0.2- CNY teller limit change
2019-10-16 | v4.5.3 | Sim Fui | R8.3.1 - emergecy release for production issue. * remittance grorup mapping & ODM upgrade renamed to R8.3.2
2019-10-22 | v4.5.4 | Sim Fui | R8.3.1 - updated cutover date to 24/10
2019-11-05 | v4.5.5 | Sim Fui | R8.3.2 - added PCR 820 'R9.0.1 renamed to R8.4.1 R9.0.2 renamed to R8.4.2 R9.1 - created.
2019-11-19 | v4.5.6 | Sim Fui | R8.3.2 - removed 5072 (ODM upgrade) as ODM upgrade is postponed and to be taken up separately by SG ESB.
2019-11-27 | v4.5.7 | Sim Fui | R8.4 - added PCR 827, sit sign off updated to 4/12 'R8.4.1 - added PCR 826
2019-12-11 | v4.5.8 | Sim Fui | R8.4.2 - updated scope 'R9.1, R9.2 - updated scope
2019-12-23 | v4.5.9 | Sim Fui | R8.4.1 - updated scope and timeline R9.2 - assessment still in progress. Remove from the plan
2019-12-26 | v4.6.0 | Sim Fui | R8.4.1 & R8.4.2 - updated the impacted components
2020-01-09 | v4.6.1 | Sim Fui | R8.4.2 - updated scope R9.1 - updated timeline
2020-01-30 | v4.6.2 | Sim Fui | R9.1 - updated scope & timeline
2020-02-07 | v4.6.3 | Sim Fui | R9.1 - updated scope
2020-02-11 | v4.6.4 | Sim Fui | R9.2 - new release
2020-02-18 | v4.6.5 | Sim Fui | R9.1 - updated scope R9.1.1 - new release
2020-02-28 | v4.6.6 | Sim Fui | R9.1.1 - renamed to R9.2 R9.2 - rename to R9.3
2020-03-03 | v4.6.7 | Sim Fui | R9.3 - updated scope & timeline
2020-03-17 | v4.6.8 | Sim Fui | R9.1 - updated cutover timeline
2020-04-28 | v4.6.9 | Sim Fui | R9.3 - updated scope & timeline
2020-04-30 | v4.7.0 | Sim Fui | R9.3 - updated scope
2020-06-01 | v4.7.1 | Sim Fui | R9.3 - updated scope & timeline R9.4 - updated scope & timeline
2020-06-17 | v4.7.2 | Sim Fui | R9.3 - updated scope R9.4 - updated scope
2020-07-15 | v4.7.3 | Sim Fui | R9.3 - updated timeline & scope R9.4 - updated timeline & scope
2020-08-14 | v4.7.4 | Sim Fui | R9.4 - updated timeline & scope
2020-08-18 | v4.7.5 | Sim Fui | R9.4 - updated timeline , updated impacted components
2020-08-28 | v4.7.6 | Sim Fui | R9.3 - updated cutover date R9.5 - updated scope
2020-09-07 | v4.7.7 | Sim Fui | R9.5 - updated timeline
2020-09-18 | v4.7.8 | Sim Fui | R9.4.1 - created new release
2020-10-08 | v4.7.9 | Sim Fui | R9.5 - updated scope R9.4 - removed duplicate row for 5107
2020-11-10 | v4.7.10 | Sim Fui | R9.5 - update scope & timeline R10.1 - renamed R9.6 to R10.1. Updated scope for R10.1 Drop1 & Drop2.
2020-12-09 | v4.8.0 | Sim Fui | R10.1 - updated timeline & scope R10.0.1, R10.1.1 - updated timeline & scope
2021-01-04 | v4.8.1 | Sim Fui | R10.0.1 - updated scope R10.0.1, R10.1.1 - updated timeline & scope
2021-01-24 | v4.8.2 | Sim Fui | R10.2 - new release R10.1.1 - updated scope & timeline
2021-02-17 | v4.8.3 | Sim Fui | R10.2 - updated scope R10.1.1 - updated timeline
2021-02-19 | v4.8.4 | Sim Fui | R10.2 - updated scope R10.2.1 - new release
2021-04-05 | v4.8.5 | Sim Fui | Rename R10.2.1 to R10.3.1 R10.3 - new release R10.3.1 - new release
2021-04-15 | v4.8.6 | Sim Fui | Update R10.3 R10.3.1 - droppe R10.4 - new release
2021-04-26 | v4.8.7 | Sim Fui | R10.3 - updated timeline
2021-05-12 | v4.8.8 | Sim Fui | R10.3 - updated fsd sign off date
2021-06-08 | v4.8.9 | Sim Fui | R10.3 - updated scope 8 digit BIN CARDS compliance - updated timeline Added tentative timeline for R10.5, R10.6, R11.1
2021-06-18 | v4.8.10 | Sim Fui | 8 digit BIN CARDS compliance - updated timeline R10.4 - updated scope and time for Drop 2
2021-07-01 | v4.9.1 | Sim Fui | Updated scope for R10.5, Updated timeline for 8 digit BIN
2021-07-06 | v4.9.2 | Sim Fui | Updated scope for R10.5
2021-07-13 | v4.9.3 | Sim Fui | R10.4 - updated SIT/UAT sign off date, added UAT defects R10.5 - updated FSD dates 8 digit BIN - updated timeline for FSD / DEV / SIT
2021-08-06 | v4.9.4 | Sim Fui | R10.4 - de-scoped HSO fixes & updated new timeline. R10.5 - updated scope / timeline
2021-08-06 | v4.9.5 | Sim Fui | R10.5 - updated scope / timeline
2021-08-17 | v4.9.6 | Sim Fui | R10.5 - updated scope R11.1 - updated timeline
2021-08-26 | v4.9.7 | Sim Fui | R10.5 - updated timeline
2021-09-08 | v4.9.8 | Sim Fui | R10.5 - updated timeline R11.1 - updated timeline
2021-09-24 | v4.9.9 | Sim Fui | 8 Digit Bin Comliance Project - updated timeline R10.6 - updated scope
2021-09-27 | v4.9.10 | Sim Fui | R11.1 - timeline and scope
2021-10-11 | v4.10.1 | Sim Fui | R10.6 - updated scope R11.1 - updated scope
2021-10-18 | v4.10.2 | Sim Fui | R10.6 - updated scope / timeline
2021-10-25 | v4.10.3 | Sim Fui | R10.6 - updated scope / timeline
2021-11-03 | v4.10.5 | Yusrin | R10.6 - updated timeline R11.1 - updated timeline R11.0.1, R11.0.2 - updated timeline
2021-11-23 | v4.10.6 | Yusrin | R11.0.1 - updated timeline R11.2 - updated timeline
2021-11-24 | v4.10.6 | Yusrin | R11.0.1 - updated timeline R11.1 - updated timeline R11.2 - updated timeline
2021-12-28 | v4.10.7 | Yusrin | R11.1 - updated timeline
2022-01-12 | v4.10.8 | Yusrin | R11.2 - updated timeline R11.0.1.1 - added timeline
2022-02-11 | v4.10.9 | Yusrin | R11.1 - updated timeline
2022-02-11 | v4.11 | Yusrin | R11.3 - Added Timeline R11.4 - Added timeline
2022-02-28 | v4.12 | Ramesh | R11.3 - Updated Timeline R11.4 - Updated timeline
2022-03-07 | v4.13 | Ramesh | R11.3 - Updated Timeline R11.4 - Updated timeline
2022-04-12 | v4.15 | Ramesh | R11.3 - Updated Timeline R11.4 - Updated timeline
2022-04-14 | v4.16 | Ramesh | R11.5 - Added Timeline
2022-04-29 | v4.17 | Ramesh | R11.5 - Updated Timeline
2022-05-05 | v4.18 | Ramesh | R11.5 - Updated Timeline
2022-05-17 | v4.19 | Ramesh | R11.5 - Updated Timeline
2022-06-03 | v4.20 | Ramesh | R11.6 - Added Timeline
2022-07-06 | v4.21 | Ramesh | R11.5 - Updated Timeline and Scope R11.6 - Updated Timeline and Scope
2022-07-18 | v4.22 | Ramesh | R11.4 - Updated Timeline R11.5 - Updated Scope
2022-07-25 | v4.23 | Ramesh | R11.4 - Updated Timeline R11.5 - Updated Scope R11.6 - Updated Timeline
2022-08-05 | v4.24 | Ramesh | R11.5 - Updated Timeline R11.6 - Updated Timeline & Scope
2022-08-17 | v4.25 | Ramesh | R11.5.1 - Added Timeline R11.6 - Updated Scope R11.7 - Added Timeline
2022-09-02 | v4.25 | Ramesh | R11.5.1 - Added Timeline R11.6 - Updated Scope
2022-09-29 | v4.25 | Ramesh | R11.6 - Updated Scope and Timeline
2022-10-17 | v4.26 | Ramesh | R12.0.1 - Added Timeline and scope R12.0.2 - Added Timeline and scope
2022-12-05 | v4.27 | Ramesh | R12.1 - Added Timeline and scope
2023-02-03 | v4.28 | Ramesh | R12.1.1 - Added Timeline and scope
2023-02-13 | v4.29 | Yusrin | R12.1.0 - Added Timeline and scope R12.1.1 - Revise Timeline
2023-02-17 | v4.30 | Yusrin | R12.1.0 - Revise Timeline R12.1.1 - Revise Timeline

## Sprint Timeline (hidden)
| Sprint 1-JAZZ | [27 empty] | Sprint 2 - Frenzy | [21 empty] | Sprint 3-Megatron | [27 empty] | Sprint 4-Arcee | [27 empty] | Sprint 5 - Mixmaster | [27 empty] | Sprint 6-Jetfire | [27 empty] | Sprint 7-Jolt | [27 empty] | Antagony | [27 empty] | Starcream | [27 empty] | Optimus Prime | [27 empty] | Nitro Zeus | [27 empty] | Nautica | [27 empty] | Devastator
R9.2
DEV & SIT (SIT sign off 3/3)
UAT | [56 empty] | U | U | U | U | U | U | U | U | U | U | U | U | U | U | U | U | U | U | U | U | U | U
Change Mgmt | [81 empty] | CM
Ramesh 29/1 - 14/2
 | time axis 2020-01-08 to 2020-12-30
 | time axis 2020-01-08 to 2020-12-30
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
UT 4 Acc | 2020-01-13: DIT; 2020-01-20: SIT
UT 4 Acc - DEV 2/1 to 21/1 | bar: 2020-01-08 to 2020-01-10; 2020-01-13 to 2020-01-17; 2020-01-20 to 2020-01-21
UT 4 acc - SIT 22/1 - 3/2 | bar: 2020-01-22 to 2020-01-24; 2020-01-28 to 2020-01-31; 2020-02-03
UAT 4/2 - 25/2 | bar: 2020-02-04 to 2020-02-25
CRA / Cutover 26/2 - 8/3 | bar: 2020-03-08
Update RSA-i form | bar: 2020-01-09 to 2020-01-10
PCR 821 - TD Advice Enhancement | bar: 2020-01-13 to 2020-01-14
Add Hold UV to add Effective Date and Expiry Date | bar: 2020-01-15 to 2020-01-16
Remittance MEPS payment mode: Unable to removed CIF no. entered | bar: 2020-01-17 to 2020-01-18; 2020-01-20
Remittance MEPS payment mode 'IC No.' and 'Applicant Name' field is enabled and editable for existing customer | bar: 2020-01-19; 2020-01-21 to 2020-01-22
Joint Acc Opening Form - Main appl & joint applicant names are swap | bar: 2020-01-17; 2020-01-20

## LI Schedule (hidden)
|  | 2015-12-01 |  |  |  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01 |  |  |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  |  | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  |  | 2016-08-01 |  |  |  | 2016-09-01 |  |  |  | 2016-10-01 |  |  |  | 2016-11-01 |  |  |  |  | 2016-12-01 |  |  |  | 2017-01-01 |  |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  |  | 2018-01-01 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
Week Ends(Sun) | time axis 2015-12-13 to 2018-12-30
Week Starts(Mon) | time axis 2015-12-07 to 2018-12-24
Releases | Activity | W49 | W50 | W51 | W52 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
Local Incorp P2 | Requirements
Development
SIT
UAT
Mock Run
Affiliate Creation
Implementation
[114 empty] | Remarks | [18 empty] | Change Requests Remarks
[114 empty] | Requirements |  |  |  | : | 02/02 - 07/03, Sign off : 09/03 | [13 empty] | PCR | ISD S/O |  | SIT Duration |  |  | SIT S/O
[114 empty] | Development |  |  |  | : | 19/02 - 20/04 | [13 empty] | 745 | 21/6 |  | 8/6 - 6/7 |  |  | 9/7
[114 empty] | SIT |  |  |  | : | 26/02 - 31/05, SIT Signoff : 01/06 | [13 empty] | 752
[114 empty] | UAT |  |  |  | : | 01/06 - 20/09, UAT Signoff : TBC | [13 empty] | 754 | 16/7 |  |  | 16/7-18/7 |  | 18/7
[114 empty] | Mock Run |  |  |  | : | 13/08 - TBC | [13 empty] | 756 | 23/7 |  |  | N/A |  | N/A
[114 empty] | Affiliate Creation |  |  |  | : | UAT : 21/9, CM : 4/10, CutOver : 9/10 | [13 empty] | 758 | 16/8 |  |  | 17/8-23/8 |  | 23/8
[114 empty] | Implementation |  |  |  | : | 3/11- 4/11
[114 empty] | Go - Live |  |  |  | : | 2018-11-05
DIT
[105 empty] | TP | TP | TP
[105 empty] | S | S | S | S | S | S | S | S | SIT signoff 19/1/18
[105 empty] | U | U | U | U | U | U | U | U | UAT signoff 19/1/18
[112 empty] | CM | Rollout 21/1/18
R
D
DIT
TP
[113 empty] | S | S | SIT signoff 31/1/18
[113 empty] | U | U | UAT signoff 31/1/18
[114 empty] | CM | Rollout 4/2/18
R
D
DIT
TP
[115 empty] | S | S | SIT signoff 15/2/18
[115 empty] | U | U | UAT signoff 15/2/18
[117 empty] | CM | Rollout 19/2/18
[112 empty] | R | R
[113 empty] | D | D | D | D
DIT
TP
[117 empty] | S | S | S | S | S | S | SIT signoff 09/3/18 - PCR, 29/3/18 - Defect
[118 empty] | U | U | U | U | U | UAT signoff 23/3/18 - PCR, 30/3/18 - Defect
[122 empty] | CM | Rollout 01/4/18
Note on EH7: Nina Sharizan Binti Zamshairi: PCR 745,752 & Retrofit( >=7.1.2 ) ISD S/O : 21/06 SIT : 08/06 - 06/07 SIT Signoff : 09/07
Note on EI7: Nina Sharizan Binti Zamshairi: PCR 754 ISD S/O : 16/07 SIT : 16/07 - 18/07 SIT Signoff : 18/07
Note on EJ7: Nina Sharizan Binti Zamshairi: PCR 756 ISD S/O : 23/07 SIT : N/A SIT Signoff : N/A

## R4.1.1 (hidden)
Defect ID | PCR SEQ No | Workstream | Severity | Detected on Date | Status | Detected in Release | Originated from Version | Summary
4477 | 633 | Back Office | 4-Cosmetics | 2015-11-30 | Fixed | RBS SG UAT |  | Increase of fees for cheques (SGD) returned due to insufficient funds from $40 to $50
4482 |  | Deposit 3 | 2-Medium | 2015-12-10 | Open | RBS SG PROD | Phase Delivery-In Phase 1.0 | Same token serial number is registered to different customers in RBS and Host

## R4.1.2 (hidden)
Defect ID | PCR SEQ No | Workstream | Severity | Detected on Date | Status | Detected in Release | Originated from Version | Summary
4458 | 628 | Remittance | 4-Cosmetics | 2015-10-06 | Open | RBS SG UAT |  | New GBP Cheque Format (CRS Draft)
4319 | 581 | Back Office | 4-Cosmetics | 2015-02-05 | Open | RBS SG PROD |  | CNY Pack

## R4.1.3 (hidden)
Defect ID | PCR SEQ No | Workstream | Severity | Detected on Date | Status | Detected in Release | Originated from Version | Summary
4490 | 636 | Common | 4-Cosmetics | 2015-12-31 | Open | RBS SG UAT |  | To increase teller drawer limit from $2k to $20k

## R4.2 (hidden)
Phase 1
Defect ID | PCR SEQ No | Workstream | Severity | Detected on Date | Status | Detected in Release | Originated from Version | Summary
4293 |  | Financing | 3-Low | 2014-12-10 | Fixed | RBS SG PROD |  | Message on backvalue for today's effective
4315 |  | Deposit 2 | 3-Low | 2015-01-19 | Fixed | RBS SG PROD |  | UV printout for FCCA Debit Advice with GL
4320 |  | TAM | 4-Cosmetics | 2015-02-04 | Fixed | RBS SG UAT |  | Branch name not populated in Operator Maintenance screen
4329 |  | Branch Operations | 3-Low | 2015-03-06 | Fixed | RBS SG UAT |  | SPEED CODE: 646 EXPECTING UPDATE , SPEED CODE : 647 EXPECTING REVERSAL LOG BUT SHOWING EXCEPTION LOG AND UPDATED
4343 |  | Common | 3-Low | 2015-04-06 | Fixed | RBS SG UAT | Phase Delivery-In Phase 1.0 | EJ - Floating message found in the message area box
4375 |  | Remittance | 3-Low | 2015-07-13 |  | RBS SG PROD | Phase Delivery-In Phase 1.0 | FCTD Account Closure for Contract No/Dealer Rate is not printed on the vouchers
4379 |  | Remittance | 3-Low | 2015-05-11 | Fixed | RBS SG UAT |  | BSRE213 (TC 7610 - TT OUTWARD REFUND / REPURCHASE ), EJ show both ‘success’ and ‘failed’ despite transaction is successful
4420 |  | Deposit 2 | 3-Low | 2015-07-22 | Open | RBS SG UAT |  | BSD2108 (Misc Dr) to send converted amount, converted currency and flag to ESB and host on TC8620
4442 |  | NAO | 3-Low | 2015-08-25 | Fixed | RBS SG PROD | Phase Delivery-In Phase 3.8 | Creation of TD Islamic Acct via Express Account Opening
4450 |  | Deposit 3 | 3-Low | 2015-09-10 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | eServices - Card Service - Account dropdown unable to display more than 25 accounts
4480 |  | Deposit 2 | 3-Low | 2015-12-03 | Fixed | RBS SG UAT | Phase Delivery-In Phase 3.4 | DEP2: Cheque deposit> SGD Marked Cheque> hitting error with service charge as deb from acc without selecting description
4484 |  | Financing | 3-Low | 2015-12-18 |  | RBS SG UAT |  | FIN > Settlement > If selected “payment mode leg disabled” check box, unable to perform the settlement transaction
Phase 2
Defect ID | PCR SEQ No | Workstream | Severity | Detected on Date | Status | Detected in Release | Originated from Version | Summary
4486 |  | Deposit 3 | 2-Medium | 2015-12-18 | Open | RBS SG UAT | Phase Delivery-In Phase 1.0 | Deposit 3 PIN/Passbook/TD/Acct/MSRE maintenance fields refresh
4488 |  | Deposit 3 | 2-Medium | 2015-12-24 | New | RBS SG UAT | Phase Delivery-In Phase 1.0 | New eServices Issuance > For second customer, drop down values are not resetting at all services
4492 | 637 | Common | 4-Cosmetics | 2016-01-04 | New | RBS SG UAT |  | To reinstate Teller Drawer Limit from $20k to $2
4495 |  | Deposit 3 | 3-Low | 2016-01-07 | Fixed | RBS SG UAT |  | DP3: Reissue/Lost Passbook >Payment mode cash should not show debiting account field.
4496 |  | Deposit 3 | 3-Low | 2016-01-07 | Fixed | RBS SG UAT |  | DP3 > Modify Passbook Details: Service Type is showing in Product Type dropdown list
4497 |  | Deposit 3 | 3-Low | 2016-01-08 | Fixed | RBS SG UAT |  | DP3: Reissue/Lost Passbook > "Debiting Account No" field is not refreshing.
4498 |  | Deposit 3 | 3-Low | 2016-01-13 | Open | RBS SG UAT |  | DP3: Pin Maintenance > System prompt to select "Service Type" once again.
4507 |  | Deposit 3 | 3-Low | 2016-02-02 |  | RBS SG UAT |  | Maintenance>Modify Passbook Details: Set On/Off Passbook/Stmt Printing issue

## R4.2.1 (hidden)
Defect ID | PCR SEQ No | Workstream | Severity | Detected on Date | Status | Detected in Release | Originated from Version | Summary
4516 |  | Deposit 3 | 2-Medium | 2016-02-15 |  | RBS SG PROD | Phase Delivery-In Phase 4.2 | Cannot issue passbook
4518 |  | Deposit 3 | 2-Medium | 2016-02-15 |  | RBS SG PROD | Phase Delivery-In Phase 4.2 | New eServices Issuance SEMA linkage failed

## R5.0 (hidden)
Defects
Defect ID | PCR SEQ No | Workstream | Severity | Status | Detected on Date | Detected in Release | Originated from Version | Summary
4224 |  | Third Party | 3-Low | Fixed | 2014-08-29 | RBS SG PROD |  | IM246054 UTMS - Discrepancy on dividend option
4255 |  | Common | 3-Low | Fixed | 2014-10-16 | RBS SG PROD | Phase Delivery-In Phase 1.0 | IM284297 Intermittent SO issues happened at branches
4317 |  | Branch Operations | 3-Low | Fixed | 2015-02-02 | RBS SG PROD | Phase Delivery-In Phase 1.0 | Balancing issue @ Balestier 30/1/15
4438 |  | Deposit 2 | 3-Low | Fixed | 2015-08-22 | RBS SG PROD | Phase Delivery-In Phase 1.0 | No printout for reversal of CA Fast Cheque Deposit
4439 |  | Deposit 2 | 3-Low | Fixed | 2015-08-22 | RBS SG PROD | Phase Delivery-In Phase 1.0 | SA local cheque deposit reversal successful in RBS but not captured in host
4449 |  | Financing | 2-Medium | Fixed | 2015-09-10 | RBS SG PROD | Phase Delivery-In Phase 1.0 | 2 a/c posting different amount in RBS and AS400
4493 |  | Deposit 2 | 3-Low | Fixed | 2016-01-04 | RBS SG PROD | Phase Delivery-In Phase 4.0 | Error printing for USD local cheque issuance. Payee’s name is incomplete despite full details entered correctly at AS400.
4221 |  | Deposit 4 | 3-Low | Fixed | 2014-08-25 | RBS SG UAT |  | To print "Has ODP" value in Detailed Balance Inquiry
4227 |  | Branch Operations | 3-Low | Fixed | 2014-08-26 | RBS SG UAT |  | Phase 3.6 > UAT Defect > BOP >Error encountered when performing Cancel Delivery Inventory item
4230 |  | NAO | 4-Cosmetics | Fixed | 2014-08-29 | RBS SG UAT |  | NAO > Link to existing Debit Card > No card num at card no drop down
4473 |  | Common | 4-Cosmetics | Fixed | 2015-11-16 | RBS SG UAT | Phase Delivery-In Phase 1.0 | Standardise PINPAD error message to other functions
4487 |  | Back Office | 3-Low | Fixed | 2015-12-18 | RBS SG UAT |  | SF Outward Return : Store & Forward Report validation (FEE not recorded for the successful transaction)
4514 |  | Deposit 3 | 3-Low | Fixed | 2016-02-10 | RBS SG UAT |  | DP3: Cheque Maintenance > Payment Mode is not refreshing for 2nd Cust
4522 |  | Deposit 3 | 3-Low | Fixed | 2016-02-19 | RBS SG UAT |  | DP3: Cheque Maintenance > Service Type > Stop Cheque: Internal system error: 100
4523 |  | Deposit 3 | 3-Low | Fixed | 2016-02-19 | RBS SG UAT |  | DP3: Cheque Maintenance: Request Cheque book SC = 0.00, showing debiting acct field
4537 |  | Branch Operations | 3-Low | Fixed | 2016-03-10 | RBS SG UAT |  | Logger for #4506 - Card allocated to DD drawer
4538 |  | Common | 3-Low | Fixed | 2016-03-10 | RBS SG UAT |  | Logger for JVM
4545 |  | Common | 4-Cosmetics | Fixed | 2016-03-18 | RBS SG UAT |  | iLOG path change
PCR
Defect ID | PCR SEQ No | Workstream | Severity | Status | Detected on Date | BRD Readiness | ISD Readiness | Summary
4513 | 641 | Remittance | 4-Cosmetics | Open | 2016-02-10 | N/A | Signed Off | Set JPY default agent as SMBCJPJT in Branch/Retail system

## R5.0.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Detected on Date | Summary | ET | DB | ESB | Host
4173 | 3-Low | NAO | Open | RBS SG UAT |  | 2016-03-15 | Side Safewatch integration: Nationality, Gender, Birthdate fields | Y

## R5.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Detected on Date | Summary | ET | DB | ESB | Host
4539 | 2-Medium | Financing | Open | RBS SG PROD |  | 2016-03-15 | Error Message - Cr Repayment via RBS |  |  | Y
4549 | 3-Low | Third Party | Open | RBS SG PROD |  | 2016-04-05 | UT Redemption Error (CORBA_TRANSACTION_ROLLEDBACK) |  |  | Y
4489 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD |  | 2015-12-31 | LOG from RBS - UNSUCCESSFUL CLOSURE OF ACCOUNT NO: 04211085531 AT RBS | Y
4546 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD |  | 2016-03-29 | Closure of current account via write off | Y
4559 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-in Phase 3.5 | 2016-04-12 | UNSUCCESSFUL CLOSURE OF FCTD 84015125702 BY CASH | Y
PCR
Defect ID | PCR SEQ No | Workstream | Status | BRD Readiness | ISD Readiness | Detected on Date | Summary | ET | DB | ESB | Host
4481 | 634 | Deposit 2 | Open | Signed Off | Signed Off | 2015-12-08 | HKD, CNH, CNY, CHF into the currency drop down list for closure of FCTD accounts | Y | Y |  | Y
4491 | 638 | Remittance | Open | Signed Off | Signed Off | 2016-01-02 | Outward FCY ACU mode on IDR | Y
4530 | 642 | Deposit 2 | Open | Signed Off | Pending Signoff | 2016-02-26 | Billion amt field in Fund Trf, Misc Dr/Cr, Acct Closure | Y

## R5.2 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | ESB | Host
4478 | 2-Medium | Common | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Account in used status remains when branches cancelling of host overriding request | Y |  | Y
4511 | 2-Medium | Branch Operations | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | RBS Day end balancing error in report | Y
4528 | 2-Medium | Deposit 3 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | GL cash out - Islamic account GL and printout | Y
4544 | 2-Medium | Deposit 3 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Update passbook validation | Y
4556 | 2-Medium | Branch Operations | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | UNSUCCESSFUL PRINT OUT FOR SURPRISE CHECK STOCK CONTROL REGISTER | Y
4562 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Unable to do entry reversal | Y
4568 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | RBS PROBLEM - MAYBANK @KOVAN 18.05.2016 | Y
4569 | 2-Medium | NAO | Fixed | RBS SG PROD | Phase Delivery-In Phase 3.5.1 | SSW discrepancies in 'also known as' field | Y
4571 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD |  | EJ and validation showing the wrong CO no. ‘288881’ after reversal was done on CO no. ‘288884’ | Y
4577 | 3-Low | Common | Fixed | RBS SG PROD |  | Reverse EC entry differ from RBS and AS400 | Y
4576 | 2-Medium | NAO | Fixed | RBS SG PROD | Phase Delivery-In Phase 5.1 | SSW gender, DOB fields | Y
4583 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD |  | CA Zero Balance account closure | Y
4584 | 2-Medium | Third Party | Fixed | RBS SG PROD |  | UTMS Account inquiry XML parsing error |  |  | Y
4588 | 3-Low | Remittance | Fixed | RBS SG SIT |  | EJ details and UV shows Dealer Code for Counter Rate | Y
4590 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | FC Account Closure UV had printed the title as Zero Balance for Write-Off scenario when Ledger Balance is less than Excess Interest | Y
4592 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Regional Link: Transaction Count Summary NOT updated for the successful txn for Regional Link | Y
4595 | 4-Cosmetics | Third Party | Fixed | RBS SG SIT |  | SIT_RBS_SG.RELEASE_5_2 - Defect #21 - Release 5.2 > Defect 4584 > UT Redemption > UV is showing dash at the Fund ID | Y
4596 | 4-Cosmetics | Third Party | Fixed | RBS SG SIT |  | SIT_RBS_SG.RELEASE_5_2 - Defect #20 - Release 5.2 > Defect 4584 > UT Redemption > EJ is not showing Payment Mode at the title | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | ESB | Host
4146 | 538 | Financing | Fixed | N/A | N/A | IM171965 RBS - UNABLE TO POST DR ADJUSTMENT (4321 & 4322 ) INSPECTION FEES |  |  | Y
4303 | 576 | Deposit 2 | Fixed | Signed Off | Signed Off | Changes on "Payment Collection Account" screen at "Payment" drop down list. | Y
4464 | 629 | Deposit 2 | Fixed | Signed Off | Signed Off | [Visa Signature] Visa Signature Card using New BIN | Y |  |  | Y
4567 | 651 | Remittance | Fixed | Signed Off | Signed Off | [IM779452] To Remove Deutsche Bank US Account From Auto Crediting For Inward Remittance (MT103) | Y | Y

## R5.2.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | ESB | Host
4601 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-in Phase 3.9 | Unable to perform AUD Cash Withdrawal | Y
4603 | 2-Medium | Back Office | Fixed | RBS SG PROD | Phase Delivery-in Phase 5.2 | HSO Issue in S&F | Y

## R5.3 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host
HPQC 4589 | 2-Medium | Third Party | Open | RBS SG PROD | Phase Delivery-In Phase 5.1 | Error encountered wih New UT account without fund with the message "Hit Error:100, FC ParserException:CPI Text Buffer Input Data Too Short : 0" |  |  |  | Y
HPQC 4471 | 3-Low | NAO | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Acct# Not found encountered on some transactions mostly TD/FCTD NAO | Y
HPQC 4529 | 3-Low | Deposit 4 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | No EJ inquiry record for trancode 0495 (envelope printing) | Y
HPQC 4535 | 3-Low | Third Party | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | UT subscription on joint CIFs | Y
HPQC 4574 | 3-Low | Common | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Service inquiry no field to display to input CIF, ATM card no, TD, FCTD account | Y
HPQC 4575 | 3-Low | NAO | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Negotiable item chequebook status show as "Remove" instead of "Issue" | Y
HPQC 4578 | 3-Low | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 5.1 | To default Amount Currency based on Account Currency | Y
HPQC 4591 | 3-Low | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | CO via RBS for the amount "$1.00", the amount in words printed out is indicated as "ONE | Y
HPQC 4605 | 2-Medium | Remittance | Open | RBS SG PROD | Phase Delivery-in Phase 5.2 | CO - Remittance - Reversal issue | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host
4044 | 493 | Branch Operations | Fixed | Signed Off | Signed Off | IM97819 TAU message prompting for cartridge almost full | Y
4203 | 547 | Third Party | Open | Signed Off | In Progress | Unit Trust Subscription | Y
4421 | 619 | Third Party | Open | Signed Off | Signed Off | Create payment mode ‘others’ in UT Redemption | Y |  |  |  | Y
4465 | 630 | NAO | Open | Signed Off | In Progress | To add product code H0 (odd days SGD TD-i) into RBS | Y | Y
4597 | 656 | Remittance | Open | Signed Off | In Progress | Threshold on outward remittance transaction code in branch RBS for control purpose | Y |  | Y

## R5.3.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host
4613 | 2-Medium | Remittance | Fixed | RBS SG UAT |  | MEPS and TT did not require SO | Y

## R5.3.2 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary
4618 | 3-Low | Common | Fixed | RBS SG UAT |  | Collection Account Reversal - 25th August
4621 | 3-Low | Remittance | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Reinstate RSW by transfer
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host
4605 | 660 | Remittance | Fixed | N/A | Signed Off | CO - Remittance - Reversal issue | Y |  |  | Y

## R5.4 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host
4627 | 3-Low | Remittance | Fixed | RBS SG UAT |  | For Transfer payment mode, if we enter Dormant acc as Sender's acc num, after SO approval, system is looping in same screen | Y
4542 | 3-Low | Remittance | Fixed | RBS SG UAT | Phase Delivery-In Phase 1.0 | Unknown Status captured under EJ for Reversal on Regional Link Withdrawal | Y |  |  | Y
4640 | 3-Low | Remittance | Fixed | RBS SG UAT | Phase Delivery-In Phase 1.0 | To add in one additional BOP code EX NON - RESIDENT TO NON - RESIDENT TRANSACTION |  | Y
4641 | 3-Low | Remittance | Fixed | RBS SG UAT | Phase Delivery-In Phase 1.0 | CIF not found in Regional Link | Y | Y
4644 | 4-Cosmetics | Remittance | Fixed | RBS SG UAT | Phase Delivery-In Phase 1.0 | MAS626 PDF not generated upon clicking on Print button | Y | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA
4266 | 569 | Remittance | Open | Signed Off | Signed Off | [MAS Notice 626] Remittance Compliance - Regional Link | Y |  | Y | Y | Y | Y |  | Azuwah
4561 | 648 | Remittance | Open | Signed Off | Signed Off | [MAS Notice 626] Regional Link Deposit - SSW Name Screening | Y |  | Y | Y | Y | Y |  | Azuwah

## R5.5 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host
4616 | 3-Low | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 3.5 | FCTD validation - Replacement cost shown in SGD instead of AUD | Y
4414 | 3-Low | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | FCTD Account Closure for Contract No/Dealer Rate is not printed on the vouchers | Y
4607 | 3-Low | Deposit 2 | Fixed | RBS SG PROD |  | Contract No/Dealer Rate is not printed on the vouchers - DP2 | Y
4628 | 3-Low | Financing | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | CORBA TRANSACTION ROLLBACK error when colleteral ID is not found during inquiry | Y
4573 | 3-Low | Remittance | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | 7630 - performed in Prod on 13 May 2016 | Y
4622 | 3-Low | Remittance | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | CRS FDD Issuance via ACU mode | Y
4629 | 3-Low | Remittance | Fixed | RBS SG PROD | Phase Delivery-In Phase 4.0 | No new serial number in CO reissue | Y
4617 | 3-Low | Third Party | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | UT subscription - Dividend instruction dropdown empty | Y
4635 | 3-Low | Common | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Name & IC not printed during passbook reissue via payget function | Y
4536 | 2-Medium | Back Office | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | Inward return : No validation on expiry date for Credit card | Y
4515 | 2-Medium | Deposit 3 | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | Stop Cheque transaction,Payment Mode = Fund Transfer and selects a TDA, screen exits to main screen | Y
4508 | 3-Low | Deposit 3 | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | Update Signature/Mandate > Add Mandate: Primary customer's name is not printing | Y
4519 | 3-Low | Deposit 3 | Fixed | RBS SG SIT | Phase Delivery-In Phase 4.2 | DP3: Reissue/Lost Passbook: For service charge “0.00” amount it is calling TAU deposit popup. | Y
4520 | 3-Low | Deposit 3 | Fixed | RBS SG SIT | Phase Delivery-In Phase 4.2 | DP3: Reissue/Lost Passbook: on Indemnity form it is printing only 2account holder details | Y
4524 | 3-Low | Deposit 3 | Fixed | RBS SG SIT | Phase Delivery-In Phase 4.2 | DP3: After successful issuance of PDC Pack, card num is not printing on “Branch Delivery form” | Y
4531 | 3-Low | Deposit 3 | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | To print Branch Delivers Serv Plat Debit Card Form during PIN Issuance | Y
4479 | 3-Low | Deposit 2 | Fixed | RBS SG SIT | Phase Delivery-In Phase 4.1 | DEP2: Cheque deposit> SGD Marked Cheque> bank name and cheque no overlapping | Y
4510 | 3-Low | Branch Operations | Fixed | RBS SG UAT |  | System allows clicking on “Update” button even there’s no reversal log in the detail box | Y
4608 | 3-Low | Deposit 2 | Fixed | RBS SG UAT |  | FT from Debit Card to CASA | Y
4534 | 3-Low | Remittance | Fixed | RBS SG UAT | Phase Delivery-In Phase 4.2.1 | To have asterisk as an “ending marker” on Line1 & 2 (Payee Name & ID) | Y
4637 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Cheque Deposit Contract Number field is accepting more than 10 char | Y
4645 | 3-Low | Deposit 2 | Fixed | RBS SG UAT |  | FCTD Account Closure can proceed without entering mandatory field for converted amount | Y
4649 | 3-Low | Deposit 2 | New | RBS SG UAT |  | Account Closure field values are overlapped in the UV printout. | Y
4646 | 3-Low | Deposit 3 | Fixed | RBS SG UAT |  | Acct num and Acct holder details are not printing on TD Mandate | Y
4647 | 3-Low | Deposit 3 | Fixed | RBS SG UAT |  | Service charge field should fetch SGD = 15.00 with fund transfer payment mode defaulted. | Y
4650 | 3-Low | Deposit 3 | Fixed | RBS SG UAT |  | Account Services for payment mode Cash, system should not fetch the Debiting acct number field at IB Token Replacement screen. | Y
4651 | 3-Low | Remittance | New | RBS SG UAT |  | nward TT: Transaction FAILED when changing rate Counter - Special - Contract with Payment mode = Transfer | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA
4585 | 658 | Third Party | Fixed | N/A | N/A | UT subscription - CORBA TRANSACTION_ROLLEDBACK error | Y |  |  |  | Y | Y |  | Hamidah
4563 | 649 | Deposit 2 | Fixed | Signed Off | Signed Off | USD local cheque logic for remarks field for sending to host | Y |  |  |  |  | Y | WO Approved | Azuwah
4610 | 661 | Deposit 2 | Fixed | Signed Off | Signed Off | To amend description on RBS validation for foreign cheque deposit to CASA | Y |  |  |  |  | Y | WO Approved | Azuwah
4586 | 655 | Remittance | Fixed | Signed Off | Signed Off | To default CNY agent bank to ICBKSGSGCLR for Outward TT | Y |  |  |  |  | Y | WO Approved | Azuwah
Sonarqube Fixes
No. | Rule |  |  |  |  | Impacted Function | Flow Change | Unit Testing | Sonarqube Test
1 | Conditions should not unconditionally evaluate to "TRUE" or "False" RCA : Conditional statements using a condition which cannot be anything but FALSE have the effect of making blocks of code non-functional. If the condition cannot evaluate to anything but TRUE, the conditional statement is completely redundant, and makes the code less readable. |  |  |  |  | Account Closure Cheque Deposit Payment Cash Withdrawal Multiple Deposit Multiple TD Placement Misc Credit Misc Debit | N | Y | Y
2 | for' loop update clause should move the counter in right direction RCA : A for loop with a counter that moves in the wrong direction is not an infinite loop. Because of wraparound, the loop will eventually reach its stop condition, but in doing so, it will run many, many more times than anticipated, potentially causing unexpected behavior. |  |  |  |  | Adjustment Maintainance | N | Y | Y
3 | Null pointers should not be dereferenced RCA : A reference to null should never be dereferenced/accessed. Doing so will cause a NullPointerException to be thrown |  |  |  |  | Account Closure Deposit Cash Deposit Cheque Multiple Deposit Paymen TD Creation & Placement Transfer/Miscellaneous Fund Transfer Transfer/Miscellaneous Misc Credit Transfer/Miscellaneous Misc Debit Withdrawal | N | Y | Y

## R5.5.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4655 | 2-Medium | Remittance | Open | RBS SG PROD |  | DD Repurchase | Y |  |  | Y

## R5.6 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4636 | 3-Low | Remittance | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Debit and Credit Nostro Printing | Y
4654 | 2-Medium | Remittance | Fixed | RBS SG PROD |  | Unable to see Customer signature on RL screen | Y
4509 | 3-Low | Branch Operations | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | BOP : Issues for non entitled Teller when performing Negotiable Items Stock Allocation function | Y
4550 | 3-Low | Common | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | Standardize error message for “device not available (Broken Device ) Defect #1 (SIT defect #16,25) | Y |  |  |  |  | Y
4551 | 3-Low | Common | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | Standardize error message for “device not available (Broken Device ) Defect #2 (SIT defect #26,24,23) | Y |  |  |  |  | Y
4552 | 3-Low | Common | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | Standardize error message for “device not available (Broken Device ) Defect #3 (SIT defect #20) | Y |  |  |  |  | Y
4633 | 3-Low | Common | Fixed | RBS SG SIT |  | TIMEOUT Error 203 shown as unknown in EJ |  |  |  | Y
4630 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Reversal for a success Cash Withdrawal transaction, there are 2 EJ recorded (1 for overriding and 1 for success). | Y
4606 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Cash Withdrawal for FCTDA, after a success transaction the 'Search Method = Without ATM/PB' is showing in EJ details. | Y
4503 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Account Closure - various | Y
4459 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | FCCA CASH DEPOSIT CROSS CURRENCY cash in not updated in the balance drawer | Y
4504 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Account Closure - various | Y
4557 | 3-Low | Deposit 3 | Fixed | RBS SG SIT |  | System return to Pay get screen with 'internal error" msg in the msg box for invalid card scenario with VISA/MASTERCARD | Y
4553 | 3-Low | Deposit 3 | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | DP3 > Maintenance > error msg stays in the msg box | Y
4527 | 3-Low | Deposit 4 | Fixed | RBS SG SIT |  | Inquire by CIF & IC num > In EJ Inquiry Log, showing "Invalid CIF No" error | Y
4532 | 3-Low | Deposit 4 | Fixed | RBS SG SIT |  | System is not printing all the ATM/PDC Card numbers during Service Inquiry by CIF/IC | Y
4533 | 3-Low | Deposit 4 | Fixed | RBS SG SIT |  | DP4: While doing Service Inquiry through PB Access num, showing extra fields in printing | Y
4594 | 3-Low | NAO | Fixed | RBS SG SIT |  | SSW report AKA, Remarks field was truncated | Y
4500 | 3-Low | Remittance | Fixed | RBS SG SIT | Phase Delivery-In Phase 1.0 | Truncated Payee Name during DD re-issuance |  |  |  | Y
4602 | 2-Medium | Common | Fixed | RBS SG UAT |  | Exception handing in D2/Remittance/D3 transactions | Y
4118 | 2-Medium | Financing | Fixed | RBS SG UAT |  | Reactivate Online posting after 0291 - Unable to perform EJ Reversal (EC) | Y
4632 | 3-Low | Remittance | Fixed | RBS SG UAT |  | "Can’t convert infinity or NaN" error when exchange rate is not avail | Y
4669 | 4-Low | Deposit 4 | Open | RBS SG SIT |  | Release 5.6 > Defect 4527 > Service Inquiry > EJ Inquiry log > Details> Date of birth is not printed. | Y
4670 | 2-High | Financing | Open | RBS SG SIT |  | Defect 4118 > FIN > Disbursement : REVERSAL Disbursement showing 2 EJ - Overriding and Success for Dormant Account | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA
4643 | 668 | Remittance | Open | Signed Off | Signed Off | RBS to send the Narration + Description Code to Host in Remarks field via transaction code 6690 |  |  |  | Y | Y | Y |  | Azuwah

## R5.6.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4680 | 2-Medium | Deposit 3 | Fixed | RBS SG PROD | Phase Delivery-In Phase 5.6 | Duplicate checkbox in printing TD advice | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA
4660 | 672 | Deposit 2 | Fixed | N/A | WIP | Teller limit change from S$2000 to S$20,000 |  |  | Y |  |  | Y |  | Hamidah

## R5.6.2 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4678 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Payment to “Life insurance” Ilog will function the same as Payment to “General Insurance” |  |  | Y
4681 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Account closure with TAU : ilog prompt message is incorrect | Y
4679 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Prod Issue - RSO No Supervisor |  |  | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA
4660 | 673 | Deposit 2 | Fixed | Y | Y | Reinstate Teller limit change from $20,000 to S$2000 |  |  | Y |  |  | Y |  | Hamidah

## R6.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4664 | 2-Medium | Deposit 2 | Fixed | RBS SG UAT |  | ESB Error In FCCA Account Closure |  |  |  | Y
4665 | 2-Medium | Deposit 2 | Fixed | RBS SG UAT |  | Transaction count summary does not increment | Y
4657 | 3-Low | Deposit 2 | Fixed | RBS SG UAT |  | System to block other branches from performing FCCA Cash Withdrawal to 038 Account | Y
4653 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Regional Link - Unknown error during reversal | Y
4684 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Outward FTT - no iLog prompted for account activation | Y
4695 | 3-Low | Remittance | Fixed | RBS SG SIT |  | REM Outward FTT: Able to perform Outward FTT with 0.00 total amount | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA
4619 | 664 | Remittance | Fixed | Y | Y | SO Rules for txn code 7630 Inward TT |  |  | Y |  |  | Y | MSS BAU Cost | Azuwah
4368 | 610 | Remittance | Fixed | N/A |  | Outward TT to MBB PHP decimal data error |  |  |  | Y |  | Y | MSS BAU Cost | Azuwah
4435 | 621 | Deposit 2 | Fixed | Y | Y | iLOG - cheque withdrawal limit for teller should change from $30,000.00 to $10,000.00 |  |  | Y |  |  | Y | MSS BAU Cost | Azuwah
4682 | 681 | Remittance | Fixed | Y | Y | To amend FTT to make Bene A/C No mandatory | Y |  |  |  |  | Y | MSS BAU Cost | Azuwah

## R6.1.1 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA
4690 | 686 | NAO | Fixed | Y | Y | Form Changes - Individual Account Opening Form | Y | Y |  |  |  | Y |  | Leila
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4711 | 3-Low | NAO | Fixed | RBS SG UAT |  | Typo error on Joint Account form | Y

## 23Apr - 6.1, 6.1.1 (hidden)
Defects - R5.6.2
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4679 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Prod Issue - RSO No Supervisor |  |  | Y
Defects - R6.1
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4664 | 2-Medium | Deposit 2 | Fixed | RBS SG UAT |  | ESB Error In FCCA Account Closure |  |  |  | Y
4665 | 2-Medium | Deposit 2 | Fixed | RBS SG UAT |  | Transaction count summary does not increment | Y
4657 | 3-Low | Deposit 2 | Fixed | RBS SG UAT |  | System to block other branches from performing FCCA Cash Withdrawal to 038 Account | Y
4653 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Regional Link - Unknown error during reversal | Y
4684 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Outward FTT - no iLog prompted for account activation | Y
4695 | 3-Low | Remittance | Fixed | RBS SG SIT |  | REM Outward FTT: Able to perform Outward FTT with 0.00 total amount | Y
PCR - R6.1
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host |  | Remarks | BA
4619 | 664 | Remittance | Fixed | Y | Y | SO Rules for txn code 7630 Inward TT |  |  | Y |  |  |  | MSS BAU Cost | Azuwah
4368 | 610 | Remittance | Fixed | N/A |  | Outward TT to MBB PHP decimal data error |  |  |  | Y |  |  | MSS BAU Cost | Azuwah
4435 | 621 | Deposit 2 | Fixed | Y | Y | iLOG - cheque withdrawal limit for teller should change from $30,000.00 to $10,000.00 |  |  | Y |  |  |  | MSS BAU Cost | Azuwah
4682 | 681 | Remittance | Fixed | Y | Y | To amend FTT to make Bene A/C No mandatory | Y | [5 empty] | MSS BAU Cost | Azuwah
PCR - R6.1.1
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host |  | Remarks | BA
4690 | 686 | NAO | Fixed | Y | Y | Form Changes - Individual Account Opening Form | Y | Y | [5 empty] | Leila
Defects - R6.1.1
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4711 | 3-Low | NAO | Fixed | RBS SG UAT |  | Typo error on Joint Account form | Y
Note on F19: Pending ESB documentation

## R6.1.2 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4720 | 693 | Remittance | Fixed | N | N | MYR RATE not showed at AS400 | Y |  |  | Y |  | Y | MSS BAU Cost | Azwa | Rakesh
4718 |  | Back Office | Fixed | N | N | Store and Forward Process | Y | [7 empty] | Aimi

## R6.1.3 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4723 | 694 | Fixed | Fixed | N | N | Account Opening form | Y |  |  |  |  | Y | MSS BAU Cost | Ida | Roziyah

## R6.2 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4687 | 684 | NAO | Fixed | N | N | TR Integration | Y |  |  |  |  | Y |  | Ida | Rakesh, Suriati, Roziyah

## R6.2.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4794 | 3-Low | NAO | Fixed |  |  | NAO Unit Trust Business Account creation - No NRIC | Y
4795 | 2-Medium | NAO | Fixed |  |  | RBS UT Account Opening error | Y
Technical PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4796 | 707 | NAO | Fixed | Y | Y | To disable "Name Screen" button for nao and eao | Y |  |  |  |  | No WO. MSS BAU |  |  | Rakesh

## R6.2.2 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4817 | 3-Low | NAO | Closed |  |  | To parameterize the "Name Check"/ "Search" button

## R6.3 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
3934 | 3-Low | OEM | Fixed | RBS SG SIT | Phase Delivery-in Phase 3.9.2 | OEM balancing T + 1 | Y
4418 | 3-Low | OEM | Fixed | RBS SG SIT | Phase Delivery-in Phase 3.9.2 | OEM > If teller is login in Emergency Mode and decided to logout - prompt message | Y
4423 | 3-Low | OEM | Fixed | RBS SG SIT | Phase Delivery-in Phase 3.9.2 | Release 3.9.2 > OEM > Transactions performed in OEM cannot be found if teller logout in OEM and login in Online Mode | Y
4424 | 3-Low | OEM | Fixed | RBS SG SIT | Phase Delivery-in Phase 3.9.2 | Release 3.9.2 > OEM > Cash Officer - no emergency recovery option | Y
4699 | 3-Low | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Reversal bypass overriding | Y
4702 | 2-Medium | Remittance | Fixed | RBS SG UAT |  | Unable to view the remittance group enquiry screens for inward tt payment mode CASH and GL. |  |  |  | Y
4703 | 2-Medium | Remittance | Fixed | RBS SG UAT |  | No Supervisor Override prompt for Inward TT amount exceed 50k for Officer | Y
4710 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Fund Transfer SA to SA invalid account validation | Y
4713 | 2-Medium | Common | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | RBS core dump error_2017Apr03 | Y
4717 | 2-Medium | Branch Operations | Fixed | RBS SG PROD | Phase Delivery-In Phase 5.6 | Unable to print Branch Cash Position Summary | Y
4733 | 2-Medium | Common | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | RBS postal code batch job | Y
4740 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Manual Posting DD: No Vostro Account found in JMS log. | Y
4742 | 3-Low | Deposit 2 | Closed | RBS SG SIT |  | DP2_FCTD_Top Up_Failed in performing reversal transaction |  |  |  | Y
4743 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2 ACCOUNT CLOSURE - STRING PI ERROR | Y
4745 | 3-Low | Financing | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | Loans Payment (Debit to CASA and Credit to Loans acct) | Y
4750 | 3-Low | Remittance | Fixed | RBS SG SIT |  | DD Encashment with MT110 hits Internal System Error |  |  |  | Y
4757 | 3-Low | Back Office | Fixed | RBS SG SIT |  | BOF > Inward Retun_ Transaction failed with no ESB Transaction No. | Y
4804 | 3-Low | NAO | Fixed | RBS SG SIT |  | Typo error on Joint Account form | Y
4815 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2 - FCTD ACCOUNT CLOSURE NO PRINT OUT AND REPRINT | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4432 | 622 | Remittance | Fixed | Y | Y | Special Rate and Contract Ref to be printed on form | Y |  |  |  |  | MSS BAU |  | Azuwah | Rakesh
4564 | 650 | Remittance | Fixed | Y | Y | New Clause to be printed on replacement of CO | Y |  |  |  |  | MSS BAU |  | Azuwah | Rakesh
4662 | 674 | Deposit 3 | Fixed (Agreed) | Y |  | To update Branch Delivery Services Report Form for PDC | Y |  |  |  |  | MSS BAU |  | Ida | Roziyah, Gangashri
4724 | 695 | Deposit 3 | Fixed | Y | Y | Form change - Authorisation & Indemnity to increase no of acc holders form | Y |  |  |  |  | MSS BAU |  | Ida | Roziyah, Gangashri
4663 | 675 | Deposit 4 | Fixed | Y | Y | Removal of bulk posting of letters | Y | Y |  |  |  | MSS BAU |  | Leila/Ida | Aimiza
4674 | 678 | Financing | Fixed | Y | Y | HP Repayment Requirement | Y | Y |  |  |  | Y |  | Ida | Rakesh
4701 | 689 | Deposit 2 | Fixed | Y | Y | Enabling Cash Withdrawal without ATM/Passbook - with overriding | Y | Y | Y |  |  | MSS BAU |  | Azuwah | Aimiza
4709 | 692 | Deposit 2 | Fixed | Y | Y | Overriding for Cash Advance by Foreign Credit Card | Y |  | Y |  |  | MSS BAU |  | Azuwah | Aimiza
4725 | 696 | Deposit 3 | Fixed | Y | Y | Form change - Lost of Passbook Indemnity | Y |  |  |  |  | MSS BAU |  | Ida | Roziyah, Gangashri
4726 | 697 | Deposit 3 | Fixed | Y | Y | Form change - eServices Form | Y |  |  |  |  | MSS BAU |  | Ida | Roziyah, Gangashri
4727 | 698 | Deposit 3 | Fixed | Y | Y | Form change - Mandate for an Account | Y |  |  |  |  | MSS BAU |  | Ida | Roziyah, Gangashri
4731 | 702 | Common | Open | Y | Y | Streamline and reduce the list of available GLs under drop down list - by 30/6 to give the final GL list |  | Y |  |  |  | MSS BAU |  | Azuwah | Ramesh
4782 | 699 | Deposit 3 | Fixed | Y | Y | Form change - Update of Signature | Y |  |  |  |  | MSS BAU |  | Ida | Roziyah, Gangashri
Performance Enhancement
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4704 | 3-Low | Common | Fixed | RBS SG Performance Enhancement |  | Stock Count Register - performance improvement for Search function | Y
4705 | 3-Low | Common | Fixed | RBS SG Performance Enhancement |  | Surprise Cash Check - performance improvement in landing page | Y
4706 | 3-Low | Common | Fixed | RBS SG Performance Enhancement |  | Login Part I - performance improvement from banner to login page | Y
Note on A4: For this release 6.3 we will still proceed to test the pop-out notification The full fix (end to end) for Defect 3934 will be included together with Defect 3370 Defect 3934 has been closed in HPQC.
Note on E15: LI BAU Sev 2
Note on E16: LI BAU Sev 2
Note on E17: LI BAU Sev 2
Note on E19: LI BAU Sev 2
Note on E20: LI BAU Sev 2

## R6.3.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4817 | 3-Low | NAO | Closed | RBS SG PROD |  | To parameterize the "Name Check"/ "Search" button
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4824 | 711 | Common | Closed | Y | Y | To change the Supervisor Overriding Limit | Y |  |  |  |  | MSS BAU |  | Azuwah | Yusrin
4827 | 713 | Common | Closed | Y | Y | Disable forfeit interest | Y |  |  |  |  | MSS BAU |  | Azuwah | Yusrin

## R6.4 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4763 | 703 | NAO | Open | Y | Y | TR Phase 2 | Y |  |  |  |  | Y |  | Ida | Rakesh
4803 | 709 | NAO | New | Y | Y | Name Screening - Enable Ongoing screening option from API | Y | [6 empty] | Ida | Rakesh
4835 | 715 | NAO | New | Y | Y | To display/print Entity Type in Summary/Violation Section and AO form | Y | [6 empty] | Ida | Rakesh
4839 | 719 | NAO | New | Y | Y | To include parameterization of enabling/disabling the search feature for TR Phase 2 | Y | [6 empty] | Ida | Rakesh
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4764 | 3-Low | NAO | Open |  |  | Some fields are truncated for NAO Business Acct Opening form
4799 | 3-Low | NAO | Open | RBS SG SIT |  | UT NAO->Subscription flow
4814 | 2-Medium | NAO | Open | RBS SG PROD |  | Blank phone numbers created/updated in RBS
4765 | 3-Low | NAO | Fixed | RBS SG PROD | Phase Delivery-In Phase 1.0 | UT joint account UV print only primary account holder
4825 | 3-Low | Financing | Fixed | RBS SG PROD | Phase Delivery-In Phase 6.3 | Ln Adjustment & Maintenance - Account Name no value
4843 | 1-Critical/Showstopper | Deposit 2 | Fixed | RBS SG UAT | Phase Delivery-In Phase 6.3 | UAT > Misc debit uncaught exception
FIXED LI Deferred Defect
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE | LI Defect ID
4737 | 3-Low | BOF | Deferred to BAU / Fixed |  |  | BOF> CNY PACK: CANNOT PERFORM REVERSAL REPRINT | [6 empty] | 74
4738 |  | BOF | Deferred to BAU / Fixed |  |  | LI_BNC_BOF > Outward Return : UNABLE to REVERSAL REPRINT for Function CA OUTWARD RTD CHEQUE | [6 empty] | 96
|  | BOF | Deferred to BAU / Fixed |  |  | LI_BNC_BOF > OUTWARD RETURN > Function = CA DIRECT INWARD MC RTD : Missing Cover note & UV during REVERSAL Reprint | [6 empty] | 98
|  | BOF | Deferred to BAU / Fixed |  |  | LI_BNC_BOF > OUTWARD RETURN > Function = CA RETURNED CASH CHEQUE : Missing Cover note & UV during REVERSAL Reprint | [6 empty] | 128
4753 |  | DP2 | Deferred to BAU / Fixed |  |  | LI>BNC>DP2>WITHDRAWAL: Missing Reprint document at EJ for FCCA Cash Withdrawal without Commission (6600,9650) | [6 empty] | 157
4776 |  | REM | Deferred to BAU / Fixed |  |  | Remittance Outward FDD Issuance transaction with Payment mode GL - EJ Discrepancy | [6 empty] | 158
4751 |  | BOF | Deferred to BAU / Fixed |  |  | LI>BNC>BOF:Outward return - CO Outward return UNABLE to REVERSE | [6 empty] | 165
4777 |  | REM | Deferred to BAU / Fixed |  |  | Remittance Outward CO - CO Issuance Text printing Discrepancy | [6 empty] | 172
4776 |  | REM | Deferred to BAU / Fixed |  |  | Remittance Outward CO - Payment Mode - House Cheque - EJ Discrepancy for TransCode - 0620_1 | [6 empty] | 175
4747 |  | REM | Deferred to BAU / Fixed |  |  | LI_BNC_REM_BSRE100_Vostro Account Credit_001 - REVERSAL REPRINT NOT WORKING | [6 empty] | 209
4770 |  | DP2 | Deferred to BAU / Fixed |  |  | Cheque Deposit transaction - Debit Account Name Field discrepancy | [6 empty] | 335
4784 |  | DP2 | Deferred to BAU / Fixed |  |  | LI_RGB_DP2_MISC DEBIT 005 - Reference code shown when default value is Blank is "---Please Select---" | [6 empty] | 431

## R6.5 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4862 | 722 | NAO | Open | Y | Y | Label change from “Registered Address as per NRIC” to “Residential Address” for Individual account opening form | Y | [6 empty] | Leila | Ganga
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4734 | 3-Low | DP3 | Fixed | RBS SG SIT |  | Error message displayed for Reissue/Lost Passbook using valid Islamic Passbook serial number. | Y
4744 | 3-Low | NAO | Fixed | RBS SG SIT |  | CASA Business Account creation, After Account creation, Service enrollment screen is not displayed. | Y
4749 | 3-Low | Deposit 4 | Fixed | RBS SG SIT |  | DP4 SERVICE INQUIRY - CIF NO. NOT Showing in printed form | Y
4760 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_FUND TRANSFER_Hit Partial Failed for Reversal transaction for Fund Transfer FCCA to FCCA Misc Debit with GL | Y
4761 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_WITHDRAWAL CASH: Missing Rate value at UV for Reversal transaction Withdrawal Cash-FCTDA Interest Withdrawal Cross Currency, Commision Type: Debit From Gross Amount | Y
4769 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Wrong CILE Amount updated at Teller Total EOD | Y
4782 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_Placement_FCTD_Getting Account Not Found Error | Y
4828 | 3-Low | Reports | Fixed | RBS SG PROD |  | Stock Count Register printout | Y
4833 | 2-Medium | TAM | Fixed | RBS SG PROD |  | TAM - ID cannot be updated at User Mapping Screen | Y
4846 | 3-Low | NAO | Fixed | RBS SG UAT |  | Parsing of parameters for name screening | Y
4845 | 3-Low | Remittance | Fixed | RBS SG PROD |  | Outward FFT same currency using payment mode ACUD | Y
4854 | 2-Medium | Third Party | Fixed | RBS SG PROD |  | UT SUBSCRIPTION CANNOT PROCESS WITH ERROR MSG :"SIBS:INVALID RELATIONSHIP" | Y
4852 | 3-Low | Financing | Fixed | RBS SG PROD |  | Loan Financing Adjustment & Maintenance GL Refno | Y
4748 | 3-Low | Back Office | Fixed | RBS SG SIT |  | STORE AND FORWARD: Report - Overlapping on the 2nd line Header | Y
4752 | 3-Low | Deposit 4 | Fixed | RBS SG SIT |  | DP4_AccountInquiry_001_16_Additional - Debit Card not printing the values in the Form and Printing different information to rbs screen | Y
4768 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_ACCOUNT CLOSURE for FCTD - PRINTING ISSUE | Y
4771 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_Payment Collection Account - HP : REV UV not alligned properly on the GL no. compared to the Forward UV | Y
4772 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_MISC DEBIT: Missing NET PFT PAYABLE for Reversal of Misc Debit-TD Interest Withdrawal Non Cash | Y
4778 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Remittance outward FTT issuance - Reversal transaction printing mismatch with original transcation printing. | Y
4779 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Remittance Outward FTT Issuance - MBB - Back of the Cheque & FORM Printing Mismatch. | Y
4780 | 3-Low | Remittance | Fixed | RBS SG SIT |  | UV Reprint issue for Outward FTT transaction using payment mode ACUD | Y
4785 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_WITHDRAWAL CASH: Missing currency code for CILE amount on UV for REVERSAL trx-Withdrawal Cash -FCTDA Interest withdrawal, Commission Type: Cash (SGD/FCCA) | Y
4808 | 3-Low | Financing | Fixed | RBS SG SIT |  | Loans/Financing -Unbilled payment using payment code as House Cheque got EJ details discrepancy | Y
4754 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_TDPlacement_Alignment for service charge is incorrect | Y
4755 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2 > Cash Deposit Reversal - Printing alignment issue | Y
4758 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_MISC CREDIT_001 : Incorrect UV printing | Y
4773 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2 > Multiple Deposit Issue (tested in BAU with same result) | Y
4788 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Account Closure - Not proceeding with FCCA Closure with credit balance - Remittance(Mode of Payment) | Y
4789 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Account Closure - Partila fail on FCCA Closure with credit balance - Miscellaneous without Nostro (Mode of Payment) | Y
4790 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | WITHDRAWAL: Rate value is missing at UV printout for Reversal transaction FCCA Cross Currency (all trx) | Y
4791 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Cash Deposit > FCCA same currency without CILE having printing issue (tested same with BAU) | Y
4792 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Cash Deposit > FCCA cross currency > with CILE - commission debit from account (FCCA - same ccy) (tested the same in BAU) | Y
4806 | 3-Low | Financing | Fixed | RBS SG SIT |  | Narration field should be printed above the payment mode for Rollover Repayment_FundTrf EJ Rev trans | Y
4813 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | DP2_FCTD_Placement_Error in UV Printing for CILE Amount for Reverse Transaction | Y
4855 | 3-Low | Common | Fixed | RBS SG SIT |  | Unable to perform "Search" with "EJ Journal Num" | Y

## R6.5.1 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4860 | 720 | Common | Open | Y | Y | Teller limit change from S$2000 to S$20,000 |  |  | Y |  |  |  |  | Leila | Aimi
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
Performance
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
Parameterization
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev

## R6.5.2 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4861 | 721 | Common |  | Y | Y | Reinstate Teller limit change from $20,000 to S$2000 |  |  | Y |  |  |  |  | Leila | Aimi
4874 | 727 | Financing |  | Y | Y | Change in RBS overriding rule for RCAD |  |  | Y |  |  |  |  | Ida | Yusrin
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
Performance
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
Parameterization
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev

## R7.1 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4838 | 718 | Remittance | Open |  | Y | MBB SG to tag on to MBB MY CRS Draft Issuance | Y | Y | [5 empty] | Azuwah | Ramesh
4883 | 733 | Remittance | Open |  | Y | CRS draft issuance to map the EUR country code to host | Y |  |  | Y |  |  |  | Azuwah | Ramesh
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE | SIT DROP
4805 | 3-Low | Financing | Fixed | RBS SG SIT |  | For Adj Maintenance - Credit agent commission transaction Collateral id is not reflecting inEJ details box | Y
4822 | 3-Low | Remittance | Fixed | RBS SG PROD |  | RSW Issue ->Transaction was not logged in MBBEJINQRYLG nor FSTJOURNALENTRY,The screen only shows "ERROR", instead of "Host error, PIN PAD error" | Y
4823 | 3-Low | Deposit 3 | Fixed | RBS SG SIT |  | Upon BA & SIT anlysis, below are the discrepancies between Form Definition and Test output of eServices | Y
4858 | 3-Low | Deposit 2 | Fixed | RBS SG PROD |  | TAU details wasn't displayed in EJ (for all account types)as opposed to Cash Withdrawal. | Y
4853 | 3-Low | Financing | Fixed | RBS SG SIT |  | Detected in LI 506, deferred to BAU. Unable to perform Credit Capitalize Late Charge DS txn. |  |  |  | Y
4809 | 3-Low | Financing | Fixed | RBS SG SIT |  | Transaction should not able to go through with out selecting the mandatory field(Product Category) | Y
4807 | 3-Low | Financing | Fixed | RBS SG SIT |  | Fin-Manualsplit Repayment alignamnet issue | Y
4811 | 3-Low | Deposit 3 | Fixed | RBS SG SIT |  | DP3 > Time Deposit: Alignment issues in TD Advice-Islamic printings | Y |  |  |  |  | Y
4812 | 3-Low | Deposit 3 | Fixed | RBS SG SIT |  | DP3 > Time Deposit: Alignment issues in Yield Enhancement Structure - Dual Currency TD Advice printing | Y |  |  |  |  | Y
4859 | 3-Low | Deposit 3 | Fixed | RBS SG UAT |  | Related to PCR#697/4726 - E-Services Form (UAT 4823) | Y
4879 | 3-Low | Financing | Fixed | RBS SG SIT |  | Financing - GST amount rounding calculation | Y
4793 | 3-Low | Remittance | Fixed | RBS SG SIT |  | RBS should have a vaiidation for <remittance group number>field to only allow only 15 chars. | Y
4783 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Cash Withdrawal (using ATM option) - REVERSAL FAILED |  |  |  | Y
4864 | 3-Low | Deposit 4 | Fixed | RBS SG SIT |  | DP4 BNC - Account Inquiry screen | Y
4865 | 3-Low | Deposit 3 | Fixed | RBS SG SIT |  | DP3: Account Maintenance: Add Relationship-Few fields are not printing values in "Authorisation & indemnity to increase number of Account Holders form" | Y
4882 | 3-Low | Financing | New | RBS SG UAT |  | Loans/Financing > Bulk Repayment function, whereby when land on the screen the default value is not as per screen properties. | Y
4886 | 3-Low | Remittance | Fixed | RBS SG SIT |  | CRS draft issuance (ACUD) | Y
4890 | 3-Low | Remittance | Open | RBS SG UAT |  | The exchange Rate is showing 1.0000000 for SGD-AUD currency | Y
Performance
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks
Parameterization
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks
[14 empty] | BA | Dev
[14 empty] | BA | Dev

## R7.1.0.5 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4910 | 749 | Financing | Fixed | Y | Signed Off | To rectify the screen properties for FIN Adjustment & Maintenance | Y |  |  |  |  | Y |  | Azwa | Ramesh, Rozi, Suriati
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4911 | 2-Medium | Remittance | Fixed | RBS SG SIT |  | Remittance group number validation | Y

## R7.1.1 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4885 | 734 | NAO | Fixed | Y | Signed Off | Country Code - KOSOVO |  | Y |  |  |  | Y |  | Ida | Rozi
4889 | 735 | Deposit 2 | Fixed | Y | Signed Off | FC ilog |  |  | Y |  |  | Y |  | Leila/Ida | Mani
4892 | 737 | Deposit 2 | Fixed | Y | Signed Off | FX | Y |  |  |  |  | Y |  | Leila/Ida | Rakesh
4895 | 739 | Common | Fixed | Y | Signed Off | TAU - Audit Issue | Y |  |  |  |  | Y |  | Ida | Rozi
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE | SIT DROP
4890 | 3-Low | Remittance | Fixed | RBS SG UAT |  | The exchange Rate is showing 1.0000000 for SGD-AUD currency | Y
Performance
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks
4888 |  | Common | Fixed | - | - | To measure improvement response time | Y
4847 |  | Common | Fixed | - | - | Login Part 2 - from open drawer page to landing page | Y
Parameterization
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks

## R7.1.2 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4908 | 747 | Remittance | Fixed | Y | Signed Off | Change of NOSTRO Agent for IDR | Y | Y |  |  |  | Y |  | Azwa | Rakesh
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE | SIT DROP
4913 | 2-Medium | Remittance | Fixed | RBS SG UAT |  | Regional Link MYR Rate Zero Issue | Y
4914 | 3-Low | Deposit 2 | Fixed | RBS SG UAT |  | User cancel the Supervisor Override message box the txn still go thru | Y
4916 | 3-Low | Remittance | Fixed | RBS SG UAT |  | Regional Link MYR Zero Rate - Special Rate | Y

## R7.1.3 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4952 | 761 | Common | Fixed |  | Signed Off | TAU recalibration - Amount from Drawer display wrong amount | Y | Y |  |  |  | Y |  | Ida | Ramesh
4904 | 746 | Common | Fixed |  |  | TAU cartridge changes from $2 to $100 bills | [5 empty] | Y |  | Ida | Ramesh
4966 | 771 | Remittance | Fixed |  | Signed Off | "For PSC Kovan only" missing checkbox for MBS | Y | Y |  |  |  | Y |  | Ida | Ramesh

## R7.2 (hidden)
Performance
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks
4920 |  | BOP | Fixed | - | - | Teller Logout EOD | Y
4921 |  | BOP | Fixed | - | - | Branch Logout EOD | Y
4850 |  | BOP | Fixed | - | - | Branch Inquiry and Final Totals | Y
4851 |  | BOP | Fixed | - | - | Negotiable Items Activity Log | Y
4848 |  | BOP | Fixed | - | - | Balance Drawer(Drawer Selection) | Y
4849 |  | BOP | Fixed | - | - | Balance Negotiable Item Drawer | Y
4939 |  | BOP | Fixed | - | - | Balance Drawer LC/FC | Y
Parameterization
Defect ID | PCR SEQ NO | Functions (Remittance) | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks
4919 | 750 (Technical PCR) | Inward Register SGD | Fixed | - | - |  | Y | Y
|  | Inward SGD |  | - | - |  | Y | Y
|  | Inward FCY |  | - | - |  | Y | Y
|  | Foreign Currency Notes |  | - | - |  | Y | Y
|  | Regional Link |  | - | - |  | Y | Y
|  | Outward FTT |  | - | - |  | Y | Y
|  | Outward and Issuance FDD |  | - | - |  | Y | Y
|  | Outward and Issuance MEPS |  | - | - |  | Y | Y
|  | Outward and Issuance CO |  | - | - |  | Y | Y
|  | Reissue Demand Draft |  | - | - |  | Y | Y
Defects (Backlog)
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4927 | 3-Low | Remittance | Fixed | RBS SG PROD |  | FDD issuance printing - missing amount in words | Y
4926 | 3-Low | Remittance | Fixed | RBS SG UAT |  | Inward FCY hit Invalid Input Data error | Y
LI-Deferred to BAU
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4915 | 3-Low | Common | Fixed |  |  | inquiry screen automatically exits without displaying error msg on inq screen | Y
4944 | 3-Low | Deposit 3 | Fixed |  |  | LI 2>RGB>DP3>DP3_Cheque Maintenance_004 - Stop cheque printout issue | Y
4945 | 3-Low | Remittance | Fixed |  |  | LI Phase2 > SIT > RBS > REM > Outward FTT Reversal Printing Issue | Y
4949 | 3-Low | Deposit 2 | Fixed |  |  | Late' status not shown on the UV vouchers for 'ETIQA General' and 'ETIQA Life' | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4959 | 766 | Common | Fixed |  | signed off | Teller limit change from S$2000 to S$20,000 |  |  | Y |  |  | Y |  | Ida | Mani
4958 | 765 | Financing | Fixed |  | signed off | Adjust settings of printing of new guarantee form via RBS due to local incorporation | Y |  |  |  |  | Y |  | Ida | Kimberly

## R8.0.1 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4960 | 767 | Common | Fixed |  | Signed off | Reinstate Teller limit change from $20,000 to S$2000 |  | Y |  |  |  | Y |  | Ida | Mani

## R8.0.2 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4896 | 3-Low | Remittance | Fixed | RBS SG PROD |  | 7270 CO Outward Return | Y
4923 | 3-Low | Branch Operations | Fixed | RBS SG PROD |  | Discrepancy on BND balancing | Y
4946 | 3-Low | Deposit 2 | Fixed | RBS SG SIT (LI Deferred) |  | FCTD Interest Withdrawal_Teller Total_011 | Y
4953 | 3-Low | Remittance | Fixed | RBS SG PROD |  | Trancode 7630 - Contract RefNo | Y
4985 | 2-Medium | Deposit 2 | Fixed | RBS SG PROD |  | Trancode 6730 is not sending auxiliary code | Y
4991 | 3-Low | Branch Operation | Fixed | RBS SG SIT |  | PCR770_Defect4963 : TAU Drawer creation and updation in TAM is not saving for value "TAU Position" and "TAU Device". | Y
5008 | 3-Low | NAO | Fixed | RBS SG SIT |  | NAO: System is concatenating all the forms printing based on Forms screen check box(s) selection | Y
5009 | 3-Low | NAO | Fixed | RBS SG SIT |  | SVS: IB & PB related forms also sending to thin-client upon checkbox selection at Forms screen | Y
5017 | 3-Low | Common | Fixed | RBS SG UAT |  | Change TAM error message for TAU Co-Sharing enhancement | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4963 | 770 | Common | Fixed | Y | signed off | Enable TAU to be shared by MSL and MBS | Y | Y |  |  |  | Y |  | Ida | Ramesh
4984 | 782 | Deposit 2 | Fixed | NA | NA | SG Ilog migration from Ilog Server to DB (DP2 - 4 rules - Cash Withdrawal) | Y | Y |  |  |  | N |  | Ida | Mani
4998 | 787 | NAO | Fixed | Y | signed off | SDIC amount changes from $50k to $75k to RBS forms and account opening | Y |  |  |  |  | Y |  | Leila | Kim

## R8.0.3 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
5023 | 2-Medium | Remittance | Fixed | RBS SG PROD |  | PROD - Remittance MEPS SO Issue |  |  | Y
5025 | 2-Medium | Remittance | Fixed | RBS SG PROD |  | Trancode 7630 Inward TT | Y
5026 | 2-Medium | SVS | Fixed | RBS SG PROD |  | SVS signature capturing | Y

## R8.1 (hidden)
Performance
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks
4964 |  | BOP - Branch Cash Position Summary | Fixed | - | - | Improve the performance by reducing the number of Client Server Communication and multiple database calls to fetch the drawers related information | Y
4965 |  | BOP - Branch Close Cash | Fixed | - | - | Improve the performance by reducing the number of Client Server Communication and multiple database calls to fetch the users and drawers related information | Y
Parameterization
Defect ID | PCR SEQ NO | Functions (NAO, Deposit3) | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks
4935-NAO | PCR 750 (Technical PCR) | Add Individual Customer | Fixed |  |  |  | Y | Y
|  | Add Business Customer |  |  |  |  | Y | Y
|  | Account Opening - Adverse Check Individual |  |  |  |  | Y | Y
|  | Account Opening - Add Account for Individual |  |  |  |  | Y | Y
|  | Account Opening – Service Enrollment |  |  |  |  | Y | Y
|  | Account Opening - Adverse Check Non Individual |  |  |  |  | Y | Y
|  | Account Opening - Add Account for Non Individual |  |  |  |  | Y | Y
|  | View/Edit Existing Individual Customer |  |  |  |  | Y | Y
|  | View/Edit Existing Non Individual Customer |  |  |  |  | Y | Y
|  | Express Account Opening |  |  |  |  | Y | Y
4936-DP3 |  | Account Services - New eServices Issuance | Fixed |  |  |  | Y | Y
|  | Account Services - PDC pack |  |  |  |  | Y | Y
|  | Modify Passbook Details |  |  |  |  | Y | Y
|  | Account Maintenance - Add/Delete Hold |  |  |  |  | Y | Y
|  | Account Maintenance - Add Relationship |  |  |  |  | Y | Y
4955-TAM |  | TAM Parameterization (REM, NAO, DP3) | Fixed |  |  |  | Y | Y
Defects (Backlog)
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4869 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | FCCA CASH DEPOSIT CCY with CILE in SGD - CILE Amount has been added to CASH OUT drawer instead of CASH IN | Y
4870 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | FCCA Cash withdrawal - behaviour of OK button when there is no SVS and signature retrieval failed | Y
4871 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Cash Withdrawal CILE refresh issue | Y
4878 | 2-Medium | Financing | Fixed | RBS SG SIT |  | Adjustment & Manitenance : All Adjustment Category screens will not reset the default value | Y
4893 | 3-Low | TAM | Fixed | RBS SG UAT |  | TAM remittance settings for Staff and Customer for same rem type and currency | Y | Y
4902 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | ilog Issues arising from PCR735 | Y
4905 | 2-Medium | Common | Fixed | RBS SG SIT |  | iLog issue for ROW 346 - Officer CNY boundary (arising from PCR735) | Y |  | Y
4912 | 3-Low | Financing | Fixed | RBS SG UAT |  | No Narration field in Capitalize Late Charge screen | Y
4917 | 3-Low | Remittance | Fixed | RBS SG SIT |  | System did not validate the Debiting Account | Y
4933 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Outward FTT disabled IC No and Applicant Name after change payment mode | Y
4940 | 3-Low | Common | Fixed | RBS SG SIT |  | Unable to delete branch in TAM | Y
4957 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | FCCA Cash Withdrawal REVERSAL – with CILE payment mode Cash in SGD | Y
4979 | 3-Low | Deposit 3 | Fixed | RBS SG SIT |  | DP3 > Add Relationship > Showing additional drop down value "P Primary" | Y | Y
5008 | 3-Low | NAO | Fixed | RBS SG SIT |  | NAO: System is concatenating all the forms printing based on Forms screen check box(s) selection | Y
5009 | 3-Low | NAO | Fixed | RBS SG SIT |  | NAO> Form Reprint > Even though user selected 'Application Form' check box, system is printing the remaining forms also | Y
5022 | 3-Low | NAO | Fixed | RBS SG SIT |  | NAO application form printing issue in SIT | Y
5031 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | SVS Error message not displaying on Cash Withdrawal screen | Y
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
5001 | 788 | Deposit 2 | Signed off | NA | NA | [R8.1] SG ILog migration from ILog Server to DB : 63 rules - cash withdrawal 20 rules - cheque withdrawal 60 rules - FCY Common rules 70 rules - Cash & Cheque Deposit 39 rules - Payment - TAM screen | Y | Y |  |  |  | N |  | Ida
5005 | 792 | Back Office | Signed off | Y |  | To reinstate GLs for Back Office |  | Y |  |  |  | Y |  | Leila
5013 | 794 | Remittance | Signed off | NA |  | System Enhancement for MYR AOO | Y |  |  | Y | Y | Y |  | Leila
5014 | 795 | Deposit 2 | Signed off | N |  | Ilog Group for Remittance/ComCentre Unit |  |  | Y |  |  | Y |  | Ida

## R8.1.1 (hidden)
Defects
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
5047 | 2-Medium | Deposit 3 | FIXED | RBS SG PROD |  | Prod - Service issuance Success but not deducted from the stocks | Y
5048 | 2-Medium | Branch Operations | FIXED | RBS SG PROD |  | Branch cash position summary does not tally but can close | Y

## R8.1.2 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4891 | 736 | NAO | Fixed |  | N/A | SSIC Codes Changes |  | Y |  |  |  | Y |  | Leila | Mani

## R8.1.3 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
5049 | 803 | NAO | Fixed |  | Sign off | To add SDIC header in NAO form | Y |  |  |  |  | Y |  | Ida | Mani

## R8.1.4 (hidden)
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
5050 | 804 | Deposit 2 | Fixed |  | Sign off | SCB onboard new BIC SCBLSG22 for SCB Singapore Limited (Subsidiary) | Y | Y |  |  |  | Y |  | Ida | Ramesh

## R8.2 (hidden)
Defects (Backlog)
Defect ID | Severity | Workstream | Status | Detected in Release | Originated from Version | Summary | ET | DB | iLog | ESB | Host | SOE
4999 | 3-Low | Common | Fixed | RBS SG PROD |  | Prod EOD balance screen issue | Y
5010 | 3-Low | SVS | Fixed | RBS SG SIT |  | SVS: Signature Boxes alignment issue in Individual Single & Joint Forms | Y
5011 | 3-Low | SVS | Fixed | RBS SG SIT |  | SVS: IB & PB related forms also sending to thin-client upon checkbox selection at Forms screen | Y
5012 | 3-Low | Reports | Fixed | RBS SG SIT |  | SVS: Thin-client is showing redundant forms | Y
5016 | 3-Low | NAO | Fixed | RBS SG SIT |  | NAO: Unable to print Application Form when user did not performed Name Screening for all joint holders | Y
5029 | 3-Low | Remittance | Fixed | RBS SG SIT |  | SO ILog Rules Issues | Y
5034 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Expectation when enter invalid CIF/IC number | Y
5036 | 3-Low | Remittance | Fixed | RBS SG SIT |  | Screen Exit after changing Agent Type | Y
5039 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Regression on Defect#5031 : SVS Error message not displaying in Cash Withdrawal screen | Y
5040 | 3-Low | Deposit 2 | Fixed | RBS SG SIT |  | Regression on Defect#5031 : SVS Error message not displaying on Cash Withdrawal screen | Y
5062 | 2-Medium | Third Party | Fixed | RBS SG UAT |  | RBS WAS8.5.5 fixes | Y | [5 empty] | Deploying WAS855 jar changes in 8.2 release for the backward compatibility testing by using was7. Not be impact on ET functionality. Test on login, logout and regression testing on 8.2 items.
5063 | 3-Low | NAO | Open | RBS SG PROD |  | Joint EAO successful but host reflected only one name | Y | [5 empty] | Add some loggers before calling CIF linkage service(BSD3118) in 8.2 release(Defect #5063) and get UAT signoff after tested this item in PPS UAT. No SIT signed off as SIT sign off done on 16/7.
PCR
Defect ID | PCR SEQ NO | Workstream | Status | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | Work Order | Remarks | BA | Dev
4894 | 738 | Deposit 2 | Fixed |  |  | To validate Rate Variance field for TD | Y | Y | Y |  |  | Y |  | Leila | Mani
4954 | 762 | Deposit 2 | Open |  |  | “Swaziland” is to be updated to “Kingdom of eSwatini” | Y | Y |  |  |  | Y |  | Leila | Ramesh
4986 | 783 | Common | Fixed |  |  | To remove “B0 CNH YES - DUAL CCY” from RBS. | Y | Y |  |  |  | Y |  | Leila | Mani

## R8.2.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev
Technical Defect | 5067 | 4-Cosmetic | Common | Open |  |  | NA | NA | WAS 8.5.5 Upgrade

## R8.3 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev
PCR | 4997/786 | 4-Cosmetics | NAO | Open | RBS SG PROD |  | Y | Signed off | Enhancement to Due to Revision in AML/CFT for Branches | Y | [5 empty] | Y |  | Leila | Kim
PCR (MSS Cost) | 5059/810 | 4-Cosmetics | NAO | Open | RBS SG PROD |  | N | Signed off | Update of RBS forms | Y | [5 empty] | Y-MSS |  | Leila | Kim
PCR (MSS Cost) | 5075/816 | 4-Cosmetics | NAO | Open | RBS SG PROD |  | N | updated in FSD of PCR 786 | KYC - Estimated annual income to be single selection | Y | [5 empty] | Y-MSS |  | Leila | Kim
Defect | 4938 | 3-Low | Common | Open | RBS SG UAT |  |  |  | RBS ATM Card No. Validation | Y | [8 empty] | Mani
Defect | 5027 | 3-Low | Common | Open | RBS SG SIT |  |  |  | No SO prompted for Manual Posting | Y | [8 empty] | Mani
Defect | 5028 | 3-Low | Remittance | Open | RBS SG SIT |  |  |  | To update the sequence of the iLog document |  |  | Y | [6 empty] | Mani
Defect | 5044 | 3-Low | TAM | Open | RBS SG SIT |  |  |  | Parameter Maintenance – Popup message appear during exit that there is an unsaved change when no change has been made | Y | [8 empty] | Mani
Defect | 5057 | 3-Low | Deposit 2 | Open | RBS SG PROD |  |  |  | Prod - Cheque withdrawal - toggle to backend msg does not appear in the msg box | Y | [8 empty] | Mani
Defect | 5061 | 4-Cosmetics | NAO | Open | RBS SG SIT |  |  |  | NAO and EAO Application form discrepancy | Y | [8 empty] | Mani
Defect | 5071 | 3-Low | NAO | Open | RBS SG PROD |  |  |  | Account creation - account type is not getting refresh/reset | Y | [8 empty] | Mani
Defect | 5073 | 4-Cosmetics | Common | Open | RBS SG UAT |  |  |  | World Check One API - Enable support for TLS 1.2 protocol | Y | [8 empty] | Mani

## R8.3.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev
Defect | 5084 | 2-Medium | Remittance | Fixed |  |  |  | NA | Trancode 7630 Inward TT - Dealer and Contract Ref No | Y | [5 empty] | Y |  |  | Ramesh

## R8.3.2 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev
PCR | 5066/812 | 4-Cosmetic | Remittance | Fixed |  |  |  | NA | Map Remittance Group # to TLBPNM |  |  |  | Y |  |  | Y |  | N/A | N/A
PCR | 5085/820 | 4-Cosmetic | Remittance | Open |  |  |  | NA | Map Remittance Group # to TLBPNM (0620) |  |  |  | Y |  |  | Y |  | N/A | N/A

## R8.4 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev
PCR | 4996/785 | 4-Cosmetics | Deposit 2 | Fixed |  |  | Y | Signed off | Enhancement for Better Managing of Time Deposit Promotion (Enhancement 2 : Account Closure) | Y |  |  | Y |  |  | Y |  | Ida | Mani/Kim
PCR | 5080/817 | 4-Cosmetics | NAO | Fixed |  |  |  | Signed off | KYC - Expected Transaction Activities & Estimated Annual Income to be converted to dropdown list | Y | [5 empty] | Y |  | Leila | Kim
PCR | 5106/827 | 4-Cosmetics | Deposit 2 | Fixed |  |  |  | Signed off | Amend default GL for TD Closure by GL to 165 030. | Y | [5 empty] | Y |  | Ida | Mani
Defect | 5064 | 3-Low | Deposit 2 | Fixed |  |  |  |  | DP2 Amount is not refreshed to 0 after toggling the accont number from FCCA to CA or vice versa | Y | [8 empty] | Mani
Defect | 5070 | 3-Low | Branch Operation | Fixed |  |  |  |  | Prod - TAU Notes Exchange (when requested amt and loaded amt difference is equal to 2SGD) | Y | [8 empty] | Mani
Defect | 5076 | 3-Low | NAO | Fixed |  |  |  |  | NAO & EAO: Screen is not refreshing for joint holder's KYC for Bank & Country list boxes. | Y | [8 empty] | Kim

## R8.4.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev
PCR | 5081/818 | 4-Cosmetics | Deposit 2 | Fixed |  |  |  | Signed off | Increase/reinstate Teller limit for CNY 2020 New Notes Exchange |  | Y | Y |  |  |  | Y |  | Ida | Kim
PCR | 5105/826 | 4-Cosmetics | Deposit 2 | New |  |  |  |  | Incorrect sequence of printing | Y | [5 empty] | Y |  | Ida | Mani
Defect-Prod | 5113 | 3-Low | Reports | Open |  |  |  |  | Prod - CO Issuance Report | Y | [7 empty] | Ida | Mani

## R8.4.2 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev
PCR | 5082/819 | 4-Cosmetics | Deposit 2 | Fixed |  |  |  |  | Reinstate Teller limit for CNY 2020 New Notes Exchange |  | Y | Y |  |  |  | Y |  | Ida | Mani
Defect | 5112 | 4-Cosmetics | NAO | Fixed |  |  |  |  | NAO services screen - Link Account with Services label displaying in red color | Y | [8 empty] | Kim
Defect | 5122 | 3-Medium | Deposit 2 | Fixed |  |  |  |  | SA acct closure did not prompt for passbook printing | Y

## R9.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
PCR | 5065/811 | 4-Cosmetic | NAO | Open |  |  |  | Signed off | Increase UT account opening at RBS to cater for up to 4 account holders | Y |  |  | Y | Y |  | Y | UTMS | Leila | Ramesh | 4/2-4/3 | Sprint 1
PCR | 5055/807 | 4-Cosmetic | NAO | Open |  |  |  | Signed off | Update RSA-i form | Y | [5 empty] | Y |  | Leila | Roziyah | 4/2-4/3 | Sprint 1
PCR | 5086/821 | 4-Cosmetic | Deposit2 | Open |  |  |  | Signed off | TD Advice Enhancement (DEP2) | Y | [5 empty] | Y |  | Leila | Roziyah | 4/2-4/3 | Sprint 1
PCR | 5052/806 | 4-Cosmetic | Deposit3 | Open |  |  |  | Signed off | Add Hold UV to add Effective Date and Expiry Date | Y | [5 empty] | Y |  | Leila | Roziyah | 4/2-4/3 | Sprint 1
Defect-Prod | 5079 | 3-Low | NAO | Open |  |  |  |  | Joint Acc Opening Form - Main applicant and joint applicant names are swap | Y | [7 empty] | Leila |  | 4/2-4/3 | Sprint 1
PCR | 5068/813 | 4-Cosmetic | Deposit 2 | Open |  |  |  |  | Removal of Far Eastern Bank from all dropdown | Y | Y |  |  |  |  | Y |  | Leila | Roziyah | 12/2-4/3 | Sprint 2 | 2020-03-08
PCR | 4837/741 | 3-Low | Third Party | Open |  |  |  | Signed off | Temporary removal of house cheque option in RBS restricted to Unit Trust Subscription | Y | [5 empty] | Y |  | Ida | Nitesh | 12/2-4/3 | Sprint 2 | 2020-03-08
PCR | 5089/822 | 3-Low | Financing | Open |  |  |  | Signed off | Change description of Charge Type 45 from "Admin Fees Storage" to "Admin Fees" in RBS | Y | Y |  |  |  |  | Y |  | Ida | Nitesh | 12/2-4/3 | Sprint 2
Defect-SIT | 5087 | 3-Low | Remittance | Open |  |  |  |  | Remittance MEPS payment mode: Unable to removed CIF no. entered | Y | [7 empty] | Ida | Roziyah | 12/2-4/3 | Sprint 2
Defect-SIT | 5088 | 3-Low | Remittance | Open |  |  |  |  | Remittance MEPS payment mode 'IC No.' and 'Applicant Name' field is enabled and editable for existing customer | Y | [7 empty] | Ida | Roziyah | 12/2-4/3 | Sprint 2
Defect-Prod | 5120 | 3-Low | Financing | Open |  |  |  |  | “No Doc available for reprint”. Manual Split Repayment - Transfer | Y | [7 empty] | Ida | Nitesh | 12/2-4/3 | Sprint 2
Defect-Prod | 5119 | 3-Low | Financing | Open |  |  |  |  | The printout reflect a “reprint” when it’s only the 1st printout. Repayment – Settlement, Adjustment Maintenance – Debit Principal | Y | [7 empty] | Ida | Nitesh | 12/2-4/3 | Sprint 2
Defect-Prod | 5118 | 2-Medium | Remittance | Open |  |  |  |  | EJ reflected incorrect "Total Amount" and "Total Amount to Credit" – Inward FCY | Y | [7 empty] | Ida | Nitesh | 12/2-4/3 | Sprint 2
Defect-UAT | 5124 | 3-Low | NAO | Open |  |  |  |  | Non-Individual Islamic TD Advice printing alignment issue | Y | [7 empty] | Leila | Roziyah | 12/2-4/3 | Sprint 2

## R9.2 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
PCR | 829 /5126 | 4-Cosmetics | Common | Open |  |  |  | N/A | Disabling of Paste Function in RBS | Y | [5 empty] | Y |  | Ida | Nitesh | 23/3-1/4 | Sprint 3
PCR | 685/4688 | 4-Cosmetics | Common | Fixed |  |  |  | Signed off | PDC Issuance Embossed Name | Y | [5 empty] | Y |  | Leila | Rozi | 23/3-1/4 | Sprint 3

## R9.3 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
Defect | 5099 | 3-Low | Deposit 2 | Fixed |  |  |  |  | TD Closure with single payment mode - "Account Holder's Signature" not in correct alignment in UV printing | Y | [8 empty] | Rozi | Drop 1 | Sprint 3 (Megatron)
Defect | 5102 | 3-Low | Deposit 2 | Fixed |  |  |  |  | TD Closure with fund transfer payment mode > Amount not printed in Reversal UV | Y | [8 empty] | Rozi | Drop 1 | Sprint 3 (Megatron)
Defect | 5103 | 3-Low | Deposit 2 | Fixed |  |  |  |  | TD Closure with REM CO payment mode and Surpress Name = Yes > printing Payee IC No. in CO form | Y | [8 empty] | Rozi | Drop 1 | Sprint 3 (Megatron)
Defect | 5127 | 4-Cosmetics | Deposit 2 | Fixed |  |  |  |  | iLog Baseline BL003 - duplicate issue |  |  | Y | [6 empty] | Rozi | Drop 1 | Sprint 3 (Megatron)
Defect | 5128 | 3-Low | Financing | Fixed |  |  |  |  | Financing payment screen - Bank Name is not listed together in Bank Code dropdown list. | Y | [8 empty] | Rozi | Drop 1 | Sprint 3 (Megatron)
Defect | 5129 | 4-Cosmetics | Financing | Fixed |  |  |  |  | FIN transactions - rbs screen vs doc specs discrepancy | Y | [8 empty] | Nitesh | Drop 1 | Sprint 3 (Megatron)
Defect | 5130 | 4-Cosmetics | Third Party | Fixed |  |  |  |  | UT Subscription - Include validation msg when debiting account is FCCA | Y | [8 empty] | Nitesh | Drop 1 | Sprint 3 (Megatron)
Defect | 5132 | 3-Low | Remittance | Fixed |  |  |  |  | Regional Link Deposit - IC No. and Applicant Name field behaviour | Y | [8 empty] | Ramesh | Drop 1 | Sprint 3 (Megatron)
Defect-Prod | 5123 | 3-Low | Deposit 2 | Fixed |  |  |  |  | Acctid field have dropdown text "Please select" | Y | [8 empty] | Ramesh | Drop 1 | Sprint 3 (Megatron)
PCR | 4867/724 | 4-Cosmetic | Deposit 2 | Fixed |  |  |  | Sign off | AML Req: Input source of funds/purpose of withdrawal on Deposit and Encashment Transactions (Part 1) | Y | [5 empty] | Y |  | Ida | Ramesh | Drop 2 | Sprint 4 (Arcee) Sprint 5 (Mixmaster) - printing
PCR | 5140/835 | 4-Cosmetic | Deposit 2 | Fixed |  |  |  | Sign off | New addition to the remittance and DP2 UV | Y | [5 empty] | Y |  | Ida | Ramesh | Drop 3 | Sprint 5 (Mixmaster)
PCR | 4983/781 | 4-Cosmetic | Deposit 2 | Fixed |  |  |  | Sign off | Premature TD require SO | Y (+OBIEE) | [5 empty] | Y | OBIEE | Leila | Ramesh | Drop 3 Drop 4 | Sprint 5 (Mixmaster) Sprint 6 (Jetfire)
Defect-Prod | 5144 |  | Deposit 3 | Fixed |  |  |  |  | Dicrepancy-charges debited from correct acc but UV printed different account | Y | [7 empty] | Leila | Rozi | Drop 4 | Sprint 6 (Jetfire)
PCR | 5150/840 | 4-Cosmetic | Deposit 2 | Fixed |  |  |  | Updated in PCR 781 | Premature TD - Get eff date value based on last renewal date | Y | [6 empty] | OBIEE | Leila | Ramesh | Drop 5 | Sprint 7 (Jolt)
Note on J12: no HPQC access. Actual desc as per hpqc - to be updated later

## R9.4 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
PCR | 830/5133 | 4-Cosmetic | Common | Open |  |  |  | Signed-off | Updated Disclaimer Clause for Non-Electronic Information | Y | Y |  |  |  |  | Y |  | Leila |  | Drop 1 | Sprint 1 (Jetfire)
PCR | 834/5138 | 4-Cosmetics | NAO | Open |  |  |  | Signed-off | Enhancement for NAO / EAO / MAO to map ‘Embossed Name’ to be printed in account opening form | Y | [5 empty] | Y |  | Leila |  | Drop 1 | Sprint 1 (Jetfire)
Defect | 5092 |  | Deposit 2 | Open |  |  |  |  | TD Closure Reversal UV Printing does not contain word "REV" in UV and printing incorrect Remt Inst | Y | [7 empty] | Ida |  | Drop 1 | Sprint 1 (Jetfire)
Defect | 5093 |  | Deposit 2 | Open |  |  |  |  | No labelling for UV Reprint TD Closure with Fund Transfer payment mode | Y | [7 empty] | Ida |  | Drop 1 | Sprint 1 (Jetfire)
Defect | 5094 |  | Deposit 2 | Open |  |  |  |  | No labelling for UV Reversal TD closure with Remittance MEPS payment mode | Y | [7 empty] | Ida |  | Drop 1 | Sprint 1 (Jetfire)
Defect | 5095 |  | Deposit 2 | Open |  |  |  |  | TD Closure Screen toggling TD & FCTD > Asterisk symbol (*) alignment issue in TD Closure Screen after navigating from FCTD | Y | [7 empty] | Ida |  | Drop 1 | Sprint 1 (Jetfire)
Defect | 5109 |  | Deposit 2 | Open |  |  |  |  | Reversal of FCTD closure via single payment mode - Transfer using multiple payment mode screen. Reversal UV printing error | Y | [7 empty] | Ida |  | Drop 1 | Sprint 1 (Jetfire)
Defect | 5137 | Pending update - unable to access HPQC | Financing | Open |  |  |  |  | To expand the field length of Bank Name for FIN payment screens | Y | [7 empty] | Leila |  | Drop 1 | Sprint 1 (Jetfire)
Defect | 5139 | Pending update - unable to access HPQC | Financing | Open |  |  |  |  | Charge codes in RBS vs Host |  | Y | [6 empty] | Ida |  | Drop 1 | Sprint 1 (Jetfire)
PCR | 815/5074 | 3-Low | Deposit | Open |  |  |  | Signed-off | RBS Offline Mode | Y | [5 empty] | Y |  | Ida |  | Drop 2 | Sprint 2 (Jolt)
PCR | 833/5136 | 833 | NAO | Open |  |  |  | Signed-off | Declaration form for FCTD Account Opening - Change RBS form to follow the intranet design | Y | [5 empty] | Y |  | Ida |  | Drop 2 | Sprint 2 (Jolt)
PCR | 836/5141 | 836 | TAM | Open |  |  |  | Signed-off | TAM validation when user inputted teller ID less than 4digits | Y | [5 empty] | Y |  | Ida |  | Drop 2 | Sprint 2 (Jolt)
Defect | 5097 |  | Remittance | Open |  |  |  |  | REM ODM Defects | Y |  | Y | [5 empty] | Ida |  | Drop 2 | Sprint 2 (Jolt)
Defect | 5100 |  | Third Party | Open |  |  |  |  | TPY ODM Defects | Y |  | Y | [5 empty] | Ida |  | Drop 2 | Sprint 2 (Jolt)
Defect | 5107 |  | Deposit 2 | Open |  |  |  |  | TD Closure with Cash, Transfer and Remittance TT payment mode > Special Rate & Contract Rate overlapped in REM form | Y | [7 empty] | Ida |  | Drop 2 | Sprint 2 (Jolt)
Defect | 5142 |  | Remittance | Open |  |  |  |  | REM - FDD & CO UV printing (PCR# 835) | Y | [7 empty] | Ida |  | Drop 2 | Sprint 2 (Jolt)
Defect | 5148 |  | Deposit 2 | Open |  |  |  |  | Forward and reversal UV printing issues for FCTD Closure Cross Currency and FCTD Closure to SGD currency with Fund Transfer payment mode. | Y | [7 empty] | Ida |  | Drop 2 | Sprint 2 (Jolt)
Defect | 5149 |  | Deposit 2 | Open |  |  |  |  | Spelling mistakes at the EJ Details screen for FCTD Closure Cross currency screen | Y | [7 empty] | Ida |  | Drop 2 | Sprint 2 (Jolt)

## R9.4.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev
PCR | 849/5161/SGRBS-51 |  | NAO | Fixed |  |  |  | Signed off | Committed Amount Entry for Product Islamic Product Code BF | Y | Y |  |  |  |  | Y |  | Ida | Rozi

## R9.5 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
PCR | 845/5155/SGRBS-47 |  | Deposit 2 | Fixed |  |  |  | Signed off | Add new Collection Account under Payment drop down list for Etiqa | Y | Y |  |  |  |  | Y |  | Ida | Rozi | Drop 1 | Optimus Prime
PCR | 847/5157/SGRBS-49 |  | Deposit 2 | Fixed |  |  |  | Signed off | Add new Collection Account under Payment drop down list for Etiqa 2 | Y | Y |  |  |  |  | Y |  | Ida | Rozi | Drop 1 | Optimus Prime
Defect | 5147/SBRBS-44 |  | Deposit 2 | Fixed |  |  |  |  | DP2 > Account Closure > Got additional comma & spaces in between the SO message | Y |  | Y | [5 empty] | Ida | Rozi | Drop 1 | Optimus Prime
Defect | 5158/SGRBS-50 |  | Deposit 2 | Fixed |  |  |  |  | Title discrepancy for Etiqa UV printing | Y | [7 empty] | Ida | Rozi | Drop 1 | Optimus Prime
PCR | 841/5151/SGRBS-45 |  | Reports | Fixed |  |  |  | Signed off | RBS List of Unclosed Drawers report | Y | [5 empty] | Y |  | Ida | Rozi | Drop 2 | Nitro Zeus
PCR | 842/5152/SGRBS-46 |  | Reports | Fixed |  |  |  | Signed off | Teller/Branch Total Signature boxes | Y | [5 empty] | Y |  | Ida | Rozi | Drop 2 | Nitro Zeus
PCR | 846/5156/SGRBS-48 |  | Remittance | Fixed |  |  |  | Signed off | New Clause to be printed on demand draft in INR | Y | [5 empty] | Y |  | Ida | Rozi | Drop 2 | Nitro Zeus
PCR | 852/5165/SGRBS-195 |  | NAO | Fixed |  |  |  | Signed off | To add "S2" Product Code | Y | Y |  |  |  |  | Y |  | Ida | Rozi | Drop 3 | Nautica

## R10.0.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
PCR | PCR860/SGRBS-208 |  | Deposit 2 | Fixed |  |  |  | Signed off | CNY Teller Limit Changes from $2K to $20K |  | Y | Y |  |  |  | Y |  | Ida | Rozi |  | Jirachi
Defect | SGRBS-210 |  | Deposit 2 | Fixed |  |  |  |  | Remove the following 2 duplicates collection accounts in RBS. 1. GI Collection – 04011005814 (Existing Etiqa General Insurance) 2. Life Par Policy – 04011519914 (Existing Etiqa Life Insurance) | Y | Y | [6 empty] | Ida | Rozi |  | Jirachi

## R10.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
PCR | 832/5135-SGRBS-184 |  | Deposit 2 | Fixed |  |  |  | Signed off | DCI Islamic Product | Y | Y |  |  |  |  | Y |  | Ida | Rozi | R10.1 - Drop 1,2 | Nautica 5/11-2/12 Devastator 3/12-30/12
PCR | 851/5164/SGRBS-194 |  | Deposit 2 | Fixed |  |  |  |  | Removal of Bank Code |  | Y |  |  |  |  | Y |  | Ida | Rozi | R10.1 - Drop 2 | Devastator 3/12-30/12
Defect | 5173/SGRBS-203 |  | Deposit 2 | Fixed |  |  |  |  | Multiple deposit with SOF – Amount not printed in UV | Y | [7 empty] | Ida | Rozi | R10.1 - Drop 2 | Devastator 3/12-30/12

## R10.1.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
PCR | PCR861/SGRBS-209 |  | Deposit 2 | Fixed |  |  |  | Signed off | CNY Teller Limit Changes from $20K to $2K |  | Y | Y |  |  |  | Y |  | Ida | Rozi |  | Jirachi
PCR | PCR863/SGRBS-215 |  | Deposit 2 | Fixed |  |  |  | Signed off | To remove bank code 9186 ICICI Bank from RBS dropdown |  | Y |  |  |  |  | Y |  | Ida | Rozi |  | Flareon

## R10.2 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline
Defect | SGRBS-213 |  | Deposit 2 | [5 empty] | Multiple TDA Creation & Placement > Unable to perform for 2nd TDA Creation | Y | [7 empty] | Ida | Rozi | 25/2-9/4
Defect | 5170/SGRBS-200 |  | NAO | [5 empty] | No max limit validation for Commitment Amount field | Y | [7 empty] | Ida | Rozi | 25/2-9/4
Defect | 5162/SGRBS-192 |  | Remittance | [5 empty] | CO reissuance - IC no, is printed when suppress name is Y | Y | [7 empty] | Ida | Rozi | 25/2-9/4
PCR | 858/SGRBS-205 |  | BOF |  |  |  |  | Sign off | Simplified EOD for Branch Cash Position Summary | Y | [5 empty] | Y |  | Ida | Rozi | 16/3-9/4
PCR | 859/SGRBS-206 |  | BOF |  |  |  |  | Sign off | Simplified EOD for Teller and Branch Total | Y | [5 empty] | Y |  | Ida | Rozi | 25/3-9/4 | if POC result is accepted by SG
PCR | 857/SGRBS-204 |  | NAO |  |  |  |  | Sign off | Enhancement to print signed copy of Account Opening form | Y | [5 empty] | Y |  | Ida | Rozi | 30/3-9/4

## R10.3 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline
PCR | PCR873/SGRBS-227 | [6 empty] | signed off | To update WC1 URL in RBS | Y | [5 empty] | Y |  | Ida | Aida
PCR | PCR874/SBRBS-231 | [6 empty] | N/A | To update WC1 API URL and IP Addresses | Y | [5 empty] | Y |  | N/A | Aida
PCR | PCR871/SGRBS-224 | [6 empty] | signed off | To include a new GL "11-1020 Inward MEPS" in Placement Screen |  | Y |  |  |  |  | Y |  | Ida | Rozi

## R10.4 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
PCR | SGRBS-214/PCR862 | [6 empty] | Signed off | Validation for FCTD Closure | Y | [5 empty] | Y |  | Ida | Aida | Drop 1
PCR | SGRBS-216/PCR864 | [6 empty] | Signed off | Validation for FCTD Placement | Y | [5 empty] | Y |  | Ida | Aida | Drop 1
PCR | SGRBS-225/PCR872 | [6 empty] | Signed off | To Remove Country "99 UNKNOWN" from Country dropdown |  | Y |  |  |  |  | Y |  | Ida | Aida | Drop 2
PCR | SGRBS-237/PCR878 | [6 empty] | Signed off | To remove old iSAVvy TD products from RBS |  | Y |  |  |  |  | Y |  | Ida | Aida | Drop 2
PCR | SGRBS-254/PCR890 | [6 empty] | Signed off | To remove FCTD Placement via Fund Transfer from FC (Without Nostro) placement mode | Y | [5 empty] | Y |  | Ida | Aida | Drop 2

## R10.5 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint | sprint
PCR | SGRBS-252/PCR888 | [6 empty] | Signed off | Cheque Returned Charges | Y | Y |  |  |  |  | Y |  | Ida | Aida | Drop 2 |  | jangmo-o
PCR | SGRBS-246/PCR882 | [6 empty] | Signed off | Population of Account Details when Overriding Writing of Passbook Magnetic Stripe | Y | [5 empty] | Y |  | Ida | Suriati | Drop 2 |  | jangmo-o/arbok
PCR | SGRBS-248/PCR883 | [6 empty] | Signed off | Update of Bank Code (May 2021) | Y | Y |  |  |  |  | Y |  | Ida | Aida | Drop 2 |  | arbok
Defect | SGRBS-258 | [7 empty] | Unable to perform reversal for DP3 Request Cheque Book transaction | Y | [7 empty] | Ida | Aida | Drop 2 |  | arbok
Defect | SGRBS-260 | [7 empty] | Fund Transfer show double entry in EJ for reversal with HSO | Y | [7 empty] | Ida | Aida | Drop 2 |  | arbok

## R10.6 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint | Sprint
PCR | SGRBS-222/PCR870 | [6 empty] | signed off | GL for AFO Unit |  | Y |  |  |  |  | Y |  | Ida | Aida |  | Sharpedo
Defect | SGRBS-239 | [7 empty] | Branch Cash Position Summary’s Total at the bottom is not showing all currencies with holdings and is only showing 1 currency (Issue raised during PIV) | Y | [7 empty] | Ida | Aida |  | Sharpedo, Oshawott
Defect | SGRBS-236 | [7 empty] | PCR 858 > BOP > Branch & Staff Id labels are misaligned in 1st page when the report printed in multiple pages | Y | [7 empty] | Ida | Aida |  | Oshawott
PCR | SGRBS-268/PCR897 | [6 empty] | signed off | To add GL code 919110 under GL5enum in DB via script for Back Office |  | Y |  |  |  |  | Y |  | Ida | Aida |  | Oshawott
Defect | SGRBS-269 | [7 empty] | To capture activation/deactivation of user id and reflecting maintenance performed by which userid | Y | [7 empty] | Ida | Aida |  | Oshawott

## R11.0.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint | Sprint
PCR | SGRBS-274/PCR902 | [7 empty] | Teller limit change from S$2000 to S$20,000 |  | Y | Y |  |  |  | Y |  | Ida | Aida |  | Dragonite
PCR | SGRBS-273/PCR901 | [7 empty] | To update RBS Account Opening Form to be in sync with intranet copy | Y | [7 empty] | Ida | Aida |  | Nidoking

## R11.0.2 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint | Sprint
PCR | SGRBS-275/PCR903 | [7 empty] | Reinstate Teller limit change from $20,000 to S$2000 |  | Y | Y |  |  |  | Y |  | Ida | Aida

## R11.0.1.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint | Sprint
Defect | SGRBS-294 | [7 empty] | The signature part in the account opening form is out of alignment | Y | [8 empty] | Aida

## R11.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | SGRBS-253/PCR889 | [7 empty] | Removal of DD issuance/reissuance function on RBS | Y | [5 empty] | Y |  | Ida | Aida |  | Oshawott
PCR | SGRBS-238/PCR879 | [7 empty] | Reviewing transaction code used/mapped for Loan Repayment function for P8 accounts. | Y | [5 empty] | Y |  | Ida | Aida |  | Nidoking
Defect | SGRBS-226 | [7 empty] | Branch reported a production defect whereby Twelve is spelt incorrectly as Tweleve instead. This error resulted in a bank’s cheque being returned | Y | [5 empty] | N |  |  | Aida |  | Nidoking
Defect | SGRBS-267 | [7 empty] | • As per BWCIF, customer’s mobile number was updated to 96547206 on 1/6/2021 @ 14:07PM. • However, at 1/6/2021 14:16PM, when the attached Online Account Opening Form was generated, customer’s Mobile Number is reflected as 91075542 on the form. • RBS db logs suggest all inquiries after 14:07PM returned 96547206 Please help to check why the acct opening form still printed the old number | Y | [5 empty] | N |  |  | Aida |  | Nidoking
Defect | SGRBS-277 | [7 empty] | EJ failed and no message displayed in the message box | Y | [5 empty] | N |  |  | Aida |  | Nidoking
Defect | SGRBS-278 | [7 empty] | EJ Failed and error message displayed after modified 2nd CIF's HP Number | Y | [5 empty] | N |  |  | Aida |  | Nidoking
PCR | SGRBS-264/PCR896 | [7 empty] | Dormant Reactivation Report | Y | [5 empty] | Y |  | Ida | Aida |  | Dragonite
Defect | SGRBS-279 | [7 empty] | Upon Credit Card num tab-out system is exiting to home screen and showing error at message box area | Y | [5 empty] | Y |  | Ida | Aida |  | Dragonite
Retrofit PCRs
Item Category | Defect ID / PCR | Release Number | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE
PCR | SGRBS-273/PCR901 | 11.0.1 | [7 empty] | Y

## R11.1.1 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
Retrofit PCRs
Item Category | Defect ID / PCR | Release Number | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE

## R11.2 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | UAT timeline | Sprint
PCR | SGRBS-219/PCR867 | [7 empty] | Card ISO 8 Digit BIN Compliance | Y |  |  |  | Y |  | Y |  | Ida
Retrofit PCRs
Item Category | Defect ID / PCR | Release Number | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE
PCR | SGRBS-273/PCR901 | 11.0.1 | [7 empty] | Y
PCR | SGRBS-253/PCR889 | 11.1 | [7 empty] | Y
PCR | SGRBS-238/PCR879 | 11.1 | [7 empty] | Y
PCR | SGRBS-264/PCR896 | 11.1
Retrofit Defects
Item Category | Defect ID / PCR | Release Number | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE
Defect | SGRBS-226 | 11.1 | [7 empty] | Y
Defect | SGRBS-267 | 11.1 | [7 empty] | Y
Defect | SGRBS-277 | 11.1 | [7 empty] | Y
Defect | SGRBS-278 | 11.1 | [7 empty] | Y
Defect | SGRBS-279 | 11.1
Defect | SGRBS-294 | 11.0.1.1 | [7 empty] | Y

## R11.3 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR898 |  |  | Open |  |  |  |  | "Self" dial on CO application | Y | [5 empty] | Y |  | Ida | Nuraida
PCR | PCR907 |  |  | Open |  |  |  |  | RBS - Apache Log4j | Y | [5 empty] | Y |  | Ida | Ramesh
PCR | PCR909 |  |  | Open |  |  |  |  | RBS Enhancements on PIN Issuance form Printing | Y | [5 empty] | Y |  | Ida | Nuraida
PCR | PCR915 |  |  | Open |  |  |  |  | RBS Enhancement ATM Card Replacement with Pin Issuance Button | Y | [5 empty] | Y |  | Ida | Nuraida
PCR | PCR899 |  |  | Open |  |  |  |  | To build a reconciliation report (query) to compare the total number of ids extracted to be interfaced to IMA against the Host record. | Y | [5 empty] | Y |  | Ida | Ramesh
Defect | SGRBS-306 |  |  | Open |  |  |  |  | Account closure with incorrect amount printed on UV vocher | Y | [7 empty] | Ida | Nuraida
Defect | SGRBS-308 |  |  | Open |  |  |  |  | RBS- Account Inquiry | Y | [7 empty] | Ida | Nuraida
PCR | PCR788 |  |  | Open |  |  |  |  | Ilog Mirgration (Dp2 ,DP3) - 255 Rules | N | Y |  |  |  |  | N |  | Ida | Ramesh
Retrofit Defects (SIT ONLY)
Item Category | Defect ID / PCR | Release Number | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE
PCR | SGRBS-219/PCR867 | 11.2 | [7 empty] | Y | Y

## R11.4 (hidden)
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR904 |  |  | Open |  |  |  |  | SSIC v2020 Migration | Y | Y |  |  | Y |  | Y |  | Ida | Nuraida
PCR | PCR788 |  |  | Open |  |  |  |  | Ilog Mirgration (NAO, REM) - 238 Rules | N | Y |  |  |  |  | N |  | Ida
Retrofit PCRs (SIT ONLY)
Item Category | Defect ID / PCR | Release Number | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE
PCR | SGRBS-219/PCR867 | 11.2 | [7 empty] | Y | Y
PCR | PCR898 | 11.3 | [7 empty] | Y
PCR | PCR907 | 11.3 | [7 empty] | Y
PCR | PCR909 | 11.3 | [7 empty] | Y
PCR | PCR899 | 11.3 | [7 empty] | Y
Retrofit Defects(SIT ONLY)
Item Category | Defect ID / PCR | Release Number | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE
Defect | SGRBS-306 | 11.3 | [7 empty] | Y
Defect | SGRBS-308 | 11.3 | [7 empty] | Y

## R11.5
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR920 |  |  | Open |  |  |  |  | PCR 920 WO- To include 4-digit Teller ID in the Excel report generated for UA | Y | [5 empty] | Y |  | Ida | Ramesh
PCR | PCR927 |  |  | Open |  |  |  |  | To include liner under existing e-channels form under agreement section | Y | [5 empty] | Y |  | Zul | Aida
Defect | SG RBS -290 |  |  | Open |  |  |  |  | System exits to home screen for Cash Withdrawal with Balance Transfer Card | Y | [7 empty] | Ida | Aida
Defect | SG RBS -259 |  |  | Open |  |  |  |  | Forward transaction without HSO and Reversal with HSO | Y | Y | [6 empty] | Ida | Aida
Defect | SG RBS -201 |  |  | Open |  |  |  |  | HSO approval for last debit leg transaction | Y | Y |  | Y |  |  |  |  | Ida | Aida
Defect | SG RBS -310 |  |  | Open |  |  |  |  | EJ Not Captured for Payee & Payee IC Number for TD Account Closure Single & Multiple Payment Mode | Y | [7 empty] | Ida | Aida
Defect | SG RBS -235 |  |  | Open |  |  |  |  | Newly added currency info is not showing in reports on same day | Y | [7 empty] | Ida | Aida
Defect | SG RBS -212 |  |  | Open |  |  |  |  | System exits when selecting Commision type 'Debit from Account' Commission Currency 'SGD' for Cash Withdrawal | Y | [7 empty] | Ida | Aida
PCR | PCR908 |  |  | Open |  |  |  |  | Payment Collection Account | Y | [5 empty] | Y |  | Ida | Aida
Defect | SG RBS -322 |  |  | Open |  |  |  |  | Pressing F12 indeed will auto populate the last entered value | Y | [7 empty] | Ida | Aida
Retrofit PCRs (SIT ONLY)
Item Category | Defect ID / PCR | Release Number | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE
PCR | PCR904 | 11.4 | [7 empty] | Y | Y |  |  | Y

## R11.5.1
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR930 |  |  | Open |  |  |  |  | 15 and 18 months TD Product code - RBS |  | Y |  |  | Y |  | Y |  | Ida | Nuraida

## R11.6
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR916 |  |  | Open |  |  |  |  | Goods and Services Tax (“GST”) rate change | Y | Y |  |  |  |  | Y |  | Ida | Nuraida
PCR | PCR925 |  |  | Open |  |  |  |  | To add new value in Description dropdown | Y | [5 empty] | Y |  | Ida | Nuraida
PCR | PCR928 |  |  | Open |  |  |  |  | System Enhancement - Maintenance of Account Relationship Linkage in RBS | Y | [5 empty] | Y |  | Ida | Nuraida
PCR | PCR930 |  |  | Open |  |  |  |  | Update Product description in RBS for Product Code = “QY”. |  | Y |  |  |  |  | Y |  | Ida | Nuraida
Defect | SG RBS -325 |  |  | Open |  |  |  |  | System exits when clicking on "Search Customer" button and pressing on "TAB" button at Traditional Menu | Y | [7 empty] | Ida | Nuraida
Defect | SG RBS -303 |  |  | Open |  |  |  |  | TD Products dropdown list toggle | Y | [7 empty] | Ida | Nuraida
Defect | SG RBS -326 |  |  | Open |  |  |  |  | Reversal UV for Customer Copy is printed when "Print Customer Copy" radio button = No | Y | [7 empty] | Ida | Nuraida
Defect | SG RBS -327 |  |  | Open |  |  |  |  | In Remittance, all value in Description dropdown list is not arranged in correct sequence | Y | [7 empty] | Ida | Nuraida
Defect | SG RBS -332 |  |  | Open |  |  |  |  | System is allowing to enter same CIF number for all Joint holders | Y | [7 empty] | Ida | Nuraida
Defect | SG RBS -334 |  |  | Open |  |  |  |  | Spelling error in RBS - Bussiness Date | Y | [7 empty] | Ida | Nuraida
Defect | SG RBS -336 |  |  | Open |  |  |  |  | 222 Overriding issue (Prod issue) | Y | [7 empty] | Ida | Nuraida
Defect | SG RBS -340 |  |  | Open |  |  |  |  | Description code not sending to Host when narration is empty for functions/transactions | Y | [7 empty] | Ida | Nuraida
Retrofit PCRs (SIT ONLY)
Item Category | Defect ID / PCR | Release Number | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | Host | SOE
PCR | PCR930 | 11.5.1 | [8 empty] | Y |  |  | Y

## R11.7
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | SVS | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR919 |  |  | Open |  |  |  |  | SVS Migration |  |  |  |  | Y |  |  | Y |  | Ida | Nuraida

## R12.0.1
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | SVS | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR936 |  |  | Open |  |  |  |  | Increase Teller limit for Y2023 CNY Notes Exchange |  | Y | Y |  |  |  |  | Y |  | Ida | Nuraida

## R12.0.2
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | SVS | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR937 |  |  | Open |  |  |  |  | Reinstate Teller limit for Y2023 CNY Notes Exchange |  | Y | Y |  |  |  |  | Y |  | Ida | Nuraida

## 12.1
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | SVS | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR938 |  |  | Open |  |  |  |  | To extend Perimeter for CO Payee Field | Y | [6 empty] | Y |  | Ida | Nuraida
PCR | PCR939 |  |  | Open |  |  |  |  | Dormant Status Check for Add Relationship Function | Y |  | Y |  |  |  |  | Y |  | Ida | Nuraida

## 12.1.0
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | SVS | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR944 |  | DP2 & DP3 | Open |  |  |  |  | CPF Time deposit | Y | Y |  | Y |  | Y |  | Y | TD advise alignment Product Code | Ida | Nuraida

## 12.1.1
Item Category | Defect ID / PCR | Severity | Workstream | Status | Detected in Release | Originated from Version | BRD Status | ISD Status | Summary | ET | DB | iLog | ESB | SVS | Host | SOE | Work Order | Remarks | BA | Dev | Sprint
PCR | PCR915 |  |  | Open |  |  |  |  | RBS Enhancement ATM Card Replacement with Pin Issuance Button | Y |  | Y |  |  |  |  | Y |  | Ida | Nuraida
PCR | PCR942 |  |  | Open |  |  |  |  | Request to generate RBS User Access Details Report | Y | Y | [5 empty] | Y |  | Ida | Ramesh
PCR | PCR 951 |  |  | Open |  |  |  |  | Account Closure Ilog Migration |  | Y | [7 empty] | Ida | Nuraida
Defect | SGRBS-365 |  |  | Open |  |  |  |  | Prod - RBS User Listing Report not generated while running the batch | Y | [8 empty] | Ida | Ramesh

## RBS Schedule
|  | 2015-12-01 |  |  |  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01 |  |  |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  |  | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  |  | 2016-08-01 |  |  |  | 2016-09-01 |  |  |  | 2016-10-01 |  |  |  | 2016-11-01 |  |  |  |  | 2016-12-01 |  |  |  | 2017-01-01 |  |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  |  | 2018-01-01 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  |  | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  |  | 2019-07-01 |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  | 2020-07-01 |  |  |  | Aug-20 |  |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  |  | 2021-11-01 |  |  |  | 2021-12-01 |  |  |  |  | 2022-01-01 |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  |  | 2022-05-01 |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  |  | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  |  | 2023-01-01 |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  |  | 2023-05-01 |  |  |  | 2023-06-01 |  |  |  | 2023-07-01
| Week Ends(Sun) | 2015-12-13 | 2015-12-20 | 2015-12-27 | 2016-01-03 | 2016-01-10 | 2016-01-17 | 2016-01-24 | 2016-01-31 | 2016-02-07 | 2016-02-14 | 2016-02-21 | 2016-02-28 | 2016-03-06 | 2016-03-13 | 2016-03-20 | 2016-03-27 | 2016-04-03 | 2016-04-10 | 2016-04-17 | 2016-04-24 | 2016-05-01 | 2016-05-08 | 2016-05-15 | 2016-05-22 | 2016-05-29 | 2016-06-05 | 2016-06-12 | 2016-06-19 | 2016-06-26 | 2016-07-03 | 2016-07-10 | 2016-07-17 | 2016-07-24 | 2016-07-31 | 2016-08-07 | 2016-08-14 | 2016-08-21 | 2016-08-28 | 2016-09-04 | 2016-09-11 | 2016-09-18 | 2016-09-25 | 2016-10-02 | 2016-10-09 | 2016-10-16 | 2016-10-23 | 2016-10-30 | 2016-11-06 | 2016-11-13 | 2016-11-20 | 2016-11-27 | 2016-12-04 | 2016-12-11 | 2016-12-18 | 2016-12-25 | 2017-01-01 | 2017-01-08 | 2017-01-15 | 2017-01-22 | 2017-01-29 | 2017-02-05 | 2017-02-12 | 2017-02-19 | 2017-02-26 | 2017-03-05 | 2017-03-12 | 2017-03-19 | 2017-03-26 | 2017-04-02 | 2017-04-09 | 2017-04-16 | 2017-04-23 | 2017-04-30 | 2017-05-07 | 2017-05-14 | 2017-05-21 | 2017-05-28 | 2017-06-04 | 2017-06-11 | 2017-06-18 | 2017-06-25 | 2017-07-02 | 2017-07-09 | 2017-07-16 | 2017-07-23 | 2017-07-30 | 2017-08-06 | 2017-08-13 | 2017-08-20 | 2017-08-27 | 2017-09-03 | 2017-09-10 | 2017-09-17 | 2017-09-24 | 2017-10-01 | 2017-10-08 | 2017-10-15 | 2017-10-22 | 2017-10-29 | 2017-11-05 | 2017-11-12 | 2017-11-19 | 2017-11-26 | 2017-12-03 | 2017-12-10 | 2017-12-17 | 2017-12-24 | 2017-12-31 | 2018-01-07 | 2018-01-14 | 2018-01-21 | 2018-01-28 | 2018-02-04 | 2018-02-11 | 2018-02-18 | 2018-02-25 | 2018-03-04 | 2018-03-11 | 2018-03-18 | 2018-03-25 | 2018-04-01 | 2018-04-08 | 2018-04-15 | 2018-04-22 | 2018-04-29 | 2018-05-06 | 2018-05-13 | 2018-05-20 | 2018-05-27 | 2018-06-03 | 2018-06-10 | 2018-06-17 | 2018-06-24 | 2018-07-01 | 2018-07-08 | 2018-07-15 | 2018-07-22 | 2018-07-29 | 2018-08-05 | 2018-08-12 | 2018-08-19 | 2018-08-26 | 2018-09-02 | 2018-09-09 | 2018-09-16 | 2018-09-23 | 2018-09-30 | 2018-10-07 | 2018-10-14 | 2018-10-21 | 2018-10-28 | 2018-11-04 | 2018-11-11 | 2018-11-18 | 2018-11-25 | 2018-12-02 | 2018-12-09 | 2018-12-16 | 2018-12-23 | 2018-12-30 | 2019-01-06 | 2019-01-13 | 2019-01-20 | 2019-01-27 | 2019-02-03 | 2019-02-10 | 2019-02-17 | 2019-02-24 | 2019-03-03 | 2019-03-10 | 2019-03-17 | 2019-03-24 | 2019-03-31 | 2019-04-07 | 2019-04-14 | 2019-04-21 | 2019-04-28 | 2019-05-05 | 2019-05-12 | 2019-05-19 | 2019-05-26 | 2019-06-02 | 2019-06-09 | 2019-06-16 | 2019-06-23 | 2019-06-30 | 2019-07-07 | 2019-07-14 | 2019-07-21 | 2019-07-28 | 2019-08-04 | 2019-08-11 | 2019-08-18 | 2019-08-25 | 2019-09-01 | 2019-09-08 | 2019-09-15 | 2019-09-22 | 2019-09-29 | 2019-10-06 | 2019-10-13 | 2019-10-20 | 2019-10-27 | 2019-11-03 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05 | 2020-01-12 | 2020-01-19 | 2020-01-26 | 2020-02-02 | 2020-02-09 | 2020-02-16 | 2020-02-23 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2019-03-22 | 2019-03-29 | 2019-04-05 | 2019-04-12 | 2019-04-19 | 2019-04-26 | 2019-05-03 | 2019-05-10 | 2019-05-17 | 2019-05-24 | 2019-05-31 | 2019-06-07 | 2019-06-14 | 2019-06-21 | 2019-06-28 | 2019-07-05 | 2019-07-12 | 2019-07-19 | 2019-07-26 | 2019-08-02 | 2019-08-09 | 2019-08-16 | 2019-08-23 | 2019-08-30 | 2019-09-06 | 2019-09-13 | 2019-09-20 | 2019-09-27 | 2019-10-04 | 2019-10-11 | 2019-10-18 | 2019-10-25 | 2019-11-01 | 2019-11-08 | 2019-11-15 | 2019-11-22 | 2019-11-29 | 2019-12-06 | 2019-12-13 | 2019-12-20 | 2019-12-27 | 2020-01-03 | 2020-01-10 | 2020-01-17 | 2020-01-24 | 2020-01-31 | 2020-02-07 | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27 | 2020-04-03 | 2020-04-10 | 2020-04-17 | 2020-04-24 | 2020-05-01 | 2020-05-08 | 2020-05-15 | 2020-05-22 | 2020-05-29 | 2020-06-05 | 2020-06-12 | 2020-06-19 | 2020-06-26 | 2020-07-03 | 2020-07-10 | 2020-07-17 | 2020-07-24 | 2020-07-31 | 2020-08-07 | 2020-08-14 | 2020-08-21 | 2020-08-28 | 2020-09-04 | 2020-09-11 | 2020-09-18 | 2020-09-25 | 2020-10-02 | 2020-10-09 | 2020-10-16 | 2020-10-23 | 2020-10-30 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-11-27 | 2020-12-04 | 2020-12-11 | 2020-12-18 | 2020-12-25 | 2021-01-01 | 2021-01-08 | 2021-01-15 | 2021-01-22 | 2021-01-29 | 2021-02-05 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-05 | 2021-03-12 | 2021-03-19 | 2021-03-26 | 2021-04-02 | 2021-04-09 | 2021-04-16 | 2021-04-23 | 2021-04-30 | 2021-05-07 | 2021-05-14 | 2021-05-21 | 2021-05-28 | 2021-06-04 | 2021-06-11 | 2021-06-18 | 2021-06-25 | 2021-07-02 | 2021-07-09 | 2021-07-16 | 2021-07-23 | 2021-07-30 | 2021-08-06 | 2021-08-13 | 2021-08-20 | 2021-08-27 | 2021-09-03 | 2021-09-10 | 2021-09-17 | 2021-09-24 | 2021-10-01 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 2021-10-29 | 2021-11-05 | 2021-11-12 | 2021-11-19 | 2021-11-26 | 2021-12-03 | 2021-12-10 | 2021-12-17 | 2021-12-24 | 2021-12-31 | 2022-01-07 | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-06-03 | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05
Week Starts(Mon) | time axis 2015-12-07 to 2023-07-31
Releases | Activity | 2015-12-07: W49; 2015-12-14: W50; 2015-12-21: W51; 2015-12-28: W52; 2016-01-04: W01; 2016-01-11: W02; 2016-01-18: W03; 2016-01-25: W04; 2016-02-01: W05; 2016-02-08: W06; 2016-02-15: W07; 2016-02-22: W08; 2016-02-29: W09; 2016-03-07: W10; 2016-03-14: W11; 2016-03-21: W12; 2016-03-28: W13; 2016-04-04: W14; 2016-04-11: W15; 2016-04-18: W16; 2016-04-25: W17; 2016-05-02: W18; 2016-05-09: W19; 2016-05-16: W20; 2016-05-23: W21; 2016-05-30: W22; 2016-06-06: W23; 2016-06-13: W24; 2016-06-20: W25; 2016-06-27: W26; 2016-07-04: W27; 2016-07-11: W28; 2016-07-18: W29; 2016-07-25: W30; 2016-08-01: W31; 2016-08-08: W32; 2016-08-15: W33; 2016-08-22: W34; 2016-08-29: W35; 2016-09-05: W36; 2016-09-12: W37; 2016-09-19: W38; 2016-09-26: W39; 2016-10-03: W40; 2016-10-10: W41; 2016-10-17: W42; 2016-10-24: W43; 2016-10-31: W44; 2016-11-07: W45; 2016-11-14: W46; 2016-11-21: W47; 2016-11-28: W48; 2016-12-05: W49; 2016-12-12: W50; 2016-12-19: W51; 2016-12-26: W1; 2017-01-02: W2; 2017-01-09: W3; 2017-01-16: W4; 2017-01-23: W5; 2017-01-30: W6; 2017-02-06: W7; 2017-02-13: W8; 2017-02-20: W9; 2017-02-27: W10; 2017-03-06: W11; 2017-03-13: W12; 2017-03-20: W13; 2017-03-27: W14; 2017-04-03: W15; 2017-04-10: W16; 2017-04-17: W17; 2017-04-24: W18; 2017-05-01: W19; 2017-05-08: W20; 2017-05-15: W21; 2017-05-22: W22; 2017-05-29: W23; 2017-06-05: W24; 2017-06-12: W25; 2017-06-19: W26; 2017-06-26: W27; 2017-07-03: W28; 2017-07-10: W29; 2017-07-17: W30; 2017-07-24: W31; 2017-07-31: W32; 2017-08-07: W33; 2017-08-14: W34; 2017-08-21: W35; 2017-08-28: W36; 2017-09-04: W37; 2017-09-11: W38; 2017-09-18: W39; 2017-09-25: W40; 2017-10-02: W41; 2017-10-09: W42; 2017-10-16: W43; 2017-10-23: W44; 2017-10-30: W45; 2017-11-06: W46; 2017-11-13: W47; 2017-11-20: W48; 2017-11-27: W49; 2017-12-04: W50; 2017-12-11: W51; 2017-12-18: W52; 2017-12-25: W53; 2018-01-01: W01; 2018-01-08: W02; 2018-01-15: W03; 2018-01-22: W04; 2018-01-29: W05; 2018-02-05: W06; 2018-02-12: W07; 2018-02-19: W08; 2018-02-26: W09; 2018-03-05: W10; 2018-03-12: W11; 2018-03-19: W12; 2018-03-26: W13; 2018-04-02: W14; 2018-04-09: W15; 2018-04-16: W16; 2018-04-23: W17; 2018-04-30: W18; 2018-05-07: W19; 2018-05-14: W20; 2018-05-21: W21; 2018-05-28: W22; 2018-06-04: W23; 2018-06-11: W24; 2018-06-18: W25; 2018-06-25: W26; 2018-07-02: W27; 2018-07-09: W28; 2018-07-16: W29; 2018-07-23: W30; 2018-07-30: W31; 2018-08-06: W32; 2018-08-13: W33; 2018-08-20: W34; 2018-08-27: W35; 2018-09-03: W36; 2018-09-10: W37; 2018-09-17: W38; 2018-09-24: W39; 2018-10-01: W40; 2018-10-08: W41; 2018-10-15: W42; 2018-10-22: W43; 2018-10-29: W44; 2018-11-05: W45; 2018-11-12: W46; 2018-11-19: W47; 2018-11-26: W48; 2018-12-03: W49; 2018-12-10: W50; 2018-12-17: W51; 2018-12-24: W52; 2018-12-31: W1; 2019-01-07: W2; 2019-01-14: W3; 2019-01-21: W4; 2019-01-28: W5; 2019-02-04: W6; 2019-02-11: W7; 2019-02-18: W8; 2019-02-25: W9; 2019-03-04: W10; 2019-03-11: W11; 2019-03-18: W12; 2019-03-25: W13; 2019-04-01: W14; 2019-04-08: W15; 2019-04-15: W16; 2019-04-22: W17; 2019-04-29: W18; 2019-05-06: W19; 2019-05-13: W20; 2019-05-20: W21; 2019-05-27: W22; 2019-06-03: W23; 2019-06-10: W24; 2019-06-17: W25; 2019-06-24: W26; 2019-07-01: W27; 2019-07-08: W28; 2019-07-15: W29; 2019-07-22: W30; 2019-07-29: W31; 2019-08-05: W32; 2019-08-12: W33; 2019-08-19: W34; 2019-08-26: W35; 2019-09-02: W36; 2019-09-09: W37; 2019-09-16: W38; 2019-09-23: W39; 2019-09-30: W40; 2019-10-07: W41; 2019-10-14: W42; 2019-10-21: W43; 2019-10-28: W44; 2019-11-04: W45; 2019-11-11: W46; 2019-11-18: W47; 2019-11-25: W48; 2019-12-02: W49; 2019-12-09: W50; 2019-12-16: W51; 2019-12-23: W52; 2019-12-30: W53; 2020-01-06: W1; 2020-01-13: W2; 2020-01-20: W3; 2020-01-27: W4; 2020-02-03: W5; 2020-02-10: W6; 2020-02-17: W7; 2020-02-24: W8; 2020-03-02: W9; 2020-03-09: W10; 2020-03-16: W11; 2020-03-23: W12; 2020-03-30: 13; 2020-04-06: 14; 2020-04-13: 15; 2020-04-20: 16; 2020-04-27: 17; 2020-05-04: 18; 2020-05-11: 19; 2020-05-18: 20; 2020-05-25: 21; 2020-06-01: 22; 2020-06-08: 23; 2020-06-15: 24; 2020-06-22: 25
Rel 4.1.1 Back Office Charges + Defect #4482 | Planning | 2016-02-08: CNY
Requirements | bar: 2015-12-07 to 2015-12-28; 2016-02-08
Development | bar: 2015-12-07 to 2015-12-28; 2016-02-08
System Test | bar: 2015-12-07 to 2015-12-28; 2016-02-08
Test Preparation | bar: 2015-12-07 to 2015-12-28; 2016-02-08
SIT | bar: 2015-12-07 to 2015-12-28; 2016-02-08
Chg Mgmt | bar: 2015-12-07 to 2015-12-28; 2016-02-08
Rel 4.1.2 (PCR 581-CNY Pack + PCR 628 - GBP CRS) | Planning | bar: 2015-12-07 to 2016-01-18; 2016-02-08
Requirements | bar: 2015-12-07 to 2016-01-18; 2016-02-08
Development | bar: 2015-12-07 to 2016-01-18; 2016-02-08
System Test | bar: 2015-12-07 to 2016-01-18; 2016-02-08
Test Preparation | bar: 2015-12-07 to 2016-01-18; 2016-02-08
SIT | bar: 2015-12-07 to 2016-01-18; 2016-02-08
Chg Mgmt | bar: 2015-12-07 to 2016-01-18; 2016-02-08
Rel 4.1.3 (PCR 636 - Raise Teller SO Limit) | Planning | bar: 2015-12-07 to 2016-01-25; 2016-02-08
Requirements | bar: 2015-12-07 to 2016-01-25; 2016-02-08
Development | bar: 2015-12-07 to 2016-01-25; 2016-02-08
System Test | bar: 2015-12-07 to 2016-01-25; 2016-02-08
Test Preparation | bar: 2015-12-07 to 2016-01-25; 2016-02-08
SIT | bar: 2015-12-07 to 2016-01-25; 2016-02-08
Chg Mgmt | bar: 2015-12-07 to 2016-01-25; 2016-02-08
Rel 4.2 Phase 1 Backlog Items | Planning | bar: 2015-12-07 to 2015-12-28; 2016-02-08
Development | bar: 2015-12-07 to 2015-12-28; 2016-02-08
System Test | bar: 2015-12-07 to 2015-12-28; 2016-02-08
Test Preparation | bar: 2015-12-07 to 2015-12-28; 2016-02-08
SIT | bar: 2015-12-07 to 2015-12-28; 2016-02-08
Rel 4.2 Phase 2 (Defect 4486,#4488 + PCR 637 - Reinstate Teller SO Limit) | Planning | bar: 2015-12-07 to 2016-01-25; 2016-02-08
Development | bar: 2015-12-07 to 2016-01-25; 2016-02-08
System Test | bar: 2015-12-07 to 2016-01-25; 2016-02-08
Test Preparation | bar: 2015-12-07 to 2016-01-25; 2016-02-08
SIT | bar: 2015-12-07 to 2016-01-25; 2016-02-08
Rel 4.2 Final Phase | RT | bar: 2015-12-07 to 2016-02-08
Chg Mgmt | bar: 2015-12-07 to 2016-02-08
Rel 4.2.1 (Defect 4516, 4518) | Planning | bar: 2015-12-07 to 2016-02-22
Development | bar: 2015-12-07 to 2016-02-22
System Test | bar: 2015-12-07 to 2016-02-22
Test Preparation | bar: 2015-12-07 to 2016-02-22
SIT | bar: 2015-12-07 to 2016-02-22
Chg Mgmt | bar: 2015-12-07 to 2016-02-22
Rel 5.0 (16 Defects + 1 PCR) | Requirements | bar: 2015-12-07 to 2016-06-27
Development | bar: 2015-12-07 to 2016-06-27
System Test | bar: 2015-12-07 to 2016-06-27
Test Preparation | bar: 2015-12-07 to 2016-06-27
SIT | bar: 2015-12-07 to 2016-06-27
Regression | bar: 2015-12-07 to 2016-06-27
Chg Mgmt | bar: 2015-12-07 to 2016-06-27
Rel 5.0.1 (SSW for NAO&EAO) | Development | bar: 2015-12-07 to 2016-05-16
SIT | bar: 2015-12-07 to 2016-05-16
UAT | bar: 2015-12-07 to 2016-05-16
Chg Mgmt | bar: 2015-12-07 to 2016-05-16
Rel 5.1 (3 PCR + 5 Defects) | Planning | bar: 2015-12-07 to 2016-05-23
Requirements | bar: 2015-12-07 to 2016-05-23
Development | bar: 2015-12-07 to 2016-05-23
Test Preparation | bar: 2015-12-07 to 2016-05-23
SIT | bar: 2015-12-07 to 2016-05-23
UAT | bar: 2015-12-07 to 2016-05-23
Chg Mgmt | bar: 2015-12-07 to 2016-05-23
VISA BIN | Development | bar: 2015-12-07 to 2016-07-11
System Test | bar: 2015-12-07 to 2016-07-11
Test Preparation | bar: 2015-12-07 to 2016-07-11
| SIT | 2016-01-18: VOID; 2016-02-08: S; 2016-02-15: S; 2016-02-22: S; 2016-02-29: S; 2016-03-07: S
UAT | bar: 2015-12-07 to 2016-07-11
Rel 5.2 *3PCR *14Prod Defects *3 SIT Defects | Requirements | bar: 2015-12-07 to 2016-07-11
Development | bar: 2015-12-07 to 2016-07-11
SIT | bar: 2015-12-07 to 2016-07-11
UAT | bar: 2015-12-07 to 2016-07-11
Rel 5.2.1 Emer Release | Development | bar: 2015-12-07 to 2016-08-01
SIT | bar: 2015-12-07 to 2016-07-25
UAT | bar: 2015-12-07 to 2016-07-25
Chg Mgmt | bar: 2015-12-07 to 2016-07-25
Rel 5.3 (PCR + Defects) | Requirements | bar: 2015-12-07 to 2016-08-22
Development | bar: 2015-12-07 to 2016-08-22
SIT | bar: 2015-12-07 to 2016-08-22
UAT | bar: 2015-12-07 to 2016-08-22
REL 5.4 - (PCR MAS Notice 626) | Requirements | bar: 2015-12-07 to 2017-01-16
Development | bar: 2015-12-07 to 2017-01-16
SIT | bar: 2015-12-07 to 2017-01-16
UAT | bar: 2015-12-07 to 2017-01-16
Rel 5.5 (PCR + Defect + Sonarqube Fixes) | Requirements | bar: 2016-07-11 to 2017-02-13
Development | bar: 2016-07-11 to 2017-02-13
SIT | bar: 2016-07-11 to 2017-02-13
UAT | bar: 2016-07-11 to 2017-02-13
Chg Mgmt | bar: 2016-07-11 to 2017-02-13
REL 5.3.1 (Defects #4613) | Development | bar: 2016-08-22 to 2016-12-19
SIT | bar: 2016-08-22 to 2016-12-19
UAT | bar: 2016-08-22 to 2016-12-19
REL 5.3.2 (PCR660 #4605+Defects) | Requirements | bar: 2016-08-22 to 2016-12-19
Development | bar: 2016-08-22 to 2016-12-19
SIT | bar: 2016-08-22 to 2016-12-19
UAT | bar: 2016-08-22 to 2016-12-19
REL 5.6 (PCR + Defect + Sonarqube Fixes) | Planning | bar: 2016-08-22 to 2017-02-13
Requirements | bar: 2016-08-22 to 2017-02-13
Development | bar: 2016-08-22 to 2017-02-13
Test Preparation | bar: 2016-08-22 to 2017-02-13
SIT | bar: 2016-08-22 to 2017-02-13
UAT | bar: 2016-08-22 to 2017-02-13
Chg Mgmt | bar: 2016-08-22 to 2017-02-13
Rel 5.5.1 (Defect #4655) | Requirements | bar: 2015-12-07 to 2016-05-02; 2016-08-22 to 2017-02-13
Development | bar: 2015-12-07 to 2016-05-02; 2016-08-22 to 2017-02-13
SIT | bar: 2015-12-07 to 2016-05-02; 2016-08-22 to 2017-02-13
UAT | bar: 2015-12-07 to 2016-05-02; 2016-08-22 to 2017-02-13
Chg Mgmt | bar: 2015-12-07 to 2016-05-02; 2016-08-22 to 2017-02-13
REL 5.6.1(Ilog Increase Limit) (PCR #672) | Planning | bar: 2016-08-22 to 2017-02-13
Requirements | bar: 2016-08-22 to 2017-02-13
Development | bar: 2016-08-22 to 2017-02-13
Test Preparation | bar: 2016-08-22 to 2017-02-13
SIT | bar: 2016-08-22 to 2017-02-13
UAT | bar: 2016-08-22 to 2017-02-13
Chg Mgmt | bar: 2016-08-22 to 2017-02-13
Rel 5.6.2(Ilog Reinstate) (PCR #673) | Planning | bar: 2016-08-22 to 2017-02-13
Requirements | bar: 2016-08-22 to 2017-02-13
Development | bar: 2016-08-22 to 2017-02-13
Test Preparation | bar: 2016-08-22 to 2017-02-13
SIT | bar: 2016-08-22 to 2017-02-13
UAT | bar: 2016-08-22 to 2017-02-13
Chg Mgmt | bar: 2016-08-22 to 2017-02-13
REL 6.1 (PCR+Defects) | Planning | bar: 2016-10-03 to 2017-04-17
Requirements | bar: 2016-10-03 to 2017-04-17
Development | bar: 2016-10-03 to 2017-04-17
Test Preparation | bar: 2016-10-03 to 2017-04-17
SIT | bar: 2016-10-03 to 2017-04-17
UAT | bar: 2016-10-03 to 2017-04-17
Chg Mgmt | bar: 2016-10-03 to 2017-04-17
REL 6.1.1 (PCR) | Planning | bar: 2016-11-28 to 2017-06-19
Requirements | bar: 2016-11-28 to 2017-06-19
Development | bar: 2016-11-28 to 2017-06-19
Test Preparation | bar: 2016-11-28 to 2017-06-19
SIT | bar: 2016-11-28 to 2017-06-19
UAT | bar: 2016-11-28 to 2017-06-19
Chg Mgmt | bar: 2016-11-28 to 2017-06-19
Rel 6.1.2 (PCR & Defect) | Development | 2017-05-08: D; 2017-05-15: 8/5 - 12/5
| Test Preparation | 2017-05-08: TP; 2017-05-15: 12/5
| SIT | 2017-05-08: S; 2017-05-15: 12/5 - 16/5 (SIT sign off 16/5)
| UAT | 2017-05-08: U; 2017-05-15: 12/5 - 16/5 (UAT sign off 16/5)
| Chg Mgmt | 2017-05-08: CM; 2017-05-15: Rollout 18/5
Rel 6.1.3 | Requirement | 2017-05-08: R; 2017-06-05: 9/5
(PCR) | Development | 2017-05-08: D; 2017-06-05: 9/5 - 12/5
| Test Preparation | 2017-05-08: TP; 2017-06-05: 10/5 - 12/5
| SIT | 2017-05-15: S; 2017-05-22: S; 2017-06-05: 15/5 - 24/5
| UAT | 2017-05-15: U; 2017-05-22: U; 2017-06-05: 15/5 - 25/5
| Chg Mgmt | 2017-05-29: CM; 2017-06-05: Rollout 31/5 (night)
R6.2 (TR Phase 1) (PCR) | FSD | bar: 2017-02-27 to 2017-08-07
| API Documentation | 2017-04-24: API Doc
| TSD - NAO & EAO | 2017-04-24: TSD; 2017-05-01: TSD
Build - NAO | bar: 2017-02-27 to 2017-08-07
Build - EAO | bar: 2017-02-27 to 2017-08-07
| DIT | 2017-05-15: DIT
Test Preparation | bar: 2017-02-27 to 2017-08-07
SIT | bar: 2017-02-27 to 2017-08-07
UAT | bar: 2017-02-27 to 2017-08-07
| Chg Mgmt | 2017-06-19: CM; 2017-06-26: Rollout 2/7
Rel 6.2.1 | Requirements | 2017-07-03: R; 2017-07-10: 4/7
| Development | 2017-07-03: D; 2017-07-10: 4/7
| Test Preparation | 2017-07-03: TP; 2017-07-10: 4/7
| SIT | 2017-07-03: S; 2017-07-10: 5/7 - 6/7
| UAT | 2017-07-03: U; 2017-07-10: 5/7 - 6/7
| Chg Mgmt | 2017-07-03: CM; 2017-07-10: Rollout 7/7 - 9pm
REL 6.3 (PCR+Defect+ Perf Enh) | Requirements | bar: 2017-02-06 to 2017-09-11
Development | bar: 2017-02-06 to 2017-09-11
Test Preparation | bar: 2017-02-06 to 2017-09-11
| SIT | 2017-06-26: S; 2017-07-03: S; 2017-07-10: S; 2017-07-17: S; 2017-07-24: S; 2017-07-31: S; 2017-08-07: S; 2017-08-14: S; 2017-08-21: SIT Sign Off 18/8
| UAT | 2017-07-17: U; 2017-07-24: U; 2017-07-31: U; 2017-08-07: U; 2017-08-14: U; 2017-08-21: UAT sign off 18/8
| Chg Mgmt | 2017-08-21: CM; 2017-08-28: Rollout 27/8
REL 6.4 (PCR + Defect) | Requirements | 2017-07-03: R; 2017-07-10: R; 2017-07-17: R; 2017-07-24: 20/7 ISD Signoff
Development | bar: 2017-07-17 to 2017-08-14
| DIT | 2017-08-21: DIT
Test Preparation | bar: 2017-08-14 to 2017-08-21
| SIT | 2017-08-28: S; 2017-09-04: S; 2017-09-11: S; 2017-09-18: S; 2017-09-25: S; 2017-10-02: S; 2017-10-09: S; 2017-10-16: S; 2017-10-23: SIT Sign Off 17/10
| UAT | 2017-09-04: U; 2017-09-11: U; 2017-09-18: U; 2017-09-25: U; 2017-10-02: U; 2017-10-09: U; 2017-10-16: U; 2017-10-23: UAT sign off 19/10
| Chg Mgmt | 2017-10-23: CM; 2017-10-30: Rollout 29/10
REL 6.5-Defects | Requirements | bar: 2015-12-07 to 2018-01-22
Development | bar: 2015-12-07 to 2018-01-22
| DIT | 2017-11-27: DIT
Test Preparation | bar: 2015-12-07 to 2018-01-22
| SIT | 2017-11-20: S; 2017-11-27: S; 2017-12-04: S; 2017-12-11: S; 2017-12-18: S; 2017-12-25: S; 2018-01-01: S; 2018-01-08: S; 2018-01-15: S; 2018-01-22: SIT signoff 19/1/18
| UAT | 2017-11-20: U; 2017-11-27: U; 2017-12-04: U; 2017-12-11: U; 2017-12-18: U; 2017-12-25: U; 2018-01-01: U; 2018-01-08: U; 2018-01-15: U; 2018-01-22: UAT signoff 19/1/18
| Chg Mgmt | 2018-01-15: CM; 2018-01-22: Rollout 21/1/18
REL 6.5.1 | Requirements | bar: 2015-12-07 to 2018-02-05
Development | bar: 2015-12-07 to 2018-02-05
| DIT | 2018-01-08: DIT
Test Preparation | bar: 2015-12-07 to 2018-02-05
| SIT | 2018-01-22: S; 2018-01-29: S; 2018-02-05: SIT signoff 31/1/18
| UAT | 2018-01-22: U; 2018-01-29: U; 2018-02-05: UAT signoff 31/1/18
| Chg Mgmt | 2018-01-29: CM; 2018-02-05: Rollout 4/2/18
REL 6.5.2 | Requirements | bar: 2015-12-07 to 2018-02-26
Development | bar: 2015-12-07 to 2018-02-26
| DIT | 2018-01-22: DIT
Test Preparation | bar: 2015-12-07 to 2018-02-26
| SIT | 2018-02-05: S; 2018-02-12: S; 2018-02-19: SIT signoff 15/2/18
| UAT | 2018-02-05: U; 2018-02-12: U; 2018-02-19: UAT signoff 15/2/18
| Chg Mgmt | 2018-02-19: CM; 2018-02-26: Rollout 19/2/18
REL 7.1 | Requirements | bar: 2015-12-07 to 2018-05-14
Development | bar: 2015-12-07 to 2018-05-14
| DIT | 2018-02-12: DIT
Test Preparation | bar: 2015-12-07 to 2018-05-14
| SIT | 2018-02-19: S; 2018-02-26: S; 2018-03-05: S; 2018-03-12: S; 2018-03-19: S; 2018-03-26: S; 2018-04-02: SIT signoff 15/3/18 - PCR, 22/3/18 - Defect
| UAT | 2018-02-26: U; 2018-03-05: U; 2018-03-12: U; 2018-03-19: U; 2018-03-26: U; 2018-04-02: U; 2018-04-09: U; 2018-04-16: U; 2018-04-23: U; 2018-04-30: U; 2018-05-07: U; 2018-05-14: UAT signoff 13/5/18 - PCR, 23/3/18 - Defect
| Chg Mgmt | 2018-05-14: CM; 2018-05-21: Rollout 20/5/18
REL 7.1.0.5 | Requirement | bar: 2018-05-21 to 2018-10-22
| Development | 2018-05-21: D; 2018-05-28: Dev 21/5
| SIT | 2018-05-21: S; 2018-05-28: SIT sign off 22/5
| UAT | 2018-05-21: U; 2018-05-28: UAT sign off 22/5
| Chg Mgmt | 2018-05-21: CM; 2018-05-28: Rollout 22/5
REL 7.1.1 | Requirements | bar: 2018-04-02 to 2018-04-16; 2018-04-30 to 2018-10-22
Development | bar: 2018-04-02 to 2018-04-16; 2018-04-30 to 2018-10-22
| DIT | 2018-04-09: DIT; 2018-04-16: DIT
Test Preparation | bar: 2018-04-09 to 2018-04-16; 2018-04-30 to 2018-10-22
| SIT | 2018-04-16: S; 2018-04-23: S; 2018-04-30: S; 2018-05-07: S; 2018-05-14: S; 2018-05-21: SIT sign off 18/5
| UAT | 2018-04-23: U; 2018-04-30: U; 2018-05-07: U; 2018-05-14: U; 2018-05-21: UAT sign off 18/5
| Chg Mgmt | 2018-05-21: CM; 2018-05-28: Rollout 27/5
REL 7.1.1 (rebaseline SIT & UAT) | Requirements | bar: 2018-04-02 to 2018-04-16; 2018-04-30 to 2018-10-22
Development | bar: 2018-04-02 to 2018-04-16; 2018-04-30 to 2018-10-22
| DIT | 2018-04-09: DIT; 2018-04-16: DIT
Test Preparation | bar: 2018-04-09 to 2018-04-16; 2018-04-30 to 2018-10-22
| SIT | 2018-04-16: S; 2018-04-23: S; 2018-04-30: S; 2018-05-07: S; 2018-05-14: S; 2018-05-21: S; 2018-05-28: SIT sign off 25/5 due to R7.1.0.5
| UAT | 2018-04-23: U; 2018-04-30: U; 2018-05-07: U; 2018-05-14: U; 2018-05-21: U; 2018-05-28: UAT sign off 25/5 due to R7.1.0.5
| Chg Mgmt | 2018-05-21: CM; 2018-05-28: Rollout 27/5
REL 7.1.2 | Requirement | 2018-05-21: R; 2018-05-28: 24/5
| Development & DIT | 2018-05-21: D; 2018-05-28: 25/5
| TP & SIT | 2018-05-21: S; 2018-05-28: SIT sign off 30/5
| UAT | 2018-05-21: U; 2018-05-28: UAT sign off 30/5
| Chg Mgmt | 2018-05-21: CM; 2018-05-28: Rollout 31/5
16IT/23A | UAT | 2018-09-17: U; 2018-09-24: UAT 21/9
LI - Affiliate Creation | Chg Mgmt | 2018-10-01: CM; 2018-10-08: CM 4/10, Cutover 9/10
REL 7.1.3 | Requirement | 2018-09-24: R; 2018-10-01: PCR761 - ISD sign off 28/9; 2018-11-19: R; 2018-11-26: PCR771 - ISD sign off 23/11
PCR746, PCR761 | Development | 2018-09-24: D; 2018-10-01: PCR 761 - 25/9-28/9; 2018-11-19: D; 2018-11-26: PCR 771 - 23/11-26/11
PCR771 | SIT | 2018-11-26: S; 2018-12-03: S; 2018-12-10: SIT 27/11 - 3/12
| UAT | 2018-11-26: U; 2018-12-03: U; 2018-12-10: UAT 27/11 - 3/12
| Change Mgmt | 2018-12-03: CM; 2018-12-10: Rollout 8/12
REL7.2 | Requirements | bar: 2018-08-27 to 2019-01-14
Parameter | Development | bar: 2018-08-27 to 2019-01-14
Performance | DIT | 2018-10-01: DIT; 2018-10-08: DIT; 2018-10-15: DIT; 2018-10-22: DIT
Defect Backlog | SIT Test Preparation | bar: 2018-09-17 to 2019-01-14
PCR 766 - teller limit | SIT | bar: 2018-09-17 to 2019-01-14
UAT | bar: 2018-09-17 to 2019-01-14
| Change Mgmt | 2019-01-14: CM; 2019-01-21: Cutover 20/1
R7.2 - PCR 765 | Requirement | bar: 2015-12-07 to 2019-01-07
PCR 765 - Guart. form adj. | Development & DIT | bar: 2015-12-07 to 2019-01-07
Test Prep & SIT | bar: 2015-12-07 to 2019-01-07
UAT | bar: 2015-12-07 to 2019-01-07
R8.0.1 | Requirement | bar: 2019-01-07
PCR767 - Teller Limit | Development/DIT | bar: 2019-01-07
Test Prep/SIT | bar: 2019-01-14 to 2019-01-21
UAT | bar: 2019-01-21 to 2019-01-28
| Change Mgmt | 2019-02-04: CM; 2019-02-11: 7/2 effective
R8.0.2 | Development/DIT | bar: 2015-12-07 to 2019-04-15
Test Prep/SIT | bar: 2015-12-07 to 2019-04-15
UAT | bar: 2015-12-07 to 2019-04-15
| Change Mgmt | 2019-03-25: CM; 2019-04-01: Cutover 31/3
R7.2 - PCR 770 | Revised ISD | 2019-01-14: R; 2019-01-21: ISD sign off 18/1
PCR 770 - TAU sharing | Development & DIT | bar: 2019-01-21 to 2019-02-04
Solution # 3 | Test Prep & SIT | bar: 2019-02-11 to 2019-03-11
UAT | bar: 2019-02-18 to 2019-03-18
PCR 787 - Upd SDIC amt | ISD | 2019-02-04: R; 2019-02-11: ISD sign off 12/1
Development & DIT | bar: 2019-02-11 to 2019-02-18
Test Prep & SIT | bar: 2019-02-18 to 2019-03-11
UAT | bar: 2019-03-04 to 2019-03-18
REL8.0.3 | Requirements | 2019-04-15: 2/4
| Development, DIT | 2019-04-15: 2/4
| Test Prep, SIT | 2019-04-15: 3/4 to 8/4
| UAT | 2019-04-15: 4/4 to 8/4
| Change Mgmt | 2019-04-15: 9/4 (effective 10/4)
REL8.1 | Requirements | bar: 2019-02-25 to 2019-05-20
Development | bar: 2019-02-25 to 2019-05-20
| DIT | 2019-03-18: DIT; 2019-03-25: DIT
SIT Test Preparation | bar: 2019-03-25 to 2019-04-08; 2019-05-06 to 2019-05-27
SIT | bar: 2019-04-08 to 2019-05-27
UAT | bar: 2019-04-08; 2019-04-22 to 2019-05-27
| Change Mgmt | 2019-05-20: CM; 2019-05-27: Cutover 28/5 (effective 29/5)
PCR794 MYR AOO | FSD | bar: 2019-04-01 to 2019-04-08
| DEV & DIT | 2019-04-15: D; 2019-04-22: D; 2019-04-29: 17/4 - 23/4
| TP & SIT | 2019-04-22: S; 2019-04-29: S; 2019-05-06: S; 2019-05-13: 24/4 - 7/5
| UAT | 2019-05-06: U; 2019-05-13: U; 2019-05-20: 6/5 - 17/5
PCR794 MYR AOO | FSD | bar: 2019-04-01 to 2019-04-08
| DEV & DIT | 2019-04-15: D; 2019-04-22: D; 2019-04-29: 17/4 - 23/4
| TP & SIT | 2019-04-29: S; 2019-05-06: S; 2019-05-13: S; 2019-05-20: 30/4 - 17/5
| UAT | 2019-05-06: U; 2019-05-13: U; 2019-05-20: 6/5 - 17/5
REL8.1.1 | DEV | 2019-05-27: D; 2019-06-03: 29/5
| SIT | 2019-05-27: S; 2019-06-03: 30/5-3/6
| UAT | 2019-05-27: U; 2019-06-03: 30/5-3/6
| Change Mgmt | 2019-05-27: CM; 2019-06-03: 4/6 night
REL8.1.2 | Requirements | bar: 2015-12-07 to 2019-06-03
Development | bar: 2015-12-07 to 2019-06-03
| SIT | 2019-06-03: S; 2019-06-10: S; 2019-06-17: SIT sign off 10/6
| UAT | 2019-06-03: U; 2019-06-10: U; 2019-06-17: UAT sign off 12/6
| Change Mgmt | 2019-06-10: CM; 2019-06-17: 15/6 , 9 pm to 10 pm
REL8.1.3 | Requirements | 2019-06-03: R; 2019-06-10: Req finalised & WO 11/6 , FSD sign off 12/6
PPS env | Development | 2019-06-03: D; 2019-06-10: D; 2019-06-17: 13/6 - 17/6
| SIT | 2019-06-10: S; 2019-06-17: 18/6 - 21/6
| UAT | 2019-06-10: U; 2019-06-17: 18/6 - 21/6
| Change Mgmt | 2019-06-10: CM; 2019-06-17: 23/6 night
REL8.1.4 | Requirements | 2019-06-17: R; 2019-06-24: ISD sign off 19/6
| Development | 2019-06-17: D; 2019-06-24: Script ready 20/6
| SIT | 2019-06-24: S; 2019-07-01: 24/6 - 25/6
| UAT | 2019-06-24: U; 2019-07-01: 25/6 - 26/6
| Change Mgmt | 2019-07-01: CM; 2019-07-08: 7/7
REL8.2 | Requirements | bar: 2019-05-13 to 2019-06-03
Development | bar: 2019-05-13 to 2019-06-03
| DIT | 2019-05-20: DIT; 2019-05-27: DIT; 2019-06-03: DIT
SIT Test Preparation | bar: 2019-04-29; 2019-05-20 to 2019-06-03
| SIT | 2019-06-10: S; 2019-06-17: S; 2019-06-24: S; 2019-07-01: S; 2019-07-08: S; 2019-07-15: S; 2019-07-22: SIT sign off 16/7/2019
UAT | bar: 2019-04-29; 2019-05-20; 2019-06-03; 2019-06-17 to 2019-07-15
| Change Mgmt | 2019-07-22: CM; 2019-07-29: Cutover 28/7
REL8.2.1 | SIT Sanity | 2019-07-29: S; 2019-08-05: S; 2019-08-12: S; 2019-08-19: S; 2019-08-26: S; 2019-09-02: S; 2019-09-09: SIT sign off 6/9
WAS Upgrade 8.5.5 | UAT | bar: 2019-07-29 to 2019-09-02; 2019-11-04
| Change Mgmt | 2019-09-09: CM; 2019-09-16: Server Upgrade 15/9
REL8.3 | Requirements | bar: 2019-06-24 to 2019-07-08
Development | bar: 2019-06-24 to 2019-07-22
| DIT | 2019-07-15: DIT; 2019-07-22: DIT
SIT Test Preparation | bar: 2019-07-01 to 2019-07-22
| SIT | 2019-07-29: S; 2019-08-05: S; 2019-08-12: S; 2019-08-19: S; 2019-08-26: S; 2019-09-02: S; 2019-09-09: S; 2019-09-16: S; 2019-09-23: S; 2019-09-30: SIT 31/7 to 23/9
UAT | bar: 2019-07-29 to 2019-09-23
| Change Mgmt | 2019-09-30: CM; 2019-10-07: Cutover 29/9
R8.3 - PCR 786 KYC | Requirement | 2019-06-24: R; 2019-07-01: R; 2019-07-08: R; 2019-07-15: FSD sign off 10/7
| Development | 2019-07-15: D; 2019-07-22: D; 2019-07-29: D; 2019-08-05: D; 2019-08-12: end 31/7
SIT Test Preparation | bar: 2019-08-05
SIT | bar: 2019-08-05 to 2019-09-09
UAT | bar: 2019-08-12 to 2019-09-09
R8.3.1 | Development | 2019-10-14: D; 2019-10-21: 17/10
| SIT | 2019-10-14: S; 2019-10-21: S; 2019-10-28: SIT 18/10 - 21/10
UAT | bar: 2019-10-14 to 2019-10-28
| Change Mgmt | 2019-11-04: CM; 2019-11-11: Cutover 24/10
REL8.3.2 | SIT (PCR 812) | 2019-09-23: S; 2019-09-30: S; 2019-10-07: S; 2019-10-14: Sign off 11/10
| SIT (PCR 820) | 2019-11-04: S; 2019-11-11: 4/11 - 8/11
| UAT | 2019-10-14: U; 2019-10-21: U; 2019-10-28: U; 2019-11-04: U; 2019-11-11: U; 2019-11-18: Sign off 13/11
| Change Mgmt | 2019-11-18: CM; 2019-11-25: Cutover 24/11
R8.4 | Requirement | 2019-07-01: R; 2019-07-08: R; 2019-07-15: R; 2019-07-22: R; 2019-07-29: R; 2019-08-05: R; 2019-08-12: R; 2019-08-19: ISD sign off 13/8
Development | bar: 2019-08-12 to 2019-09-30
| SIT | 2019-10-07: S; 2019-10-14: S; 2019-10-21: S; 2019-10-28: S; 2019-11-04: S; 2019-11-11: S; 2019-11-18: S; 2019-11-25: S; 2019-12-02: S; 2019-12-09: SIT sign off 4/12
| UAT | 2019-10-21: U; 2019-10-28: U; 2019-11-04: U; 2019-11-11: U; 2019-11-18: U; 2019-11-25: U; 2019-12-02: U; 2019-12-09: UAT sign off 6/12
| Change Mgmt | 2019-12-16: CM; 2019-12-23: Cutover 15/12
R8.4.1 | ISD | bar: 2018-10-01 to 2019-01-14; 2019-11-25
DEV | bar: 2018-10-01 to 2019-01-14; 2019-12-02 to 2019-12-09
| SIT | 2019-12-09: S; 2019-12-16: S; 2019-12-23: S; 2019-12-30: S; 2020-01-06: SIT sign off 2/1
| UAT | 2019-12-16: U; 2019-12-23: U; 2019-12-30: U; 2020-01-06: UAT sign off 2/1
| Change Mgmt | 2020-01-06: CM; 2020-01-13: Cutover 9/1, effective 10/1
R8.4.2 | ISD | bar: 2019-12-23
DEV | bar: 2019-01-07; 2019-12-30
| SIT | 2020-01-06: S; 2020-01-13: S; 2020-01-20: SIT sign off 17/1
| UAT | 2020-01-13: U; 2020-01-20: U; 2020-01-27: UAT sign off 22/1
| Change Mgmt | 2020-01-27: CM; 2020-02-03: Cutover 28/1, effective 29/1
R9.1 | DEV &SIT - sprint 1 | bar: 2020-01-06 to 2020-02-03
[215 empty] | S | S | S | S | S | 8/1-4/2
| UAT - drop 1 | 2020-02-03: U; 2020-02-10: U; 2020-02-17: U; 2020-02-24: U; 2020-03-02: U; 2020-03-09: 4/2 - 4/3
DEV &SIT - sprint 2 | bar: 2020-02-03 to 2020-02-24
[219 empty] | S | S | S | S | 5/2-26/2, SIT sign off 26/2
| UAT - drop 2 | 2020-02-10: U; 2020-02-17: U; 2020-02-24: U; 2020-03-02: U; 2020-03-09: 12/2-4/3, UAT sign off 4/3
| Change Mgmt | 2020-03-23: CM; 2020-03-30: Cutover 29/3
R9.2 | DEV &SIT - sprint 3 | bar: 2019-07-01 to 2019-09-30; 2020-01-06 to 2020-01-27; 2020-02-17 to 2020-03-02
[223 empty] | S | S | SIT sign off 13/3
| UAT | 2020-03-23: U; 2020-03-30: 23/3 - 1/4, UAT sign off 1/4
| Change Mgmt | 2020-03-30: CM; 2020-04-06: Cutover 5/4
R9.3 | DEV &SIT - sprint 3 (defect/prod backlog) | bar: 2019-07-01 to 2019-09-30; 2020-02-24 to 2020-03-30
[222 empty] | S | S | S | S | S | 27/2-25/3
| UAT - Drop 1 | 2020-04-06: U; 2020-04-13: U; 2020-04-20: U; 2020-04-27: UAT Drop 1: start 7/4
SG Project Schedule - Drop 1
| *DEV &SIT - sprint 4 (PCR 724 Part 1) | 2020-03-23: D; 2020-03-30: D; 2020-04-06: D; 2020-04-13: D; 2020-04-20: D; 2020-09-28: DEV & Unit Testing: 6/4 - 27/4
[226 empty] | S | S | S | S | S | 25/3-22/4 | [21 empty] | SIT : 13/4 - 27/4
| UAT - Drop 2 | 2020-04-20: U; 2020-04-27: U; 2020-05-04: U; 2020-05-11: U; 2020-05-18: U; 2020-05-25: UAT Drop 2: start 20/4; 2020-09-28: UAT : 20/4 - 22/6
SG Project Schedule - Drop 2
| *DEV &SIT - sprint 5 (PCR 781, 835) | 2020-04-20: D; 2020-04-27: D; 2020-05-04: D; 2020-05-11: D; 2020-05-18: D; 2020-09-28: DEV & Unit Testing: 20/4 - 25/5
[230 empty] | S | S | S | S | S | 23/4-20/5 | [17 empty] | SIT : 27/4 - 5/6
| UAT - Drop 3 | 2020-05-18: U; 2020-05-25: U; 2020-06-01: U; 2020-06-08: U; 2020-06-15: U; 2020-06-22: U; 2020-06-29: UAT Drop 3: start 18/5; 2020-09-28: UAT : 22/5 - 22/6
CRA : 2/7
| *DEV &SIT - sprint 6 (PCR 781) | 2020-05-18: D; 2020-05-25: D; 2020-06-01: D; 2020-09-28: Cutover : 19/7 26/7 30/8
[234 empty] | S | S | S | 22/5 to 5/6, SIT sign off 5/6
| UAT - Drop 3 | 2020-05-18: U; 2020-05-25: U; 2020-06-01: U; 2020-06-08: U; 2020-06-15: U; 2020-06-22: U; 2020-06-29: UAT Drop 4: start 22/5, UAT sign off 26/6
| Change Mgmt | 2020-08-24: CM; 2020-08-31: Cutover 30/8
R9.4 | DEV & SIT | bar: 2015-12-07 to 2020-09-07
[234 empty] | S | S | S | S | S | 21/5-17/6
DEV & SIT | bar: 2015-12-07 to 2020-10-19
[238 empty] | S | S | S | S | S | 18/6-15/7
| SIT - Drop 3 (5107) | 2020-08-10: S; 2020-08-17: SIT sign off 14/8
| UAT - Drop 1/2/3 | 2020-08-24: U; 2020-08-31: U; 2020-09-07: 28/8 - 11/9
| Change Mgmt | 2020-09-21: CM; 2020-09-28: Cutover 27/9
R9.4.1 | DEV | 2020-10-12: D; 2020-10-19: 12/10-14/10
| SIT | 2020-10-12: S; 2020-10-19: S; 2020-10-26: 15/10-23/10
| UAT | 2020-10-26: U; 2020-11-02: U; 2020-11-09: 26/10-4/11
| Change Mgmt | 2020-11-02: CM; 2020-11-09: Cutover 8/11
R9.5 | DEV & SIT - Drop 1 | 2020-09-07: D; 2020-09-14: D; 2020-09-21: D; 2020-09-28: D; 2020-10-05: D; 2020-10-12: 10/9-7/10
[250 empty] | S | S | S | S | S
| UAT Drop 1 | 2020-10-05: U; 2020-10-12: U; 2020-10-19: U; 2020-10-26: U; 2020-11-02: U; 2020-11-09: U; 2020-11-16: U; 2020-11-23: U; 2020-11-30: 8/10
| DEV & SIT - Drop 2 | 2020-10-05: D; 2020-10-12: D; 2020-10-19: D; 2020-10-26: D; 2020-11-02: D; 2020-11-09: 8/10-4/11 (DEV)
[254 empty] | S | S | S | S | S
| UAT Drop 2 | 2020-11-02: U; 2020-11-09: U; 2020-11-16: U; 2020-11-23: U; 2020-11-30: 6/11 to 27/11
DEV & SIT - Drop 3 | bar: 2020-04-06; 2020-11-09 to 2020-11-16; 2020-12-07; 2020-12-28 to 2021-02-22
[259 empty] | S | S | SIT sign off 20/11
| UAT Drop 3 | 2020-11-16: U; 2020-11-23: U; 2020-11-30: 16/11-27/11
| Cutover | 2020-11-30: CM; 2020-12-07: Cutover 6/12
R10.0.1 Teller Limit (to $20K) | DEV | bar: 2020-04-06; 2020-11-30 to 2020-12-07; 2021-01-04 to 2021-02-22; 2021-03-15 to 2021-03-22
| SIT | 2021-01-04: S; 2021-01-11: S; 2021-01-18: SIT sign off 14/1/2021
| FSD | 2021-01-04: FSD : 4/1/2021
| UAT | 2021-01-04: U; 2021-01-11: U; 2021-01-18: 6/1-15/1
| Cutover | 2021-01-18: CM; 2021-01-25: Cutover 21/1 (effective 22/1)
R10.1 Drop 1/2 | FSD submission 28/10 | bar: 2020-04-06; 2020-10-26 to 2020-11-16; 2020-11-30; 2021-02-22 to 2021-03-01
iDCI | FSD sign off 4/11 | bar: 2020-04-06; 2020-11-02 to 2020-11-23; 2021-02-22 to 2021-03-01
| DEV & SIT | 2020-11-09: D; 2020-11-16: D; 2020-11-23: D; 2020-11-30: D; 2020-12-07: 5/11-2/12
[260 empty] | S | S | S | S | 16/11-11/12
TSD submission 2/12 | bar: 2020-04-06; 2020-11-02 to 2020-11-16; 2020-11-30 to 2020-12-07; 2021-02-22 to 2021-03-01
| UAT | 2020-11-30: U; 2020-12-07: U; 2020-12-14: U; 2020-12-21: U; 2020-12-28: U; 2021-01-04: U; 2021-01-11: U; 2021-01-18: UAT 4/12 -13/1
| Cutover | 2021-02-01: CM; 2021-02-08: Cutover 6/2
R10.1 Drop 2 | DEV | 2020-12-07: D; 2020-12-21: 7/12 - 9/12
Remove bank codes | SIT | 2020-12-07: S; 2020-12-14: S; 2020-12-21: 10/12-18/12
FSD submission 18/12 | bar: 2020-04-06; 2020-11-02 to 2020-11-23; 2020-12-07 to 2020-12-21; 2021-02-22 to 2021-03-01
| UAT | 2020-12-21: U; 2020-12-28: U; 2021-01-04: U; 2021-01-11: U; 2021-01-18: 21/12 - 13/1
| Cutover | 2021-02-01: CM; 2021-02-08: Cutover 6/2
R10.1.1 | DEV | bar: 2020-04-06; 2020-11-30 to 2020-12-07; 2021-01-18 to 2021-02-15; 2021-03-01 to 2021-03-22; 2021-04-19
| SIT | 2021-01-18: S; 2021-01-25: S; 2021-02-01: S; 2021-02-08: S; 2021-02-15: 20/1-10/2
| FSD | 2021-01-04: FSD : 4/1/2021 (teller limit), 3/2 (remove bank code)
| UAT | 2021-02-01: U; 2021-02-08: U; 2021-02-15: 1/2-11/2
| Cutover | 2021-02-15: CM; 2021-02-22: Cutover 16/2 (effective 17/2)
R10.2 - Drop 1 | DEV | 2021-01-25: D; 2021-02-01: D; 2021-02-08: D; 2021-02-15: D; 2021-02-22: D; 2021-03-01: 28/1-24/2
| SIT | 2021-01-25: S; 2021-02-01: S; 2021-02-08: S; 2021-02-15: S; 2021-02-22: S; 2021-03-01: SIT drop 1 to be completed by 24/2
| FSD | 2021-02-22: FSD : 22/2
| UAT | 2021-03-01: U; 2021-03-08: U; 2021-03-15: U; 2021-03-22: U; 2021-03-29: U; 2021-04-05: U; 2021-04-12: 1/3-9/4
| Cutover | 2021-04-19: CM; 2021-04-26: 18/4
R10.2 - Drop 2 | DEV | 2021-02-22: D; 2021-03-01: D; 2021-03-08: D; 2021-03-15: D; 2021-03-22: D; 2021-03-29: 25/2-24/3
| SIT | 2021-02-22: S; 2021-03-01: S; 2021-03-08: S; 2021-03-15: S; 2021-03-22: S; 2021-03-29: 25/2-24/3
| FSD | 2021-03-15: FSD: one week before end of sprint
| UAT | 2021-03-22: U; 2021-03-29: U; 2021-04-05: U; 2021-04-12: 25/3-9/4
| Cutover | 2021-04-19: CM; 2021-04-26: 18/4
R10.3 | DEV - Script for new GL | 2021-04-12: D; 2021-04-19: 12/4
| POC - WC1 | 2021-04-12: D; 2021-04-19: D; 2021-04-26: 12/4-24/4 (Pre-requisite: Whitelist the TR-API URLs for Pilot & Prod env to access the TR-API via Proxy have been done before 12/4,
| DEV & DIT - WC1 | 2021-04-12: D; 2021-04-19: D; 2021-04-26: 12/4-24/4 Proxy credentials to connect API via Proxy from respective host systems ready before 12/4)
| SIT (GL) | 2021-04-12: S; 2021-04-19: S; 2021-04-26: 15/4-22/4
| SIT (WC1) | 2021-04-26: S; 2021-05-03: 26/4 to 28/4
| FSD submission (new GL) | 2021-04-12: 16/4; 2021-05-03: (FSD signed off 20/4)
| FSD submission (WC1) | 2021-04-19: 20/4; 2021-05-03: (FSD signed off 22/4)
| UAT (GL) | 2021-04-19: U; 2021-04-26: U; 2021-05-03: 23/4-30/4
| UAT (WC1) | 2021-04-26: U; 2021-05-03: 26/4-30/4
| CAB | 2021-05-03: CAB 6/5; 2021-05-24: PH: 13/5 Thu, 14/5 Fri
| Cutover | 2021-05-17: CM; 2021-05-24: 16/5
R10.4 - Drop 1 | DEV | 2021-04-19: D; 2021-04-26: D; 2021-05-03: D; 2021-05-10: D; 2021-05-17: D; 2021-05-24: 22/4-19/5; 2021-06-21: *3/5 to 17/5 - DWH Postal Code Enhancement SIT/UAT Support
| SIT | 2021-05-03: S; 2021-05-10: S; 2021-05-17: S; 2021-05-24: 3/5-19/5
| FSD submission PCR 862, 864 | 2021-05-10: 10/5
| FSD sign off | 2021-05-10: 12/5
| UAT | 2021-05-17: U; 2021-05-24: U; 2021-05-31: U; 2021-06-07: U; 2021-06-14: U; 2021-06-21: 20/5-16/6; 2021-07-12: PH: 26/5 Wed
R10.4 - Drop 2 | DEV | 2021-05-17: D; 2021-05-24: D; 2021-05-31: D; 2021-06-07: D; 2021-06-14: D; 2021-06-28: 20/5-18/6; 2021-07-26: PH: 7/6 Wed; 2021-08-16: *1st around of UAT i.e. from 31 May 2021 to 4 Jun 2021.
| SIT | 2021-05-17: S; 2021-05-24: S; 2021-05-31: S; 2021-06-07: S; 2021-06-14: S; 2021-06-21: S; 2021-06-28: S; 2021-07-05: S; 2021-07-12: 20/5-13/7
| FSD submission PCR 872 | 2021-06-07: 8/6
| FSD submission PCR 878 | 2021-06-07: 10/6
| FSD submission PCR 890 | 2021-06-21: 22/6
| FSD sign off PCR 872 | 2021-06-07: 10/6
| FSD sign off PCR 878 | 2021-06-14: 14/6
| FSD sign off PCR 890 | 2021-06-21: 24/6
| UAT | 2021-06-14: U; 2021-06-21: U; 2021-06-28: U; 2021-07-05: U; 2021-07-12: 17/6-14/7; 2021-08-16: *1st around of UAT i.e. from 31 May 2021 to 4 Jun 2021.
| CAB | 2021-07-12: 15/7; 2021-07-26: PH: 20/7 Tue
| Cutover | 2021-07-26: CM; 2021-08-02: 25/7
De-merge HSO Fixes | bar: 2021-06-28 to 2021-07-05; 2021-07-26 to 2021-08-02
| SIT Regression | 2021-07-26: S; 2021-08-02: 26/7-30/7, SIT Sign Off 30/7
| UAT Regression | 2021-07-26: U; 2021-08-02: U; 2021-08-09: 27/7 - 2/8, UAT Sign off: 2/8
| CAB | 2021-08-09: CAB 5/8
| Cutover | 2021-08-16: CM; 2021-08-23: 15/8
R11.2 | FSD | 2021-07-12: R; 2021-07-19: R; 2021-07-26: R; 2021-08-02: R; 2021-08-09: 14/7-6/8. FSD sign off on 6/9
(baseline from R10.6) | Dev + Env Setup + SIT Sanity | 2021-08-09: D; 2021-08-16: e; 2021-08-23: e; 2021-08-30: e; 2021-09-06: s
Change Id - C131565 | DIT - Host/cards | 2021-08-09: Sprint: 7/10-3/11; 2021-10-04: DIT; 2021-10-11: DIT; 2021-10-25: 4/10-15/10 (Project timeine for DEV : 6/9-29/10)
| TSD | 2021-10-18: 18/10 (submit draft TSD)
[308 empty] | New card for SIT must be available by 15/10 | [14 empty] | (delayed)
| SIT | 2021-08-09: Sprint: 7/10-3/11, 4/11-1/12, 2/12-29/12; 2021-11-01: S; 2021-11-08: S; 2021-11-15: S; 2021-11-22: S; 2021-11-29: S; 2021-12-06: S; 2021-12-13: S; 2021-12-20: S; 2021-12-27: S; 2022-01-03: S; 2022-01-10: S; 2022-01-17: ?; 2022-01-24: ?; 2022-01-31: ?; 2022-02-07: ?; 2022-02-14: 1/11-14/1 (Project timeline for SIT: 1/11-14/1). SIT test on R10.6 BL
| UAT | 2021-11-15: U; 2021-11-22: U; 2021-11-29: U; 2021-12-06: U; 2021-12-13: U; 2021-12-20: U; 2021-12-27: U; 2022-01-03: U; 2022-01-10: U; 2022-01-17: U; 2022-01-24: U; 2022-01-31: U; 2022-02-07: U; 2022-02-14: U; 2022-02-21: U; 2022-02-28: U; 2022-03-07: U; 2022-03-14: U; 2022-03-21: U; 2022-03-28: U; 2022-04-04: 16/11-31/3
| Code Merge BAU items | 2022-02-14: Code Merge from 27/1-18/2 (R11.1 Items/Upon R11.1 signoff)
| SIT Retrofit | 2022-03-07: SR; 2022-03-14: 22/2-4/3
| UAT Retrofit | 2022-03-07: UR; 2022-03-14: 22/2-4/3; 2022-04-11: (pending SG IT to confirm)
| Cutover | 2022-04-18: CM; 2022-04-25: CM; 2022-05-02: 29/4-15/4
R10.5 - Drop 1 | DEV | 2021-06-14: D; 2021-06-21: D; 2021-06-28: D; 2021-07-05: D; 2021-07-12: D; 2021-07-19: 17/6-14/7
(no item in Drop 1-PCR 870 was dropped) | SIT | bar: 2021-06-14 to 2021-08-02
FSD submission | bar: 2021-06-14 to 2021-08-02
| UAT | 2021-07-12: U; 2021-07-19: U; 2021-07-26: U; 2021-08-02: U; 2021-08-09: U; 2021-08-16: 15/7-11/8
R10.5 - Drop 2 | DEV | 2021-07-12: D; 2021-07-19: D; 2021-07-26: D; 2021-08-02: D; 2021-08-09: D; 2021-08-16: 15/7-11/8
| SIT | 2021-08-02: S; 2021-08-09: S; 2021-08-16: S; 2021-08-23: S; 2021-08-30: S; 2021-09-06: S; 2021-09-13: 3/8-8/9
| FSD submission - PCR 882 | 2021-07-26: FSD submission 27/7
| FSD submission - PCR 888 | 2021-07-26: FSD submission 30/7
| FSD submission - PCR 883 | 2021-07-26: FSD submission 20/8
| UAT - PCR 888 | 2021-08-09: U; 2021-08-16: U; 2021-08-23: U; 2021-08-30: U; 2021-09-06: U; 2021-09-13: U; 2021-09-20: U; 2021-09-27: UAT sign off 22/9
| UAT - PCR 882 | 2021-08-16: U; 2021-08-23: U; 2021-08-30: U; 2021-09-06: U; 2021-09-13: 19/8 to 7/9
| UAT - PCR 883 | 2021-08-23: U; 2021-08-30: U; 2021-09-06: U; 2021-09-13: 26/8 to 7/9
| CAB | 2021-09-20: CAB 23/9
| Cutover | 2021-10-04: CM; 2021-10-11: 3/10
R10.6 - Drop 1 | No environment for R10.6 Drop 1. Therefore R10.6 have one drop only, i.e. to start on sprint 9/9 - 6/10 Sprint 12/8 - 8/9 to work on R10.5 (PCR883) & 8 digit BIN | bar: 2021-08-09 to 2021-10-04; 2021-11-08
R10.6 | DEV (PCR870, defect 239/236) | 2021-09-06: D; 2021-09-13: D; 2021-09-20: D; 2021-09-27: D; 2021-10-04: D; 2021-10-11: 9/9-6/10
| SIT PCR 870 | 2021-09-13: S; 2021-09-20: S; 2021-09-27: S; 2021-10-04: S; 2021-10-11: 14/9-6/10
| FSD submission - PCR 870 | 2021-09-20: FSD submission 23/9
| SIT defect 239/236 | 2021-09-20: S; 2021-09-27: S; 2021-10-04: S; 2021-10-11: S; 2021-10-18: GUI: 23/9-6/10, Report: 4/10-15/10
| UAT - PCR 870 | 2021-10-04: U; 2021-10-11: U; 2021-10-18: U; 2021-10-25: U; 2021-11-01: 7/10-29/10
| UAT - Defect 239/236 | 2021-10-18: U; 2021-10-25: U; 2021-11-01: 11/10-29/10
DEV (PCR897) | bar: 2021-10-04 to 2021-11-01
SIT (PCR897) | bar: 2021-10-04 to 2021-10-18; 2021-11-01
UAT (PCR897) | bar: 2021-10-04 to 2021-11-01
| FSD submission - PCR 897 | 2021-10-18: FSD submission 20/10
DEV (defect 269) | bar: 2021-10-04 to 2021-11-01
| SIT (defect 269) | 2021-10-25: S; 2021-11-01: SIT sign off 28/10
| UAT (defect 269) | 2021-10-25: U; 2021-11-01: UAT sign off 29/10
| CAB | 2021-11-01: CAB 3/11
| Cutover | 2021-11-15: CM; 2021-11-22: 14/11
R11.0.1 | DEV - PCR 901, PCR902 | 2021-08-30: Sprint: 2/12 - 29/12; 2021-11-29: D; 2021-12-06: D; 2021-12-13: 6/12-10/12
| SIT - PCR 901, PCR902 | 2021-12-13: S; 2021-12-20: S; 2021-12-27: 13/12-27/12
| FSD - PCR 901, PCR902 | 2021-12-20: FSD 21/12
| UAT | 2021-12-13: U; 2021-12-20: U; 2021-12-27: U; 2022-01-03: 15/12-29/12
| CAB | 2021-12-27: CAB 30/12
| Cutover | 2022-01-10: CM; 2022-01-17: 11/1 (morning before start of biz)
R11.0.2 | DEV | 2022-01-03: D; 2022-01-10: 3/1-7/1
| SIT | 2022-01-10: S; 2022-01-17: S; 2022-01-24: S; 2022-01-31: 10/1-24/1
| FSD submission date | 2022-01-10: FSD 18/1
| UAT | 2022-01-10: U; 2022-01-17: U; 2022-01-24: U; 2022-01-31: 12/1-26/1
| CAB | 2022-01-24: CAB 27/1
| Cutover | 2022-02-07: CM; 2022-02-14: 7/2 (morning before start of biz)
R11.0.1.1 | DEV | 2022-01-10: D; 2022-01-17: 11/1
| SIT | 2022-01-10: S; 2022-01-17: 12/1
| UAT | 2022-01-10: U; 2022-01-17: 13/1
| CAB | 2022-01-10: CAB 17/1
| Cutover | 2022-01-17: CM; 2022-01-24: 18/1
R11.1 | DEV - PCR 889 | 2021-10-18: D; 2021-10-25: D; 2021-11-01: D; 2021-11-08: 18/10-3/11 (Sprint 7/10-3/11)
Change Id - | SIT - PCR 889 | 2021-11-01: S; 2021-11-08: 1/11-3/11
| FSD PCR 889 | 2021-11-01: FSD submssion 2/11
| DEV - PCR 879 | 2021-11-01: D; 2021-11-08: D; 2021-11-15: D; 2021-11-22: D; 2021-11-29: D; 2021-12-06: 4/11-1/12
| SIT - PCR 879 | 2021-11-29: SIT focus on 8 digit bin
| FSD - PCR 879 | 2021-11-01: FSD submssion 23/11
| DEV - PCR896 | 2022-01-03: D; 2022-01-10: D; 2022-01-17: 03/1-14/1
| SIT - PCR896 | 2022-01-03: S; 2022-01-10: S; 2022-01-17: S; 2022-01-24: S; 2022-01-31: 03/1-24/1
| FSD - PCR896 | 2021-12-27: FSD submssion 7/1
| UAT | 2021-12-27: U; 2022-01-03: U; 2022-01-10: U; 2022-01-17: U; 2022-01-24: U; 2022-01-31: U; 2022-02-07: 30/12-4/2
R11.3 (Post 8 digit BIN) | DEV | 2021-12-27: D; 2022-01-03: D; 2022-01-10: D; 2022-01-17: D; 2022-01-24: D; 2022-01-31: 30/12-26/1
To be confirmed | SIT | 2021-12-27: S; 2022-01-03: S; 2022-01-10: S; 2022-01-17: S; 2022-01-24: S; 2022-01-31: 31/12-26/1
| UAT | 2022-01-24: U; 2022-01-31: U; 2022-02-07: U; 2022-02-14: U; 2022-02-21: U; 2022-02-28: 27/1-25/2
| Code Merge BAU items | 2021-12-27: Code Merge from 30/12-31/1 (R11.0.1 Items/upon 11.0.1 signoff)
| SIT Retrofit | 2022-01-03: SR 3-5 Jan
| UAT Retrofit | 2022-01-03: UR 3-5 Jan
| CAB | 2022-02-14: CAB 17/2
| Cutover | 2022-02-21: CM; 2022-02-28: 27/2
R11.4 | DEV
SIT
UAT
CAB
Cutover
R11.3 | FSD | 2022-01-31: FSD submission
| DEV | 2022-02-14: D; 2022-02-21: D; 2022-02-28: D; 2022-03-07: 14/2-4/3
| SIT | 2022-02-28: S; 2022-03-07: S; 2022-03-14: S; 2022-03-21: S; 2022-03-28: 28/2 - 25/3
| FSD - PCR 909 | 2022-03-07: FSD Submission 1/3
| DEV - PCR 909 | 2022-03-07: D; 2022-03-14: 7/3-11/3
| SIT - PCR 909 | 2022-03-28: S; 2022-04-04: 28/3 - 1/4
| UAT | 2022-03-28: U; 2022-04-04: U; 2022-04-11: U; 2022-04-18: U; 2022-04-25: 28/3 - 29/4
| CAB | 2022-04-25: CAB 19/5
| Cutover | 2022-05-02: CM; 2022-05-09: 29/5
R11.4 | FSD - PCR 904 | 2022-03-07: FSD submission
| DEV - PCR 904 | 2022-03-07: D; 2022-03-14: D; 2022-03-21: D; 2022-03-28: D; 2022-04-04: 7/3-1/4
| SIT- PCR 904 | 2022-04-04: S; 2022-04-11: S; 2022-04-18: S; 2022-04-25: S; 2022-05-02: 4/4-30/4
| UAT | 2022-05-02: U; 2022-05-09: U; 2022-05-16: U; 2022-05-23: U; 2022-05-30: 2/5-29/5
| CAB | 2022-08-01: CAB 11/8
| Cutover | 2022-08-15: CM 20/8
R11.5 | FSD PCR 920
| DEV | 2022-04-18: D; 2022-04-25: D; 2022-05-02: D; 2022-05-09: D; 2022-05-16: 18/4-13/5
| FSD PCR927 | 2022-06-20: FSD submission
| DEV | 2022-06-20: D; 2022-06-27: 20/6-23/6
| SIT | 2022-05-16: S; 2022-05-23: S; 2022-05-30: S; 2022-06-06: S; 2022-06-13: S; 2022-06-20: S; 2022-06-27: S; 2022-07-04: 17/5- 20/7
| UAT | 2022-06-27: U; 2022-07-04: U; 2022-07-11: U; 2022-07-18: 27/6- 28/7
| FSD PCR908 | 2022-07-18: FSD submission
| DEV | 2022-07-18: D; 2022-07-25: 21/7-27/7
| SIT | 2022-07-25: S; 2022-08-01: 28/7- 5/8
| UAT | 2022-08-08: U; 2022-08-15: U; 2022-08-22: 10/8- 19/8
| CAB | 2022-08-22: CAB 26/8
| Cutover | 2022-09-05: CM; 2022-09-12: 4/9
R11.5.1 | FSD | 2022-08-01: FSD submission
Adhoc | DEV | 2022-08-29: D; 2022-09-05: 1/9-2/9
| SIT | 2022-09-05: S; 2022-09-12: S; 2022-09-19: 5/9- 15/9
| UAT | 2022-09-12: U; 2022-09-19: 12/9- 19/9
| CAB | 2022-09-19: CAB 22/9
| Cutover | 2022-10-03: CM; 2022-10-10: 2/10
R11.6 | FSD | 2022-06-20: FSD submission
Project SIT | DEV | 2022-08-08: D; 2022-08-15: D; 2022-08-22: D; 2022-08-29: 8/8-26/8
| DEV (SGRBS-332, SGRBS-334, SGRBS-336) | 2022-09-12: D; 2022-09-19: D; 2022-09-26: 12/9-20/9
| DEV (SGRBS-340) | 2022-09-26: D; 2022-10-03: 29/9-30/9
| SIT | 2022-08-22: S; 2022-08-29: S; 2022-09-05: S; 2022-09-12: S; 2022-09-19: S; 2022-09-26: S; 2022-10-03: S; 2022-10-10: S; 2022-10-17: 23/8- 13/10
| UAT | 2022-09-12: U; 2022-09-19: U; 2022-09-26: U; 2022-10-03: U; 2022-10-10: U; 2022-10-17: 12/9- 17/10
| CAB | 2022-10-17: CAB 20/10
| Cutover | 2022-10-24: CM; 2022-10-31: 30/10
R11.7 | Config and UT | 2022-08-29: Build and UT; 2022-10-03: 29/8- 23/9
Project SIT | SIT | 2022-09-26: S; 2022-10-03: S; 2022-10-10: S; 2022-10-17: S; 2022-10-24: 26/9- 21/10
| UAT | 2022-10-10: U; 2022-10-17: U; 2022-10-24: U; 2022-10-31: U; 2022-11-07: 10/10- 4/11
| Migration Mock Run(UAT) | 2022-11-07: U; 2022-11-14: 7/11- 15/11
| CAB | 2022-11-14: CAB 16/11
| Cutover | 2022-12-05: CM; 2022-12-12: 11/12
R12.0.1 | Dev(PCR 936) | 2022-11-28: D; 2022-12-05: 28/11- 30/11
Project SIT | SIT | 2022-11-28: S; 2022-12-05: S; 2022-12-12: 1/12- 9/12
| UAT | 2022-12-12: U; 2022-12-19: 12/12- 16/12
| CAB | 2022-12-19: CAB 22/12
| Cutover | 2023-01-02: CM; 2023-01-09: 3/01
R12.0.2 | Dev(PCR 937) | 2022-12-26: D; 2023-01-02: 22/12- 23/12
Project SIT | SIT | 2022-12-26: S; 2023-01-02: S; 2023-01-09: 28/12- 6/1
| UAT | 2023-01-02: U; 2023-01-09: 9/01- 13/01
| CAB | 2023-01-09: CAB 19/01
| Cutover | 2023-01-16: CM; 2023-01-23: 29/01
R12.1 | Dev(PCR 938 & 939) | 2022-12-12: D; 2022-12-19: D; 2022-12-26: D; 2023-01-02: D; 2023-01-09: 12/12- 06/01
Project SIT | SIT | 2023-01-09: S; 2023-01-16: S; 2023-01-23: S; 2023-01-30: S; 2023-02-06: 9/01- 2/2
| UAT | 2023-01-23: U; 2023-01-30: U; 2023-02-06: U; 2023-02-13: 23/01- 10/02
| CAB | 2023-02-13: CAB 16/02
| Cutover | 2023-02-20: CM; 2023-02-27: 26/01
R12.1.0 | FSD(PCR 944) | 2023-02-13: FSD Submission 20/2-21/2
| Dev | 2023-02-20: D; 2023-02-27: D; 2023-03-06: 21/2-3/3
| SIT | 2023-03-06: S; 2023-03-13: S; 2023-03-20: 6/3-17/3
| UAT | 2023-03-13: U; 2023-03-20: U; 2023-03-27: 14/3-23/3
| CAB | 2023-03-20: CAB 23/03
| Cutover | 2023-03-27: CM; 2023-04-03: 2/4
R12.1.1 | PCR 915 & PCR 942 | 2023-01-16: FSD Submission 25/1
| Dev | 2023-01-16: D; 2023-01-23: D; 2023-01-30: D; 2023-02-06: D; 2023-03-06: D; 2023-03-13: 19/01- 10/02 & 6/3 - 10/3
| Code Retrofit | 2023-03-20: C; 2023-03-27: 20/03- 21/03
| SIT | 2023-02-13: S; 2023-02-20: S; 2023-02-27: S; 2023-03-06: S; 2023-03-13: S; 2023-03-20: S; 2023-03-27: 13/02- 24/03
| UAT | 2023-03-20: U; 2023-03-27: U; 2023-04-03: U; 2023-04-10: U; 2023-04-17: 22/03- 12/04
| CAB | 2023-04-10: CAB 13/04
| Cutover | 2023-05-01: CM; 2023-05-08: 23/04
HARI
RAYA
Note on BD99: SIT SignOff: 16-Dec-2016
Note on BF100: UAT SignOff: 30-Dec-2016
Note on BG101: Rollout: 8-Jan-2016
Note on BB106: Rollout: 8-Dec-2016
Note on BH113: Rollout: 13-Jan-2017
Note on BK120: Rollout: 30-Jan-2017
Note on BQ125: SIT Sign-Off: 17-Mar-2017
Note on BR126: UAT Sign-Off: 24-Mar-2017
Note on BV127: Rollout: 23-Apr-2017
Note on BT132: SIT Sign-Off: 7-Apr-2017
Note on BU133: UAT Sign-Off: 14-Apr-2017
Note on BV134: Rollout: 23-Apr-2017
Note on CD153: SIT end date 13/6/17
Note on CD154: UAT end date 13/6/17
Note on EW238: SIT halted due to host env issue. SIT resumed on 3/12. Pointing to RB19.
Note on FU272: UAT : PCR 795 as per request from SG IT
Note on LJ471: Mohd Yusrin Bin Mohd Yusof: to extend