## WO
PCR 952
Cost Estimation
Prepared by : Ramesh Raju |  |  | 2023-03-10 |  | Version : 1.0
Between: |  |  |  | And:
Integrated Delivery House |  |  |  | Maybank Technology
20th Floor |  |  |  | Malayan Banking Berhad
Menara Maybank |  |  |  | 1 Ang Mo Kio Street 64
100, Jalan Tun Perak |  |  |  | Maybank Street Singapore 569083
50050 Kuala Lumpur
# | Services | # of Hours | # of Mandays | Cost (RM) | Comments
To provide development services as stated in the scope section of this quotation. The detail breakdown of the support as follows:
1 | Project Management | 3.6 | 0.45 | 439.88
2 | Requirement study, Functional Specification, SIT/UAT Support | 8 | 1 | 977.5
3 | Development, Unit Test, Review, SIT/UAT Support | 58 | 7.25 | 7086.88
4 | SIT Test Planning, Execution, Defect Management, UAT Support | 118.4 | 14.8 | 14467
| TOTAL | 188 | 23.5 | 22971.26
Scope
IN SCOPE
1 | BA
1.1 | Scope of Changes: 1. Writing ISD
2 | Design & Development
2.1 | Scope of Changes: RBS Enhancement ATM Card Replacement with Pin Issuance Button
3 | Testing
3.1 | Please refer to the Testing tab
OUT OF SCOPE
1 | Any other functions not listed in In-Scope
2 | UAT execution and UAT management.
3 | Host availability and environment readiness both SIT and UAT.
4 | Change of Scope and timeline.
5 | Cutover support will be under SG PPS support
6 | Any item not stated as in scope.
Timeline
# | Services | # of Mandays | Start Date | End Date | Comments
1 | Project Management | 0.45 | TBD | TBD
2 | Requirement study, Functional Specification, SIT/UAT Support | 1 | TBD | TBD
3 | Development, Unit Test, Review, SIT/UAT Support | 7.25 | TBD | TBD
4 | SIT Test Planning, Execution, Defect Management, UAT Support | 14.8 | TBD | TBD
| Reviewed By: |  |  |  | Approved By:
Fredrik Lum Yoke Fai/ Michelle Soo Wei Yin
| Date: |  |  |  | Date:

## Development
Component
Design and develop stored procedure for user profile create and delete
Design and develop stored procedure for use profile modify, suspend and restored
Update TAM audit trails for CRUD Operation for stored procedure

## Testing
Objective:
PCR#952 - IMA centralization and feasibility study on AS400, Unix apps
In Scope:
> To validate system allow to login TAM (Teller Administrator Module)
> To validate system allow to create TAM Operator ID
> To validate system allow to enter Email Address in TAM Operator Maintenance
> To validate system allow to assign Group in Operator Maintenance
> To validate system allwo to assign Drawers in Operator Maintenance
> To validate able to assign Host ID in User Mapping
> To validate system allow to Tick and Untick the ID Status in User Mapping
> To validate system allow to select/tick Officer Type / Teller Type
> To validate system allwo to perform Operator Home Branch Maintenance
> To validate system allow to login to RBS (Regional Branch Solution)
> To validate system allow to perform txns
Assumptions:
> Assume this is purely Technical CR and there will be no functional changes and impacts